

|  |  |
| --- | --- |
|  | **[Drafting note: Draft Dated:** **6 May 2024]**  Capacity Investment Scheme Agreement  [Insert Facility name]  ⎯  The Commonwealth of Australia represented by the Department of Climate Change, Energy, the Environment and Water (**Commonwealth**)  [Insert name] (ACN/ABN [insert number]) (**Operator**)  ⎯  **[Important Notice**  This is a copy of the proforma Capacity Investment Scheme Agreement (**CISA**) provided in connection with the Capacity Investment Scheme tender process being conducted by the Australian Government pursuant to the Capacity Investment Scheme South Australia and Victoria Tender Guidelines issued by the Australian Government on 15 December 2023 (**Tender Guidelines**). Capitalised terms in this Important Notice have the meaning in the Tender Guidelines.  The draft Project Documents are not an offer by the Australian Government or AEMO to enter into those documents with any entity which receives a copy of those documents and does not impose any legal commitment on the Australian Government or AEMO.  The provision of the draft Project Documents to Proponents is not intended to create legal rights for any party or to form a legally binding relationship, obligation or commitment by or involving the Australian Government or AEMO. Recipients of the draft Project Documents should not rely on them or their contents as the sole basis for making any financial, investment or business decisions. The Australian Government reserves the right to withdraw or amend the draft Project Documents at any time.] |

Capacity Investment Scheme Agreement

Details 7

Parties 7

Background 7

Agreed terms 8

1. Defined terms & interpretation 8

1.1 Defined terms 8

1.2 Interpretation 22

1.3 Order of precedence 23

1.4 Indexation 24

1.5 Commonwealth's rights, duties and functions 25

1.6 Reasonable endeavours of the Commonwealth 25

1.7 No Commonwealth Liability for Review and Approval 26

1.8 Prior approval or consent 26

1.9 Action without delay 26

1.10 Provisions limiting or excluding Liability, rights or obligations 26

1.11 Relationship of the parties 26

2. Term 27

3. Conditions Precedent 27

3.1 Commencement 27

3.2 Satisfaction of Conditions Precedent 27

3.3 Draft CP Cure Plans and CP Cure Plans 27

3.4 Failure to meet CP Sunset Date 29

3.5 Extension of CP Dates 29

3.6 Waiver of Conditions Precedent 30

4. Contract Manager for each Party 30

5. Milestone Events 30

5.1 Achievement of Milestone Events 30

5.2 Draft ME Cure Plans and ME Cure Plans 32

5.3 Failure to meet COD (Sunset) 33

5.4 Extension of dates related to Milestone Events 33

5.5 Sole consequences 34

6. Construction obligations 34

6.1 General construction obligations 34

6.2 Testing and commissioning plan 35

7. Commercial Operation 35

8. Delay and extensions 36

8.1 Extension of required dates 36

8.2 Cap on extensions 36

8.3 Unilateral Extensions 37

9. Operation and maintenance requirements 37

9.1 General operation obligations 37

9.2 Trading Protocol 37

9.3 Maintenance plan 38

9.4 Operation and scheduling 38

9.5 Bona fide and Arm's Length Arrangements 39

9.6 Emergency maintenance 39

10. Performance and Other Requirements 39

10.1 Performance Requirement obligations 39

10.2 Measurement and validation 39

10.3 Performance Requirement failures 40

10.4 The Operator is a special purpose vehicle 41

11. Authorisations 42

11.1 Authorisations 42

11.2 Notice to Commonwealth 42

12. Insurance 42

12.1 Insurances required 42

12.2 Insurer 42

12.3 Maintenance of Insurance Policies 42

12.4 Evidence of insurance 43

12.5 Non-vitiation 43

13. Alterations to the Facility 43

14. Social Licence 44

14.1 Obligation to comply 44

14.2 Reports and auditing 44

14.3 Audit 45

14.4 Non-compliance 45

14.5 SLC Cure Plan 46

14.6 Termination regarding SLCs 47

15. Knowledge Sharing 48

16. Invoicing and Payment 49

16.1 Payment Notice and Invoicing 49

16.2 Payment 50

16.3 Disputed Invoice 50

16.4 Adjustments 50

16.5 Interest on late payments 51

16.6 Set off 51

17. Taxes 52

18. GST 52

18.1 Definitions and interpretation 52

18.2 GST Exclusive Consideration 52

18.3 Barter supply 52

18.4 GST gross-up 52

18.5 Payments and reimbursements 53

18.6 Adjustments 53

18.7 No Partnership 53

19. Force Majeure 53

19.1 Project Force Majeure Event 53

19.2 Connection Force Majeure Event 54

19.3 Notification 55

19.4 Suspension of obligations 55

19.5 Accrued rights and obligations 55

19.6 Extension 55

19.7 Mitigation 56

19.8 Impact on payments 56

19.9 Termination for extended Force Majeure Event 56

19.10 Cessation 56

19.11 Pre-existing Force Majeure Event 56

20. Reinstatement 56

20.1 Reinstatement Event 56

20.2 Reinstatement plan 57

20.3 Consequences of failing to reinstate 58

20.4 Obligation to reinstate 58

21. Change in Law 58

21.1 Change in Law 58

21.2 Exclusions 59

21.3 Mitigation 59

21.4 Notice 59

21.5 Adjustment to the Annual Payment Cap, Annual Revenue Ceiling and Annual Revenue Floor 59

22. Termination 60

22.1 Termination for Convenience by the Commonwealth 60

22.2 Termination by the Commonwealth for Operator Default 60

22.3 Termination by the Operator for Commonwealth Default 62

22.4 Preservation of rights 62

22.5 Sole basis of termination 62

23. Payments on Termination 62

23.1 Fixed Termination Payment and Early Termination Payment 63

23.2 Sole remedy 63

23.3 Unenforceability 63

23.4 Invoice 64

24. Assignment and Change in Control 64

24.1 Assignment or Novation By Operator 64

24.2 Security Interest 65

24.3 Assignment or Novation by Commonwealth 65

24.4 Non-compliance 65

24.5 Change in Control 65

25. Risk and Liability 66

25.1 Indemnity 66

25.2 Consequential Loss and Limitation of liability 67

25.3 Benefits held on trust 68

26. Representations and Warranties by the Operator 68

26.1 General warranties 68

26.2 Operator warranties 68

26.3 Tender matters 69

26.4 Repetition 69

26.5 Trustee representations and warranties 69

26.6 Trustee undertakings 70

26.7 Restrictions on the Trustee 70

26.8 Trustee limitation of liability 70

26.9 No reliance 71

27. Performance Security 71

28. Intellectual Property 73

28.1 Project Intellectual Property 73

28.2 Licence of Specified Material 73

28.3 Moral rights 73

28.4 Warranties 73

28.5 Intellectual Property Indemnity 73

28.6 Remedy for breach of warranty 74

29. Subcontracting 74

29.1 Operator remains responsible 74

29.2 Key Subcontractors 74

30. Confidentiality 75

30.1 Confidential Information not to be Disclosed 75

30.2 Exception to obligations of Confidentiality 75

30.3 Freedom of information 76

31. Access, records and reporting 77

31.1 Operator to retain records 77

31.2 Access to records 77

31.3 Other information 78

31.4 Right to access and audit 78

31.5 Site Inspection 79

32. Reporting 80

32.1 CP Period Reporting 80

32.2 Construction Period Reporting 80

32.3 Operating reports 81

32.4 Revenue reports 82

32.5 Capacity Products and Green Product reporting 82

32.6 Foreign Acquisitions and Takeovers Act reporting 82

32.7 Assurances 83

32.8 Provision of further information 83

33. Publicity 83

34. Relevant Commonwealth Policies and Other Requirements 84

35. Dispute Resolution 84

35.1 Dispute mechanism 84

35.2 No proceedings 84

35.3 Disputes 84

35.4 Procedure to resolve Disputes 84

35.5 Negotiation 84

35.6 Independent Expert 85

35.7 Other relief 86

35.8 Continued performance following a Dispute 86

35.9 Interim relief 86

36. Pooled Disputes 86

36.1 Referral of Pooled Disputes 86

36.2 Resolution by Pooled Dispute Panel 86

36.3 Bilateral resolution 87

37. Governing Law 87

38. Notices 87

38.1 Form 87

38.2 Delivery 87

38.3 When effective 88

38.4 When taken to be received 88

38.5 Receipt outside business hours 88

39. General 88

39.1 Variation and waiver 88

39.2 Consents, approvals or waivers 88

39.3 Discretion in exercising rights 89

39.4 Partial exercising of rights 89

39.5 Remedies cumulative 89

39.6 Indemnities and reimbursement obligations 89

39.7 Supervening law 89

39.8 Counterparts 89

39.9 Entire agreement 90

39.10 Expenses and no liability for loss 90

39.11 Rules of construction 90

39.12 Severability 90

39.13 Survival 90

39.14 Proportionate liability 90

39.15 Further steps 90

Schedule 1 – Reference Details 91

Schedule 2 - Conditions Precedent 95

Schedule 3 - Milestone Events and Milestone Dates (Scheduled) 97

Schedule 4 – Payment Mechanism 98

Schedule 5 – Termination Payments 104

Schedule 6 – Knowledge Sharing Plan 106

Schedule 7 – Key Subcontractors 109

Schedule 8 – Social Licence Commitments 110

Schedule 9 – Form of Tripartite Deed 112

Schedule 10 – Form of Performance Security 135

Schedule 11 - Commonwealth Policy and Other Requirements 136

Signing page 144

Details

|  |  |
| --- | --- |
| Date |  |

Parties

|  |  |
| --- | --- |
| Name | **The Commonwealth of Australia** represented by the **Department of Climate Change, Energy, the Environment and Water** |
| Short form name | **Commonwealth** |
| Notice details | [insert address]  Email: [insert] |
|  | Attention: [insert] |

|  |  |
| --- | --- |
| Name | **[insert name] (**ACN/ABN [insert]) |
| Short form name | **Operator** |
| Notice details | [insert address]  Email: [insert] |
|  | Attention: [insert] |

Background

1. Following a competitive tender process, the Operator has been awarded this long term revenue support agreement in respect of the Facility by the Commonwealth.
2. As a condition of the award of this Agreement, the Operator has agreed to design, construct, commission, test, complete, operate, manage and maintain the Facility in each case in accordance with this Agreement
3. Amongst other things, the parties will make the payments set out in Schedule 4 during the Support Period.

Agreed terms

1. Defined terms & interpretation
   1. Defined terms
2. In this document:
3. **Accounts and Records** has the meaning given in clause 31.1(a).
4. **Adjusted Net Operational Revenue** has the meaning given in section 11 of Schedule 4.
5. **AEMO** means the Australian Energy Market Operator Limited ACN 072 010 327, or any successor entity that is the market operator from time to time under the National Electricity Law.
6. **Affected Party** means the party affected by the event or circumstance that constitutes a Force Majeure Event.
7. **Aggregate Annual Rebate** has the meaning given in section 8 of Schedule 4.
8. **Ancillary Services** has the meaning given in the NER.
9. **Annual Payment Cap** has the meaning given in Schedule 1.
10. **Annual Reconciliation Payment** has the meaning given in section 6 of Schedule 4.
11. **Annual Revenue Ceiling** has the meaning given in Schedule 1.
12. **Annual Revenue Floor** has the meaning given in Schedule 1.
13. **Annual Revenue Sharing Amount** has the meaning given in section 10 of Schedule 4.
14. **Annual Storage Capacity Report** has the meaning given in clause 32.3(b).
15. **Annual Support Amount** has the meaning given in section 9 of Schedule 4.
16. **Approved Reinstatement Plan** has the meaning given in clause 20.2.
17. **Associate**, in respect of a party, means that party's officers, employees, servants, agents, advisers, consultants, contractors and direct or indirect subcontractors.
18. **Audit** means an audit and inspection conducted in accordance with clause 31.4.
19. **Auditor** has the meaning given in clause 31.4(a).
20. **Authorisation** means any applicable consent, licence, approval, permit, registration, accreditation, determination, certificate, registration, permission, filing or other authorisation that is required to be issued by or obtained from any Government Agency or in accordance with any Law.
21. **Authorised Bank** means a bank or financial institution that is the holder of a current licence and is regulated by the Australian Prudential Regulation Authority, or an equivalent regulatory authority in its place of incorporation and which has the Required Rating.
22. **Availability Rebate** has the meaning given in section 4.1 of Schedule 4.
23. **Availability Rebate Percentage** has the meaning given in section 4.2 of Schedule 4.
24. **Background Intellectual Property** means any Intellectual Property developed independently of the Project and used by or on behalf of the Operator for the purpose of undertaking the Project.
25. **Bid** means a ‘dispatch bid’ (as defined in the NER) made in accordance with this Agreement and the NER in respect of the Project.
26. **Breach Notice** has the meaning given in clause 22.2(e)(i).
27. **Business Day** means:
    1. for receiving a Notice under clause 38, a day that is not a Saturday, Sunday, public holiday or bank holiday in the place where the notice is received and not in the period 25 December to 1 January (inclusive); and
    2. for all other purposes, a day that is not a Saturday, Sunday, bank holiday or public holiday in the capital city of the Relevant Jurisdiction or the Australian Capital Territory.
28. **Capacity Product** means any right, entitlement, credit, offset, allowance, compensation, payment, benefit or certificate of any kind, recognised or arising under any scheme, Law, policy or arrangement which becomes available to the owner or operator of an energy storage system or generating facility that is attributable to the capacity or availability of the Project, but not including any Green Products or any Ancillary Services.
29. **Change in Control** occurs in relation to the Operator (whether alone or together with any Associate or Associates) where:
    1. a person who does not Control the Operator acquires such Control;
    2. a person that Controls the Operator ceases to have such Control;
    3. if the Operator is a trust, a change in the manager, trustee or Responsible Entity of the Operator,

but in each case does not include a change in Control of the Operator which occurs as a result of:

* 1. the Operator or any of its Related Bodies Corporate becoming listed on the Australian Stock Exchange or other recognised securities exchange;
  2. a transfer of or other dealing in shares in the Operator or any of its Related Bodies Corporate that are listed on the Australian Stock Exchange or other recognised securities exchange; or
  3. an internal restructure or reorganisation, provided that the restructuring or reorganisation does not result in a change to the Ultimate Holding Company (as defined in the Corporations Act) of the Operator.

For the purposes of this definition of Change in Control, "Associate" or "Associates" has the meaning given in the Corporations Act and includes a person deemed to be an associate of a designated body (within the meaning of section 12 of the Corporations Act).

1. **Change in Law** means:
   1. a change in or repeal of any part of the NEL or the NER or a change in the way the NEL or NER is applied or interpreted as a result of a decision of a court of competent jurisdiction after the Signing Date; or
   2. a change in, repeal of any part of a Law, or change in the way a Law is applied or interpreted as a result of a decision of a court of competent jurisdiction after the Signing Date, in each case which expressly or exclusively applies to the Project, the Facility, its assets or the Project area or to the Operator but only in its capacity as the person contracting with the Commonwealth to implement the Project,

but which expressly excludes:

* 1. any of the events referred to in paragraph (a) or (b) which:
     1. had been published in the Commonwealth of Australia Gazette or the Victorian or South Australian Government Gazette, as the case may be, by way of a bill, draft bill or draft statutory instrument or had been otherwise specifically referred to publicly prior to the Signing Date;
     2. a party performing activities in accordance with Good Industry Practice which are similar to the activities which the Operator is required to perform under this Agreement would have reasonably foreseen or anticipated a change similar to or having a similar effect on the rights and obligations of the Operator prior to the Signing Date;
     3. is substantially the same as a Law in force prior to the Signing Date;
     4. in the case of the NER referred to in paragraph (a) only, as at the Signing Date was the subject of a final determination of the Australian Energy Market Commission, agreement of the Energy Ministers or a rule change by the South Australian Minister for Energy; or
  2. any of the changes described in clause 21.2.

1. **Claim** means any claim, action, demand, suit or proceeding (including for breach of contract, tort (including negligence) or any other common law, equitable or statutory cause of action or by way of contribution or indemnity) made under any Project Document or otherwise at Law in connection with the Project, including for specific performance, restitution, payment of money (including damages), an extension of time or any other form of relief or remedy.
2. **COD** or **Commercial Operation Date** means the date on which Commercial Operation is achieved.
3. **COD Condition** has the meaning given in clause 7(a).
4. **COD (Sunset)** has the meaning given in Schedule 1.
5. **COD (Target)** has the meaning given in Schedule 1.
6. **Commencement Date** has the meaning given in clause 3.2(d).
7. **Commercial Close** means the time at which:
   1. the Operator has secured the equity and/or internal shareholder debt financing that is required to fund the construction and commissioning of the Project; and
   2. the Operator issues an unconditional notice to proceed for the full scope of work under the engineering, procurement and construction contract (or equivalent) for the Project.
8. **Commercial Operation** means that:
   1. all COD Conditions have either been satisfied by the Operator in accordance with clause 7(a) or waived by the Commonwealth; and
   2. the Operator has provided to the Commonwealth all notices and accompanying documents referred to in clause 5.1.
9. **Communications** has the meaning given in clause 38.1.
10. **Condition Precedent** means each condition specified in Schedule 2.
11. **Condition Precedent Date** means, for each Condition Precedent, the relevant date identified as the Condition Precedent Date in Schedule 2 (as such date may be adjusted pursuant to this Agreement).
12. **Confidential Information** means information (regardless of its form) that is by its nature confidential and:
    1. is designated by a party as confidential; or
    2. a party knows or ought to know is confidential,

but does not include information which:

* 1. is in the public domain or becomes publicly available other than through a breach of any Project Document including clause 30 or any other confidentiality obligation of the disclosing party;
  2. has been independently developed or acquired by the party which receives that information; and
  3. is disclosed with the prior written consent of the party which provided the information (such consent not to be unreasonably withheld or delayed) to the other party.

1. **Connection Force Majeure** **Event** has the meaning given in clause 19.2.
2. **Connection Point** means the "connection point" (as defined in the NER) for the Facility.
3. **Consolidated Group** means a Consolidated Group or MEC (Multiple Entry Consolidated) group as those terms are defined in section 995-1 of the *Income Tax Assessment Act 1997* (Cth).
4. **Construction Contracts** means any one or more contracts between the Operator and its subcontractors which when performed in the aggregate will result in the completion of the design, construction, commissioning and testing of the Facility to enable it to comply with the Performance Requirements.

**Construction Period** means the periodcommencing on the Commencement Date and ending on the earlier of:

* 1. COD; and
  2. the date this Agreement is terminated or otherwise ends.

**Contract Manager** has the meaning given in clause4(a).

1. **Contracted Capacity** has the meaning given in Schedule 1.

**Contracted Percentage** has the meaning given in Schedule 1.

**Control** has the meaning given in section 50AA of the Corporations Act, except that:

* 1. the application of section 50AA(4) will be disregarded;
  2. in the case of a body corporate, it includes the direct or indirect right to exercise more than 50% of the votes exercisable at a general meeting of that body corporate and the direct or indirect right to appoint more than 50% of its directors;
  3. in the case of a trust, it includes the direct or indirect right to exercise more than 50% of the votes exercisable by the beneficiaries of that trust in their capacity as beneficiaries and the ability to appoint or remove the trustee of the trust;
  4. in the case of any other person, it includes the direct or indirect right to exercise more than 50% of the voting rights in the person; and
  5. in the case of any person (including those listed in paragraphs (b) to (d) above), it includes the direct or indirect capacity to determine the outcome of decisions about the person’s financial and operating policies,

1. and **Controlled** has a corresponding meaning.
2. **Controller** means, in relation to a Change in Control of the Operator, the person or body corporate to whom Control will pass.
3. **Corporations Act** means the *Corporations Act 2001* (Cth).
4. **Corrected GST Amount** has the meaning given in clause 18.6(a).
5. **Cost Change Principles** means the following principles to be applied in determining an adjustment to the Annual Payment Cap, Annual Revenue Ceiling and Annual Revenue Floor:
   1. the cost or benefit passed through to the Commonwealth will not include the Cost Change Threshold amount;
   2. any adjustment to the Annual Payment Cap, Annual Revenue Ceiling and Annual Revenue Floor will commence at the start of the next Financial Year;
   3. the adjusted Annual Payment Cap, Annual Revenue Ceiling and Annual Revenue Floor may vary throughout the remaining Term, provided that any such variation(s) occurs at the start of the next Financial Year;
   4. the adjustment will reflect the impact of the Change in Law on the Operator had the Operator used reasonable endeavours to mitigate additional costs and maximise reductions in costs in accordance with clause 21.3;
   5. any increase in the Operator’s costs will be discounted for any related economic benefit to the Operator associated with the relevant Change in Law (including any tax benefits); and
   6. where the most efficient response to the Change in Law involves the incurring of capital expenditure by the Operator, in determining the Relevant Cost Change which applies to the Change in Law the cost of that capital expenditure will be annualised and allocated on a proportional basis over the longer of the remaining part of the Term and the expected useful economic life of the relevant capital item.
6. **Cost Change Threshold** means $2 million (Indexed).
7. **CP Cure Plan** has the meaning given in clause 3.3(f).
8. **CPI** means the Consumer Price Index (All Groups) weighted average of the eight capital cities of Australia as published for a Quarter by the Australian Bureau of Statistics or if clause 1.4(c) applies, the index determined in accordance with clause 1.4(c).
9. **CP Period** means the period commencing on the Signing Date and ending on the earlier of the Commencement Date and CP Sunset Date.
10. **CP Sunset Date** has the meaning given in Schedule 1 as such date may be adjusted pursuant to the terms of this Agreement.
11. **CP Target Date** has the meaning given in Schedule 1 as such date may be adjusted pursuant to the terms of this Agreement.
12. **Deemed Availability Period** has the meaning given in section 4.3(b) of Schedule 4.
13. **Default Interest Rate** means the rate which is the Australian Tax Office General Interest Charge rate current at the due date of payment expressed as a percentage.
14. **Dispute** has the meaning given in clause 35.1.
15. **Disputed Amount** has the meaning given in clause 16.3(a).
16. **Dispute Notice** has the meaning given in clause35.3.
17. **Draft CP Cure Plan** has the meaning given in clause 3.3(a).
18. **Draft ME Cure Plan** has the meaning given in clause 5.2(a).

**Draft PR Cure Plan** has the meaning given in clause 10.3(c)(iv).

**Draft SLC Cure Plan** has the meaning given in clause 14.5(a).

**Early Termination Payment** has the meaning given in Schedule 5.

**Election to Reinstate** has the meaning given in clause 20.1(a).

**Energy** means electricity exported to the Network by the Facility as measured at the Metering Point.

**Entity** has the meaning given in section 64A of the Corporations Act, but is also deemed to include a joint venture within the meaning of Australian Accounting Standard 131 (AASB 131).

1. **Environment** means the physical factors of the surroundings of humans and other life forms, including the land, soil, plants, habitat, waters, atmosphere, climate, sounds, odours, tastes, biodiversity and the social and aesthetic characteristics.
2. **Equivalent Availability Factor** means the amount determined in accordance with section 4.3 of Schedule 4**.**
3. **Equivalent Availability Threshold** means 90%.
4. **Expiry Date** means the Final Expiry Date, unless this Agreement is terminated or ends prior to that date in which case the Expiry Date will be the date of that termination or end.
5. **Facility** has the meaning given in Schedule 1.
6. **Final Expiry Date** has the meaning given in Schedule 1.
7. **Final Support Commencement Date** has the meaning given in Schedule 1.
8. **Financial Close** means the time at which:
   1. the Operator has secured the equity and external debt financing that is required to fund the construction and commissioning of the Project, and all conditions precedent to first draw down under that financing have been satisfied or waived (other than any condition relating to this Agreement becoming unconditional); and
   2. the Operator issues an unconditional notice to proceed for the full scope of work under the engineering, procurement and construction contract (or equivalent) for the Project.
9. **Financial Year** means:
   1. for the first Financial Year, the period commencing on the Signing Date until the next 30 June;
   2. subject to paragraph (c) of this definition, each subsequent 12 Month period commencing on 1 July and ending on 30 June; and
   3. for the final Financial Year, the period from the end of the last full Financial Year (as identified in paragraph (b) of this definition) to the Expiry Date,

unless this Agreement is terminated or ends earlier, in which case the last Financial Year will be the period from the end of the last full Financial Year (as identified in paragraph (b) of this definition) immediately preceding the termination or end date to the Expiry Date.

1. **Financier** means any person or organisation which provides funding to the Operator, or a Related Body Corporate of the Operator, for the Project under a Funding Agreement.
2. **Fixed Termination Payment** has the meaning given in Schedule 5.
3. **Force Majeure Event** means a Project Force Majeure Event or a Connection Force Majeure Event.
4. **Funding Agreement** means any agreement under which funding is provided for the Project, security is granted by the Operator in respect of that funding and/or derivatives are entered into by the Operator for the Project.
5. **Good Faith** means acting honestly, reasonably, with fair dealing and in a manner consistent with and which does not undermine this Agreement
6. **Good Industry Practice** means Good Construction Industry Practice and Good Electricity Industry Practice or either one of them (as the case may be).
7. **Good Construction Industry Practice** means the exercise of that degree of skill, care, diligence, efficiency, prudence and foresight that would be expected from skilled and experienced and internationally recognised designers, engineers and constructors of facilities of a similar type, size and value to the Facility under conditions comparable to the Project, consistent with applicable Laws, Authorisations, industry codes and standards.
8. **Good Electricity Industry Practice** has the meaning given in the National Electricity Rules.
9. **Government Agency** means a government, government department or other body, or a governmental, semi-governmental, judicial, municipal, statutory or public entity or authority (including a statutory authority, a State owned enterprise or a corporate Commonwealth entity), a self-regulatory authority established under statute, or a stock exchange (wherever created or located) or a person (whether or autonomous or not) who is charged with the administration of the Law.
10. **Green Product** means any right, entitlement, credit, offset, allowance, compensation, payment, benefit or certificate of any kind, recognised or arising under any scheme, Law, policy or arrangement which may be created in respect of, or relate to, the regulation or reduction of greenhouse gas emissions and which becomes available to the owner or operator of an energy storage system or generating facility that is attributable to the Project.
11. **GST Amount** has the meaning given in clause 18.4(a).
12. **GST Exclusive Consideration** has the meaning given in clause 18.4(a).
13. **GST Group** means a GST group formed in accordance with Division 48 of the GST Law and any related act imposing such tax or legislation that is enacted to validate, recapture or recoup such tax.
14. **GST Law** has the meaning given to that term in the *A New Tax System (Goods and Services Tax) Act 1999* (Cth).
15. **Import Capacity** has the meaning given in Schedule 1.
16. **Independent Expert** has the meaning given in clause 35.6.
17. **Indexed** means the relevant amount is to be indexed in accordance with the CPI Factor set out in clause 1.4.
18. **Input Resource** means the energy available at the Connection Point.
19. **Insolvency Event** means, in respect of the Operator:
    1. it is (or states that it is) an insolvent under administration or insolvent (each as defined in the Corporations Act);
    2. it is in liquidation, in provisional liquidation, under administration or wound up or has had a “controller” (as defined in the Corporations Act) appointed to all or substantially all of its property;
    3. it is subject to any arrangement (including a deed of company arrangement or scheme of arrangement), assignment, moratorium or compromise or composition, protected from creditors under any statute or dissolved (in each case, other than to carry out a reconstruction or amalgamation while solvent on terms approved by the other parties to this Agreement);
    4. an application or order has been made (and in the case of an application which is disputed by the person, it is not stayed, withdrawn or dismissed within 20 Business Days), resolution passed, proposal put forward or any other action taken, in each case in connection with that person, which is preparatory to or could result in any of the things described in paragraphs (a), (b) or (c) or any other action taken, in each case in connection with that person, in respect of any of the things described in paragraphs (a), (b) or (c);
    5. it is taken (under section 459F(1) of the Corporations Act) to have failed to comply with a statutory demand;
    6. it is the subject of an event described in section 459C(2)(b) or section 585 of the Corporations Act (or it makes a statement from which the Commonwealth reasonably deduces it is so subject);
    7. it is otherwise unable to pay its debts when they fall due; or
    8. something having a substantially similar effect to any of the things described in paragraphs (a) to (g) happens in connection with the Operator under the law of any jurisdiction.
20. **Insurance Policies** means the policies specified in clause 12.1.
21. **Intellectual Property** means all intellectual property rights, including the following rights:
    1. patents, copyright (including future copyright), rights in circuit layouts, designs, trade and service marks (including goodwill in those marks), know how, domain names and trade names and any right to have information kept confidential;
    2. any application or right to apply for registration of any of the rights referred to in paragraph (a); and
    3. all rights of a similar nature to any of the rights in paragraphs (a) and (b) that may subsist anywhere in the world (including Australia),

whether or not such rights are registered or capable of being registered.

1. **Key Subcontract** means a contract between the Operator and any Key Subcontractor and any direct or indirect Key Subcontractor which performs any part of the Operator's obligations under any Transaction Document.
2. **Key Subcontractor** means a Subcontractor: **[Drafting note: this value will be set as a percentage of total capital expenditure being 20% of Capex during the Construction Period and 50% of annual Opex during the Operations Period. The shortlisted Proponent is required to provide that information as part of its Financial Value Bid in Stage B of the Tender Process.]** 
   1. specified as such in Schedule 7;
   2. under a Subcontract which has a contract value of more than $[insert amount] (Indexed) in the Construction Period;
   3. whose various Subcontracts have an aggregate value of more than $[insert amount] (Indexed) in the Construction Period;
   4. under a Subcontract which has a contract value of more than $[insert amount] (Indexed) in the Operations Period; and
   5. whose various Subcontracts have an aggregate value of more than $[insert amount] (Indexed) in the Operations Period,

and any replacement of that Subcontractor in accordance with this Agreement.

**Knowledge Sharing Deliverables** means the deliverables set out in the Knowledge Sharing Plan.

**Knowledge Sharing Plan** means the knowledge sharing plan set out in Schedule 6.

1. **Law** means:
   1. those principles of common law and equity established by decisions of courts;
   2. any legislation or regulation including the NER; or
   3. any Authorisation (including any conditions or requirements under them) which is issued under an instrument referred to in paragraph (b) of this definition.
2. **Legislation** means:
   1. legislation and delegated legislation of the Commonwealth or any State or Territory of the Commonwealth;
   2. all ordinances, by-laws, regulations of and other statutory instruments (however described) issued under the legislation or delegated legislation described in paragraph (a) of this definition of Legislation; and
   3. consolidations, amendments, re-enactments and replacements of legislation or delegated legislation described in paragraph (a) of this definition of Legislation,
3. but excludes Authorisations.
4. **Liability** means any debt, obligation, claim, action, cost (including legal costs, deductibles or increased premiums), expense, loss (whether direct or indirect), damage, compensation, charge or liability of any kind (including fines or penalties), whether it is:
   1. actual, prospective or contingent; or
   2. currently ascertainable or not,
5. and whether under or in any way in connection with any of the Project Documents or arising at Law.
6. **Location** means the region of the NEM in relation to which the Project is to be registered, and **Located** has a corresponding meaning
7. **Loss** means any loss, damage, liability, cost or expense (including legal expenses on a full indemnity basis) of any kind suffered or incurred or agreed to be paid by way of settlement or compromise.
8. **Maximum Capacity** has the meaning given in Schedule 1.
9. **ME Cure Plan** has the meaning given in clause 5.2(f).
10. **Metering Point** has the meaning given in Schedule 1.
11. **Milestone Event** means each milestone described in Schedule 3.
12. **Milestone Date (Scheduled)** means, in respect of a Milestone Event, the Milestone Dates (Scheduled) identified as such in Schedule 3 in respect of that Milestone Event (as such date may be adjusted pursuant to this Agreement).
13. **Minimum Hours** has themeaning given in Schedule 1.
14. **Minimum State of Charge** has themeaning given in Schedule 1.
15. **Month** means a calendar month.
16. **National Electricity Law** means the National Electricity Law set out in the schedule to the *National Electricity (South Australia) Act 1996* (SA) as it applies in the Relevant Jurisdiction.
17. **National Electricity Market** and **NEM** means the national electricity market managed by AEMO pursuant to the National Electricity Law and the National Electricity Rules.
18. **National Electricity Rules** and **NER** means the National Electricity Rules made under the National Electricity Law, as it is applied in the Relevant Jurisdiction.
19. **Net Annual Payment** has the meaning given in section 7 of Schedule 4.
20. **Net Operational Revenue** means, for a period, the Operational Revenue for that period less the Permitted Costs for that period.
21. **Network** means the transmission or distribution network (as applicable) to which the Facility is connected at its Connection Point.
22. **Network Support Services** means any service provided by the Facility to support a transmission network or a distribution network, including any service that is an alternative to network augmentation.
23. **Notice to Proceed Date** has the meaning given in Schedule 1.
24. **Offtake Contract** means any contract, arrangement or understanding entered into by the Operator arising from or in connection with:
    1. electricity imported and/or exported by the Project;
    2. the supply of Ancillary Services by the Project;
    3. the availability or use of the Rated Capacity, Registered Capacity or Maximum Capacity of the Project; and/or
    4. the availability or use of the energy Storage Capacity of the Project.
25. To avoid doubt, without limitation an Offtake Contract may take the form of:
    1. a purchase contract;
    2. subject to clause 9.5, a tolling contract, a lease or such other arrangement as gives a third party the economic benefit of the Project for a period of time;
    3. an underwriting arrangement in respect of the profit or revenue of the Project or the Operator; and/or
    4. a derivative, forward, option or any such combination where the consideration under it is derived by reference to electricity, Capacity Products or Green Products.
26. **Operational Revenue** means, in respect of a period, the revenue of the Operator determined on a cashflow basis in that period (without double counting), including amounts:
    1. from the sale of electricity, hedges arising from or in connection with the Project and/or the Project (excluding interest rate and foreign currency hedges), Capacity Products or Green Products;
    2. from the supply of Ancillary Services, Network Support Services or System Support Services;
    3. to the extent not referred to above, under an Offtake Contract;
    4. to the extent not referred to above, from AEMO (in its capacity as a market body) in respect of the Facility in accordance with the NEL and NER,

but excluding:

* 1. amounts which the Commonwealth is obliged to pay to the Operator under this Agreement;
  2. damages to which the Operator is entitled under a Construction Contract or a contract for the operation and/or maintenance of the Facility (except to the extent those damages compensate for loss of revenue and/or profit); and
  3. amounts to which the Operator is entitled under or in connection with an insurance policy (other than amounts which compensate for loss of revenue and/or profit).

1. **Operations Period** means the period commencing on the day after COD and ending on the Expiry Date.
2. **Operations Year** means
   1. for the first Operations Year, the period commencing on the first day after COD until the next 30 June;
   2. subject to paragraph (c) of this definition, each subsequent 12 Month period during the Operations Period commencing on 1 July and ending on 30 June; and
   3. for the final Operations Year, the period from the end of the last full Operations Year (as identified in paragraph (b) of this definition) to the Expiry Date,

unless this Agreement is terminated or ends earlier, in which case the last Operations Year will be the period from the end of the last full Operations Year (as identified in paragraph (b) of this definition) immediately preceding the termination or end date to the Expiry Date.

1. **Operator Party** means any Related Body Corporate of the Operator and/or any Associate of the Operator or Related Body Corporate of the Operator.
2. **Other Agreement** means another agreement materially similar to this Agreement in relation to the Capacity Investment Scheme and titled "Capacity Investment Scheme Agreement" to which the Commonwealth is a party, other than this Agreement.
3. **Other Counterparty** means, in respect of an Other Agreement, the Commonwealth's counterparty under that Other Agreement.
4. **Other Dispute** means a dispute between the Commonwealth and an Other Counterparty under an Other Agreement.
5. **Pandemic** means:
   1. COVID-19; and
   2. any other infectious disease that is declared as a pandemic by the World Health Organisation after the date of this Deed.
6. **Pandemic Change in Law** means (if it takes effect after the date of this Agreement):
   1. a change in (including any extension, repeal, revocation or expiry of) Legislation in response to a Pandemic;
   2. new Legislation in response to a Pandemic; or
   3. a new Pandemic Direction or a change to (including any extension, repeal, revocation or expiry of) an existing Pandemic Direction.
7. **Pandemic Direction** means a direction, order, requirement, declaration or exercise of a power by a relevant Government Agency in the Relevant Jurisdiction or in any other Australian jurisdiction in response to a Pandemic which the Operator is required to implement in order to comply with its obligations under Legislation, including:
   1. a public health order or direction issued by a relevant Government Agency pursuant to Legislation in the Relevant Jurisdiction Authority;
   2. the exercise of powers or issuing of directions pursuant to a declaration of an emergency as a 'state of disaster' or a declaration of a 'state of emergency'; or
   3. the exercise of powers or issuing of directions analogous or with a similar effect to those contemplated in paragraphs (a) or (b) of this definition.
8. **Payment Notice** means any notice issued by the Operator pursuant to clause 16.1(a) or 16.1(b) or by the Commonwealth pursuant to clause 16.1(c).
9. **Peak Period** means the period from 1 December of each year to 31 March of the following year in each case during the Operations Period, as may be adjusted by the Commonwealth by notice to the Operator where the Commonwealth considers than an adjustment to that period is appropriate to reflect changes in electricity demand and peak Spot Prices applicable in the Relevant Jurisdiction provided that:
   1. the Commonwealth must give the Operator at least 2 years' notice of any change to the Peak Period; and
   2. the Peak Period must not exceed four months out of any period of 12 months.
10. **Performance Requirement** has the meaning given in clause 10.1.
11. **Performance Requirements (Minimum)** has the meaning given in clause 10.3(c).
12. **Performance Security** has the meaning given in clause 27(a).

**Permitted Costs** means, in respect of a period, the following direct costs and expenses reasonably and properly incurred by the Operator on a cash flow basis in respect of the Project in that period (without double counting):

* 1. the costs in relation to the import of electricity from the Network for the Project, including any costs incurred on arm’s length terms on account of Green Products required by Law (or required to avoid a shortfall charge imposed by Law) to be acquired or surrendered in respect of such electricity;
  2. the costs incurred by the Project in respect of any Ancillary Services, Network Support Services or System Support Services;
  3. any other amounts incurred by the Operator under the National Electricity Rules in relation to the Project;
  4. any payments under any Offtake Contract, provided that an Offtake Contract will not qualify under this paragraph (d) if the counterparty to the Offtake Contract is a Related Body Corporate of the Operator and the Operator has not demonstrated to the Commonwealth’s reasonable satisfaction that the arrangement is on arm’s length terms; and
  5. any other costs and expenses the Operator and the Commonwealth agree are Permitted Costs,

but excluding:

* 1. operating costs (other than those listed in paragraph (a) and (b) above), maintenance costs and other capital costs;
  2. any Taxes (and GST, in accordance with clause 18.5(a));
  3. any fines or penalties (including fines or penalties under the National Electricity Law or the National Electricity Rules);
  4. any damages (including liquidated damages), warranty payments, or payments related to non-performance under an Offtake Contract; and
  5. any interest, margin, guarantee or letter of credit fees, line fees, commitment fees, establishment fees, underwriting fees, discount, rent under finance leases or hire purchase or other one-off or recurrent payments in the nature of the foregoing (including gross-ups and recurrent increased cost or reduced yield indemnity payments) payable by the Operator in relation to any debt financing for the Project.

1. **Permitted Security Interest** means:
   1. any Security Interest arising solely by operation of Law and in the ordinary course of the Recipient's ordinary business; and
   2. any Security Interest granted in support of the external debt financing whose sole purpose is to fund the design, construction, commissioning, testing, operation and maintenance of the Facility.
2. **Pooled Dispute** has the meaning in clause 36.1
3. **Pooled Dispute Panel** means a panel constituted in accordance with clause 36.2.
4. **Pooled Dispute Participant** means, in respect of a Pooled Dispute:
   1. Commonwealth;
   2. Operator; and
   3. each other Operator Counterparty that receives a Pooled Dispute Referral in respect of that Pooled Dispute from the Commonwealth,

but notwithstanding the foregoing, does not include any person that ceases to be a Pooled Dispute Participant pursuant to clause 36.3.

1. **Pooled Dispute Referral** has the meaning in clause 36.1(b).
2. **PR Cure Period** has the meaning given in clause 10.3(c)(iv).
3. **PR Cure Plan** has the meaning given in clause 10.3(g).
4. **Project** means the design, construction, commissioning, testing, completion, operation and maintenance of the Facility and all necessarily related or ancillary activities.
5. **Project Documents** means:
   1. this Agreement;
   2. the Tripartite Deed; and
   3. any other document the parties agree is a Project Document.
6. **Project Force Majeure Event** has the meaning given in clause 19.1.
7. **Project Intellectual Property** means all Intellectual Property developed by or on behalf of the Operator in the course of undertaking the Project, including all Intellectual Property in all reports, plans, documents, information, data and other material written, created or prepared by or on behalf of the Operator in relation to the Project.
8. **Proposed Reinstatement Plan** has the meaning given in clause 20.1(a).
9. **Quarter** means each consecutive three month period commencing on each Quarterly Date during the period from the Signing Date to the Expiry Date save that:
   1. the first Quarter of the CP Period will be the period from the day after the Signing Date to the date which is a day before the first Quarterly Date during the CP Period;
   2. the last Quarter during the CP Period will be the period from the last Quarterly Date to the Commencement Date;
   3. the first Quarter of the Construction Period will be the period from the day after the Commencement Date to the date which is a day before the first Quarterly Date during the Construction Period;
   4. the last Quarter during the Construction Period will be the period from the last Quarterly Date to the COD;
   5. the first Quarter of the Operations Period will be the period from the day after COD to the date which is a day before the first Quarterly Date during the Operations Period;
   6. the last Quarter during the Operations Period will be the period from the last Quarterly Date to the Expiry Date;
   7. the first Quarter of the Support Period will be the period from the day after Support Period Start Date to the date which is a day before the first Quarterly Date during the Support Period; and
   8. the last Quarter during the Support Period will be the period from the last Quarterly Date to the Expiry Date.
10. **Quarterly Date** means every 1 January, 1 April, 1 July and 1 October.
11. **Quarterly Payment** means the amount determined in accordance with section 3 of Schedule 4.

**Rated Capacity** means the actual instantaneous export capability of the Facility from time to time.

1. **Recipient** has the meaning given in clause 18.4(a).
2. **Registered Capacity** has the meaning given in Chapter 4A of the National Electricity Rules.
3. **Registration Date** has the meaning given in Schedule 1.

**Reinstatement Event** means an event or circumstance (whether alone or together with other events or circumstances) that results in the loss or destruction of, or material damage to, at least:

* 1. 50% of the Maximum Capacity of the Facility (in MW); and/or
  2. 50% of the Storage Capacity of the Facility (in MWh).

1. **Related Body Corporate** in relation to a corporation means a body corporate that is related to the corporation within the meaning of the Corporations Act.
2. **Relevant Cost Change** means a net increase or decrease in the Operator's reasonable and direct costs which are reasonably and properly incurred (or to be incurred) of:
   1. designing, constructing, commissioning, testing and completion of the Facility;
   2. operating and maintain the Facility; or
   3. storing and exporting energy,
3. that arises as a direct result of a Change in Law which occurs after the date which is 12 months after the Signing Date and as a result of applying the Cost Change Principles,but in each case excluding any Permitted Costs.
4. **Relevant Jurisdiction** means the State or Territory in Australia in which the Facility is or is to be Located.
5. **Reports** has the meaning given in clause 22.2(h).
6. **Required Rating** means, in respect of an entity, the rating assigned by a ratings agency to the unsecured, senior long term debt or deposit obligations of the entity (unsupported by third party credit enhancement) of at least:
   1. A– by Standard and Poor's (Australia) Pty Limited; or
   2. A3 by Moody's Investors Service, Inc,

and if both of those agencies cease to operate or provide ratings of the kind referred to above, an equivalent rating from another reputable ratings agency acceptable to the Commonwealth (acting reasonably).

1. **Responsible Entity** has the meaning given in the Corporations Act.
2. **Revenue Ceiling Sharing Percentage** has the meaning given in section 1 of Schedule 4.
3. **Revenue Floor Support Percentage** has the meaning given in section 1 of Schedule 4.
4. **Revised Statement** means a “routine revised statement” or a “special revised statement” (each as defined in the NER).
5. **Security Amount** has the meaning given in Schedule 1.
6. **Security Interest** means:
   1. any security for the payment of money or performance of obligations, including a mortgage, charge, lien, pledge, encumbrance, trust arrangement, contractual right of set-off, preferential right, power or title retention or flawed deposit arrangement or any other security agreement or arrangement in favour of any person including any “security interest” as defined in sections 12(1) or (2) of the *Personal Property Securities Act 2009* (Cth); or
   2. any agreement to create any of the above or allow them to exist.
7. **Signing Date** means the date on which the last party signs this Agreement.
8. **SLC Cure Plan** has the meaning given in clause 14.5(g).
9. **Social Licence Commitments** means the commitments set out in in Schedule 8.
10. **Specified Material** means any reports, plans, documents, information, data or other material and associated Intellectual Property rights (whether developed by or on behalf of the Operator or its Associates) which:
    1. the Operator provides or grants, or is required to provide or grant, to the Commonwealth under or in connection with this Agreement or the Tender; or
    2. is copied or derived at any time from the material referred to in paragraph (a).
11. **Spot Price** has the meaning in the NER.
12. **Storage Capacity** has the meaning given in Schedule 1.
13. **Storage Capacity Rebate** means the rebate determined or calculate in accordance with sections 5.1 and 5.2 of Schedule 4.
14. **Storage Capacity Rebate Percentage** means the percentage calculated in accordance with section 5.3 of Schedule 4.
15. **Subcontract** means any subcontract relating to the performance of the Operator's obligations under any Transaction Document (other than a contract with the Commonwealth) including with subcontractors whether hired directly by the Operator or by a person hired by the Operator and including each tier of subcontract, sub-subcontract and so forth.
16. **Subcontractor** means a subcontractor of the Operator (other than the Commonwealth) and includes any subcontractor of such a subcontractor, whether hired directly by the Operator or by a person hired by the Operator and including each tier of subcontract, sub-subcontract and so forth and any replacement of that subcontractor in accordance with this Agreement.
17. **Supplier** has the meaning given in clause 18.4.
18. **Support Period** means the period commencing on the day after Support Period Start Date and ending on the Expiry Date.
19. **Support Period Start Date** has the meaning given in Schedule 1.
20. **Support Year** means
    1. for the first Support Year, the period commencing on the first day of the Support Period until the next 30 June;
    2. subject to paragraph (c) of this definition, each subsequent 12 Month period during the Support Period commencing on 1 July and ending on 30 June; and
    3. for the final Support Year, the period from the end of the last full Support Year (as identified in paragraph (b) of this definition) to the Expiry Date,

unless this Agreement is terminated or ends earlier, in which case the last Support Year will be the period from the end of the last full Support Year (as identified in paragraph (b) of this definition) immediately preceding the termination or end date to the Expiry Date.

1. **System Support Services** means any service provided by the Facility to support the power system (as defined in the NER) including the provision of inertia or the provision of a system strength service, as each is defined in the NER, but excluding any Network Support Service.

**Tax** means any present or future tax, levy, impost, duty, rate, charge, excise, royalty (whether based on value, profit or otherwise), fee, deduction or withholding of any nature, which is imposed, levied or administered by an Authority, the Commonwealth or any State or Territory of the Commonwealth, together with any interest, penalty, charge, fee or other amount imposed or made on, or in connection with, any of the foregoing.

**Tender** meansthe tender process conducted by the Commonwealth (assisted by AEMO and its Related Bodies Corporate) which resulted in the parties entering into this Agreement.

**Tender Date** means the date on which the Operator submitted its “Financial Value Bid” in connection with the Tender.

**Tender Submission** means all documents submitted by or on behalf of the Operator or its Related Bodies Corporate to the Commonwealth (assisted by AEMO and its Related Bodies Corporate) in connection with the Tender.

1. **Tenure** means
   1. a freehold interest; and/or
   2. an interest under a lease, sale and purchase agreement, transfer granting an easement agreement, easement or similar right including any valid option to enter into such an agreement or right, which provides for access to and/or use of land for the purpose of developing, constructing, commissioning, operating, maintaining and decommissioning the Facility (including any connection assets).
2. **Term** means the period commencing on the Commencement Date and ending on and including the Expiry Date.
3. **Termination Payment** means an Early Termination Payment or a Fixed Termination Payment.
4. **Tested Storage Capacity** has the meaning given under section 5.4(c)(iv) of Schedule 4.
5. **Trading Protocol** means a protocol setting out in reasonable detail the processes and strategy which the Operator uses to generate revenue directly or indirectly from the Facility and/or the Project, which as a minimum must be prepared in accordance with Good Electricity Industry Practice.
6. **Transaction Documents** means:
   1. **[Drafting note: list of the equity, debt and project documents related to the project to be inserted here. The shortlisted Proponent is required to propose its definition for Transaction Documents as part of its Financial Value Bid in Stage B of the Tender Process. Please note that the equity documents referenced here need only be those from the first entity of substance in the ownership chain of the Operator and finance documents should include funding from third party financiers to finance special purpose vehicles]**
7. **Tripartite Deed** means the document entitled "Tripartite Deed" between the Commonwealth, the Operator, the Facility Agent and/or the Security Trustee on behalf of the Financiers substantially in the form attached as Schedule 9 .
8. **[Trust** means [***insert***]**.**
9. **Trust Deed** means [***insert***].**]**
10. **Trust Property** means all of the assets of the Trust] [**Drafting** **note: to be included if the Operator enters into this Agreement in its capacity as trustee of a trust**]
11. **Warranted Materials** has the meaning given in clause 28.4.
    1. Interpretation

Headings and subheadings are for convenience only and do not affect interpretation. Unless the contrary intention appears, in this Agreement:

* + 1. the singular includes the plural and vice versa and a word indicating gender includes every other gender;
    2. another grammatical form of a defined word or expression has a corresponding meaning;
    3. the meaning of general words is not limited by specific examples introduced by "including", "for example", "such as" or similar expressions;
    4. a reference to a document also includes any variation, replacement, novation or supplement of it;
    5. a reference to a "**person**" includes an individual, a corporation, a body corporate, a partnership, a joint venture (whether incorporated or unincorporated), an unincorporated association, an Entity, a trust and any Government Agency or any other entity or organisation;
    6. a reference to a particular person includes the person's executors, administrators, successors, permitted substitutes (including persons taking by novation) and assigns and in the case of a trustee, includes any substituted or additional trustee;
    7. unless otherwise indicated:
       1. a reference to a party, clause, Schedule, Annexure or Attachment is a reference to a party, clause, Schedule, Annexure or Attachment of or to this Agreement; and
       2. a reference to a section, table, item or part is a reference to the relevant numbered section, table, item or part within the Schedule, Annexure or Attachment (as applicable) in which it is located;
    8. a reference to a time of day is to the time in the capital city of the Relevant Jurisdiction;
    9. a reference to dollars, $ or $A is a reference to the currency of Australia;
    10. a reference to any legislation includes regulations under it and any consolidations, amendments, re-enactments or replacements of any of them;
    11. a reference to "**regulations**" includes instruments of a legislative character under legislation (such as regulations, rules, by-laws, subordinate legislation, ordinances, statutory instruments (however described) and proclamations);
    12. a reference to a group of persons is a reference to any two or more of them jointly and to each of them individually and a reference to an obligation or a Liability assumed by, or a right conferred on, two or more persons binds or benefits them jointly and severally;
    13. a reference to any thing (including an amount) is a reference to the whole and each part of it;
    14. a period of time dating from a given day or the day of an act or an event is to be calculated exclusive of that day;
    15. if the day on which a party must do something under this Agreement not a Business Day, the party must do it on the next Business Day; and
    16. this Agreement is comprised of the Details, the Background, clauses 1 to 39, Schedule 1 to Schedule 11 and any Annexures and Attachments to this Agreement;
    17. a reference to a right includes any benefit, remedy, function, discretion, authority or power;
    18. where there is a reference to a Government Agency, institute, association or other body referred to in a Project Document which:
        1. is reconstituted, renamed or replaced or if its powers or functions are transferred to, or assumed by, another entity, that Project Document is deemed to refer to that other entity; or
        2. ceases to exist, that Project Document is deemed to refer to the new entity (if any) which serves substantially the same purpose or object as the former entity; and
    19. if:
        1. a term used in this Agreement (including as a result of a prior application of this clause 1.2) has the meaning given to it in the NER; and
        2. the term in the NER is subsequently renamed or replaced with another term of similar effect,

the new term will be used in place of the term which was renamed or replaced.

* 1. Order of precedence
     1. If there is an ambiguity, inconsistency or discrepancy between any of the documents forming part of this Agreement, those documents will be interpreted in the following order of priority:
        1. clauses 1 to 39 inclusive;
        2. Schedules 1 to 5, 10 and 11; and
        3. Schedules 6, 7, 8 and 9,

so that the terms of the higher ranked document prevails to the extent of the ambiguity, inconsistency or discrepancy.

* + 1. If there is an ambiguity, inconsistency or discrepancy within a document forming part of this Agreement or two or more documents of the same level of order of precedence, the Commonwealth will notify the Operator how the ambiguity, inconsistency or discrepancy is to be resolved and the Operator must comply with that direction.
    2. If there is an ambiguity, inconsistency or discrepancy between this Agreement and any other Project Document, then the following order of precedence applies to the extent of any ambiguity, inconsistency or discrepancy:
       1. the Tripartite Deed;
       2. this Agreement; and
       3. the remaining Project Documents (if any).
    3. If any party discovers any ambiguity, inconsistency or discrepancy within or between any one or more of the documents forming part of this Agreement or between the Project Documents, that party must give the other party notice of such ambiguity, inconsistency or discrepancy within a reasonable time after discovering it.
    4. The resolution of any ambiguity, inconsistency or discrepancy pursuant to this clause 1.3 does not entitle the Operator to make any Claim against the Commonwealth and the Operator waives any such right nor does it modify any of the Operator's rights and obligations.
  1. Indexation
     1. Unless otherwise provided in this Agreement, only amounts identified in this Agreement which are followed by the term "(Indexed)" are subject to indexation. Where an amount identified in this Agreement is followed by the term "(Indexed)", that amount is to be indexed by multiplying the relevant amount by the CPI Factor.
     2. The CPI Factor (**CPIF**) is calculated as:

**CPIF = RCPI / ICPI**

where:

**CPIF** means the CPI Factor;

**RCPI** means the CPI value most recently published by the Australian Bureau of Statistics at the end of the relevant Quarter; and

**ICPI** means the CPI value most recently published by the Australian Bureau of Statistics for the Quarter most recently ended prior to the Signing Date.

* + 1. The following rules only apply to the amounts identified in this Agreement as being "(Indexed)":
       1. if there is a change in the coverage of the relevant price index from that applying at the Signing Date and the new index is linked to another index, the defined term is to be referrable to the new index;
       2. if the index is published and:
          1. there is a change in its coverage and it is not linked to another index; or
          2. there is a change in its periodicity,

the parties must request the President of the Institute of Actuaries of Australia (or the President's nominee) to determine:

* + - * 1. whether the index remains appropriate as a general indicator of the rate of price change for the relevant goods and services; and
        2. if it is not, what other index should be used as a substitute index for the purpose of the defined term's use in this Agreement,

and that determination is final and binds the parties;

* + - 1. if there is a change in the reference base of the index from that applying at the Signing Date and the person that publishes that index provides a conversion factor, that conversion factor must be applied to calculate revised figures for the purpose of the defined term's use in this Agreement, in terms of the new reference base;
      2. if there is a change in the reference base of the index from that applying at the Signing Date and the person that publishes that relevant index does not provide a conversion factor, the parties must request the President of the Institute of Actuaries of Australia (or the President's nominee) to calculate a revised index for the purposes of the defined term's use in this Agreement, and that calculation is final and binds the parties;
      3. if the index ceases to be published by the person that publishes that relevant index and that person publishes another index which is:
         1. a replacement of that index; and
         2. linked to the index,

the defined term must be re-calculated to the same reference base as the replacement index;

* + - 1. if the index ceases to be published by person that publishes that relevant index and that person does not publish another index which is linked to the index, the parties must request the President of the Institute of Actuaries of Australia (or the President's nominee) to calculate a revised index for the purposes of the defined term's use in this Agreement, and that calculation is final and binds the parties;
      2. if the index ceases to be published by the person that publishes that relevant index and that person does not publish another index in place of the index, the parties must request the President of the Institute of Actuaries of Australia (or the President's nominee) to determine an appropriate index which is a general indicator of the rate of price change for the relevant goods and services, and that determination is final and binds the parties; and
      3. if a change in Law which occurs after the Signing Date causes a material aberration in the index, the index must be adjusted to remove the impact of that material aberration in accordance with any such methodology published by a responsible Government Agency for adoption by business or, in the absence of such publication, within 6 months of the occurrence of the material aberration as agreed by the parties or, in the absence of agreement, as determined in accordance with clause 35.
  1. Commonwealth's rights, duties and functions
     1. Unless otherwise expressly provided in a Project Document, nothing in any Project Document gives rise to any duty on the part of the Commonwealth to consider interests other than its own interests when exercising any of its rights or carrying out any of its obligations under any Project Document.
     2. Notwithstanding anything expressly provided or implied in any Project Document to the contrary:
        1. the Commonwealth is not obliged:
           1. to exercise any executive or statutory right, duty or function, or to influence, over-ride, interfere with or direct any part of the Commonwealth or any other Government Agency in the proper exercise and performance of any of its executive or statutory rights, duties or functions;
           2. to develop or implement any new Commonwealth policy or change any Commonwealth policy;
           3. to enact any new legislation or implement a change in Law or make or revoke any regulation including any statutory instrument or delegation;
           4. to provide an interpretation of any legislation, regulation or Commonwealth policy; and
        2. nothing expressly provided or implied in any Project Document has the effect of constraining the Commonwealth or placing any fetter on the Commonwealth's discretion to exercise or not to exercise any of its executive or statutory rights, duties or functions.
  2. Reasonable endeavours of the Commonwealth

In any Project Document, a requirement for the Commonwealth to use 'best endeavours', 'reasonable endeavours', 'act reasonably', to not act unreasonably, to act in 'Good Faith' or to take 'reasonable' or 'all reasonable' steps or action, does not require the:

* + 1. exercise or non-exercise of any executive or statutory discretion, right or power;
    2. development or implementation of any new Commonwealth policy or change in Commonwealth policy;
    3. enactment of any new legislation or making of a change in Law or the making or revocation of any regulation including any statutory instrument or delegation; or
    4. Commonwealth to act in a way it regards as not in the public interest.
  1. No Commonwealth Liability for Review and Approval

Except to the extent expressly provided otherwise in this Agreement, no:

* + 1. review of, comment upon, acceptance, approval or certification of any document or approval of or consent to a proposed Subcontractor, permission, comment or recommendation, in each case by the Commonwealth or its Associates or deemed approval or consent (or a failure to do so);
    2. failure by (or on behalf of) the Commonwealth or Commonwealth's Associates, to detect any non-compliance by the Operator with its obligations in accordance with the Project Documents or any Laws;

will:

* + 1. relieve the Operator from, or alter, affect or modify, its Liabilities, obligations or responsibilities whether in accordance with the Project Documents or otherwise according to Law or give rise to the right of the Operator to make a Claim against the Commonwealth;
    2. constitute a waiver or prejudice the Commonwealth's rights against the Operator whether under the Project Documents or otherwise according to Law;
    3. constitute an approval or acceptance by the Commonwealth of the Operator's performance of its obligations in accordance with the Project Documents or acceptance of any item or material delivered; or
    4. entitle the Operator to an adjustment of any Milestone Event, Milestone Date (Scheduled), payment or amount or any other obligation arising from or in connection with any Project Document or to Claim from the Commonwealth any Liability incurred by the Operator.
  1. Prior approval or consent

If the Operator is required by a Project Document to obtain the Commonwealth's consent or approval to an action, document or thing, unless otherwise expressly provided, that consent or approval must be obtained as a condition precedent to the action, document or thing occurring or coming into effect.

* 1. Action without delay

Unless there is a provision in a Project Document which specifies a period of time in which something must be done by the Operator, all things must be done by the Operator without undue delay.

* 1. Provisions limiting or excluding Liability, rights or obligations
     1. A right or obligation of the Commonwealth or the Operator under this Agreement will not limit or exclude any other right or obligation of the Commonwealth or the Operator under this Agreement unless otherwise expressly provided.
     2. Any provision of this Agreement which seeks, either expressly or by implication, to limit or exclude any Liability of a party is to be construed as doing so only to the extent permitted by Law.
  2. Relationship of the parties
     1. Nothing in any Project Document:
        1. creates a partnership, joint venture, fiduciary, employment or agency relationship with the Commonwealth; or
        2. imposes any duty of Good Faith on the Commonwealth,

unless otherwise expressly provided.

* + 1. The Operator acknowledges that the Commonwealth may enter into arrangements which are the same or similar to those set out in the Project Documents with other persons.

1. Term

Subject to clause 3, this Agreement commences on the Signing Date and ends on the last day of the Term.

1. Conditions Precedent
   1. Commencement
      1. Subject to clause 3.1(b), this Agreement and the rights and obligations of the parties under this Agreement will not come into force and effect until the Operator has received a notice from the Commonwealth in accordance with clause 3.2(d) and each of the Conditions Precedent has been satisfied by the Operator (or waived by the Commonwealth in accordance with clause 3.6).
      2. Clauses 1, 2, 3, 4, 8, 10.4, 14, 18, 19, 20, 21, 27, 28, 29, 30, 31, 33, 34, 35, 36, 37, 38.7, 39, 41, 42, 43, 44, 45 and Schedules 1, 2, 5, 7, 9, 10 and 11 come into full force and effect immediately on the Signing Date.
   2. Satisfaction of Conditions Precedent
      1. Schedule 2 sets out the Conditions Precedent which the Operator must satisfy.
      2. Unless otherwise waived in accordance with clause 3.6, the Operator must:
         1. use reasonable endeavours to satisfy each Condition Precedent by the relevant Condition Precedent Date;
         2. use reasonable endeavours to satisfy all of the Conditions Precedent by the CP Target Date; and
         3. satisfy all of the Conditions Precedent by the CP Sunset Date,

and in each case the Operator must notify the Commonwealth within 5 Business Days after doing so.

* + 1. The Operator must provide with that notice objective evidence which demonstrates that the relevant Condition Precedent has been satisfied, and must promptly provide any further information reasonably requested by the Commonwealth regarding the satisfaction of a Condition Precedent within 5 Business Days after being requested to do so.
    2. Within 5 Business Days after it becomes aware that the last of the Conditions Precedent has been satisfied or waived, the Commonwealth must provide a notice to the Operator confirming that all of the Conditions Precedent have been satisfied or waived and the date upon which the last Condition Precedent was satisfied or waived (**Commencement Date**) and with that notice provide two versions of the Tripartite Deed signed by the Commonwealth.
  1. Draft CP Cure Plans and CP Cure Plans
     1. If at any time the Operator is, or the Commonwealth reasonably believes that the Operator is, likely to fail to satisfy:
        1. any Condition Precedent on or before the relevant Condition Precedent Date;
        2. all of the Conditions Precedent on or before the CP Target Date; or
        3. all of the Conditions Precedent on or before the CP Sunset Date,

the Operator must submit a draft cure plan to the Commonwealth within 20 Business Days after receipt of a written request to do so from the Commonwealth (**Draft** **CP Cure Plan**).

* + 1. A Draft CP Cure Plan must identify the proposed revised dates (such date to be as soon as reasonably practicable after the Draft CP Cure Plan is submitted to the Commonwealth and which includes reasonable period for contingency) by which the Operator will satisfy the relevant Condition Precedent or all of the Conditions Precedent (as applicable) and demonstrate, to the Commonwealth’s reasonable satisfaction, that the Operator will be able to satisfy:
       1. the relevant Condition Precedent or Conditions Precedent on or before the proposed revised dates; and
       2. each of the remaining Conditions Precedent which have not been satisfied by no later than the CP Sunset Date.
    2. The Commonwealth must act reasonably in determining whether to approve or reject a Draft CP Cure Plan submitted under clause 3.3(a) and must use reasonable endeavours to either approve or reject the Draft CP Cure Plan within 30 Business Days (or such other period agreed by the parties) after that Draft CP Cure Plan (which complies with this Agreement) is submitted to the Commonwealth. Without limitation, it will be unreasonable for the Commonwealth to reject the Draft CP Cure Plan where it:
       1. is prepared in accordance with the requirements of this Agreement;
       2. identifies a date for the satisfaction of the relevant Condition Precedent which is as soon as reasonably practicable (including a reasonable period for contingency) after the Operator submits the Draft CP Cure Plan to the Commonwealth; and
       3. demonstrates that the Operator will be able to satisfy the relevant Condition Precedent or Conditions Precedent on or before the proposed revised dates and each of the remaining Conditions Precedent which have not been satisfied by no later than the CP Sunset Date.
    3. If the Commonwealth rejects a Draft CP Cure Plan pursuant to clause 3.3(c):
       1. the Commonwealth must provide the Operator with reasonable details of its reasons for the rejection at the time the Draft CP Cure Plan is rejected; and
       2. within 20 Business Days after the Draft CP Cure Plan is rejected, the Operator must amend and resubmit a revised Draft CP Cure Plan for approval by the Commonwealth in accordance with clause 3.3(c).
    4. Clauses 3.3(c) and 3.3(d)(i), but not clause 3.3(d)(ii), will apply to an amended Draft CP Cure Plan submitted by the Operator pursuant to clause 3.3(d)(ii).
    5. If the Commonwealth approves a Draft CP Cure Plan, it must notify the Operator of that approval and that Draft CP Cure Plan becomes the approved cure plan on the date of that approval (**CP Cure Plan**). On and from the date on which the Commonwealth notifies the Operator of that approval, the Operator must:
       1. subject to clause 8, comply with the CP Cure Plan;
       2. provide a report to the Commonwealth regarding its progress against the CP Cure Plan within 5 Business Days after the end of each Month until the relevant Conditions Precedent the subject of the CP Cure Plan have been satisfied by the Operator or waived by the Commonwealth; and
       3. if applicable, any reference to the relevant Condition Precedent Date, CP Target Date and CP Sunset Date in this Agreement will be deemed to refer to the relevant Condition Precedent Dates, the CP Target Date and/or CP Sunset Date as adjusted under the CP Cure Plan.
    6. If the Operator:
       1. is unable to comply with the conditions specified in clause 3.3(b);
       2. fails to submit or resubmit a Draft CP Cure Plan to the Commonwealth when required to do so pursuant to this clause 3.3;
       3. has submitted a draft CP Cure Plan which has been rejected by the Commonwealth and has resubmitted the draft CP Cure Plan which (subject to clause 3.3(i)) has also been rejected, each case in accordance with this Agreement;
       4. subject to clause 3.3(f), fails to commence the implementation of the CP Cure Plan as required pursuant to this clause 3.3 or otherwise fails to comply with the CP Cure Plan in any material respect, and does not remedy any such failure within 10 Business Days after receipt of a notice from the Commonwealth requiring it to do so; or
       5. is complying with a CP Cure Plan but the Commonwealth becomes aware (acting reasonably) that the conditions specified in clause 3.3(b) will not be satisfied by the relevant dates referred to in clause 3.3(b),

the Commonwealth may terminate this Agreement by notice to the Operator, this Agreement will terminate on the date set out in that notice and that termination will be deemed to be a termination pursuant to clause 22.2.

* + 1. The Commonwealth must not terminate this Agreement pursuant to clause 3.3(g) if the Operator is entitled to and has submitted a Draft CP Cure Plan to the Commonwealth under clause 3.3(a) and the Commonwealth has not yet approved or rejected the Draft CP Cure Plan under clause 3.3(c).
    2. Where the Operator submits a Draft CP Cure Plan which has been rejected in accordance with clause 3.3(c) and submits a revised Draft CP Cure Plan for approval in accordance with clause 3.3(d)(ii), in determining whether to approve or reject that resubmitted Draft CP Cure Plan the Commonwealth may only:
       1. review and provide comments on:
          1. the new and amended information provided by or on behalf of the Operator with that resubmitted Draft CP Cure Plan;
          2. previous information supplied in relation to the relevant Draft CP Cure Plan which is impacted by that new and amended information; and
          3. any information in the Draft CP Cure Plan which is impacted by any new circumstances which have arisen after the submission of the first version of the relevant Draft CP Cure Plan; and
       2. approve or reject that resubmitted Draft CP Cure Plan based on that new and/or amended information, the previous information which has been impacted by that new and amended information and those new circumstances.
  1. Failure to meet CP Sunset Date

If the Operator fails to satisfy all of the Conditions Precedent on or before the CP Sunset Date, this Agreement will automatically terminate on the day after the CP Sunset Date without the Commonwealth having to take any further action and that termination will be deemed to be a termination pursuant to clause 22.2.

* 1. Extension of CP Dates

Each of the Condition Precedent Dates, CP Target Date and CP Sunset Date:

* + 1. may be adjusted:
       1. in accordance with clause 8; or
       2. by written agreement between the parties; and
    2. are not subject to adjustment for any other reason.
  1. Waiver of Conditions Precedent
     1. Schedule 2 identifies that the Commonwealth is the only party which benefits from the satisfaction of each Condition Precedent. Only the Commonwealth may waive a Condition Precedent provided however the Commonwealth must only do so where the Operator requests the Commonwealth to waive the relevant Condition Precedent.
     2. A Condition Precedent is only waived where the Commonwealth gives written notice of that waiver of the Condition Precedent to the Operator.

1. Contract Manager for each Party
   * 1. Each party must ensure that at all times during the Term, there is a natural person appointed by it to be its contract manager for this Agreement (**Contract Manager**). The initial Contract Manager for each of the Commonwealth and the Operator is the person to whom notices are to be sent as set out in Notice details at the start of this Agreement.
     2. Each party shall notify the other in writing of any change in the identity, position and contact details of its Contract Manager within 10 Business Days after the change, as the case may be.
     3. Each party's Contract Manager must administer this Agreement on behalf of the party appointing him or her and may exercise all rights, powers, authority and functions of the party appointing him or her under this Agreement and does so as agent of the party appointing him or her.
     4. Each party may at any time delegate the exercise of any power or authority of that party to a person other than its then appointed Contract Manager. That party must promptly notify the other party of the identity of each delegate and the powers and authority delegated (including any conditions applying to the delegated power). A party may vary or terminate any power or authority it has delegated, whether to the Contract Manager or otherwise, and must promptly notify the other party of any such variation or termination.
2. Milestone Events
   1. Achievement of Milestone Events
      1. The Operator must:
         1. use reasonable endeavours to achieve each Milestone Event on or before the relevant Milestone Date (Scheduled) including achieving Commercial Operation on or before the COD (Target); and
         2. achieve Commercial Operation on or before the COD (Sunset).
      2. If a Milestone Event is not achieved by the relevant Milestone Date (Scheduled), the Operator must continue to use reasonable endeavours to achieve the Milestone Event as soon as reasonably practicable after the relevant Milestone Date (Scheduled).
      3. The Operator must notify the Commonwealth 20 Business Days prior to the date on which it reasonably expects to achieve a Milestone Event. If after the Operator provides that notice to Commonwealth, the date on which the Operator reasonably expects to achieve that Milestone Event changes, the Operator must notify the Commonwealth promptly of the revised date.
      4. The Operator must notify the Commonwealth that it has achieved a Milestone Event within 10 Business Days after becoming aware that it has achieved that Milestone Event. The Operator must provide to the Commonwealth with that notice objective evidence which demonstrates that the relevant Milestone Event has been achieved, and must promptly provide any further information reasonably requested by the Commonwealth regarding the achievement of that Milestone Event within 5 Business Days after being requested to do so.
      5. Notwithstanding anything to the contrary in this Agreement, a Milestone Event will not have been achieved unless and until the Operator has provided to the Commonwealth:
         1. in relation to the Milestone Event related to Commercial Operations only, evidence from an appropriately qualified independent professional firm nominated by the Operator and approved by the Commonwealth (acting reasonably) and which has no actual or perceived conflict of interest which demonstrates that the relevant Milestone Event has been achieved. The Operator must ensure that the professional firm providing that independent evidence has agreed to permit the Commonwealth to rely on that evidence (subject to standard and reasonable limitations of liability and qualifications which that firm imposes on such reliance in the ordinary course of its business) and is liable to the Commonwealth for the contents of that evidence;
         2. a certificate from a director of the Operator that the information contained in the notice referred to in clause 5.1(d) is true, complete and accurate; and
         3. such other information or documentation as may be reasonably necessary to demonstrate that the relevant Milestone Event (other than the one related to Commercial Operations) has been satisfied in accordance with this Agreement including evidence from an appropriately qualified independent person (provided on a reliance or non-reliance basis) and which has no actual or perceived conflict of interest which demonstrates that the relevant Milestone Event has been achieved.
      6. As soon as reasonably practicable and in any event within 20 Business Days after the Operator issues a notice in accordance with clause 5.1(d), if the Operator:
         1. has achieved the relevant Milestone Event, the Commonwealth must issue a certificate to the Operator stating that the relevant Milestone Event has been achieved and identifying in that notice the date on which the relevant Milestone Event was achieved; or
         2. has not achieved the relevant Milestone Event, the Commonwealth must issue a notice to the Operator identifying the requirements in this Agreement which are preventing the Operator from achieving the relevant Milestone Event. After receipt of that notice, the Operator must continue to expeditiously and diligently progress the completion of those requirements in this Agreement to enable it to achieve the relevant Milestone Event. After the Operator has completed those requirements, it must issue a further notice under clause 5.1(d) and repeat the process set out in clauses 5.1(d) to this 5.1(f) until the relevant Milestone Event is achieved.
      7. Where all of the COD Conditions have been achieved, if the Operator fails to provide to the Commonwealth with each of the following (within 20 Business Days after the date on which last of the COD Conditions has been achieved by the Operator or waived by the Commonwealth each in accordance with this Agreement):
         1. the notice, evidence and/or further information requested each as identified in clause 5.2(c); and/or
         2. the evidence from the appropriately qualified independent professional firm, certificate from the director of the Operator and the other information and document each as identified in clause 5.2(d),

the Commonwealth may, at its absolute discretion take any one or more of the following steps:

* + - 1. procure the evidence referred to in clause 5.2(d)(i) itself, in which case the Operator must pay the Commonwealth within 15 Business Days after receipt of a request to do so, the reasonable costs incurred by the Commonwealth in obtaining that evidence;
      2. direct the Operator to provide the certification referred to in clause 5.2(d)(ii) within a further period of 15 Business Days, in which case the Operator must provide that certification within that further period of 15 Business Days;
      3. notify the Operator that it has failed to provide the relevant notice, evidence and/or further information requested each as identified in clause 5.2(c) and/or the evidence of the appropriately qualified independent professional firm, certificate from the director of the Operator and the other information and document each as identified in clause 5.2(d) in each case on or before the end of that 20 Business Day period and if the Operator does not provide them to the Commonwealth within a further period of 20 Business Days after receipt of that notice, terminate this Agreement by further notice to the Operator and this Agreement will terminate on the date set out in that further notice and that termination will be deemed to be a termination pursuant to clause 22.2; and
      4. determine that Commercial Operation has been achieved and notify the Operator of the date on which Commercial Operation was achieved, in which case Commercial Operation will be deemed to have occurred on the date notified by the Commonwealth.
  1. Draft ME Cure Plans and ME Cure Plans
     1. If at any time the Operator fails to achieve Commercial Operation on or before the COD (Target), the Operator must submit a draft cure plan to the Commonwealth within 20 Business Days after receipt of a written request to do so from the Commonwealth (**Draft** **ME Cure Plan**).
     2. A Draft ME Cure Plan must identify the proposed revised date (such date to be as soon as reasonably practicable after the Draft ME Cure Plan is submitted to the Commonwealth and which includes reasonable period of contingency) by which the Operator will achieve Commercial Operation and demonstrate, to the Commonwealth’s reasonable satisfaction, that the Operator will be able to achieve Commercial Operation on or before the proposed revised date and that proposed revised date must be no later than the COD (Sunset).
     3. The Commonwealth must act reasonably in determining whether to approve or reject a Draft ME Cure Plan submitted pursuant to clause 5.2(a) and must use reasonable endeavours to either approve or reject the Draft ME Cure Plan within 20 Business Days (or such other period agreed by the parties) after that Draft ME Cure Plan (which complies with this Agreement) is submitted to the Commonwealth. Without limitation, it will be will be unreasonable for the Commonwealth to reject the Draft ME Cure Plan where it:
        1. is prepared in accordance with the requirements of this Agreement;
        2. identifies a date by which the Operator will achieve Commercial Operation which is as soon as reasonably practicable (including a reasonable period for contingency) after the Operator submits the Draft ME Cure Plan to the Commonwealth; and
        3. demonstrates that the Operator will be able to achieve Commercial Operation on or before the proposed revised date and that proposed revised date must be no later than the COD (Sunset).
     4. If the Commonwealth rejects a Draft ME Cure Plan pursuant to clause 5.2(c):
        1. the Commonwealth must provide the Operator with reasonable details of its reasons for the rejection at the time the Draft ME Cure Plan is rejected; and
        2. within 20 Business Days after the Draft ME Cure Plan is rejected, the Operator must amend and resubmit a revised Draft ME Cure Plan for approval by the Commonwealth in accordance with clause 5.2(c).
     5. Clauses 5.2(c) and 5.2(d)(i), but not clause 5.2(d)(ii), will apply to an amended Draft ME Cure Plan submitted by the Operator pursuant to clause 5.2(d)(ii).
     6. If the Commonwealth approves a Draft ME Cure Plan, it must notify the Operator of that approval and that Draft Cure Plan becomes the approved cure plan on the date of that approval (**ME** **Cure Plan**). On and from the date on which the Commonwealth notifies the Operator of that approval:
        1. subject to clause 8, the Operator must comply with the ME Cure Plan;
        2. the Operator must provide a report to the Commonwealth regarding its progress against the ME Cure Plan within 5 Business Days after the end of each Month until Commercial Operations has been achieved; and
        3. if applicable, any reference to the COD (Target) in this Agreement will be deemed to refer to the COD (Target) as adjusted under the ME Cure Plan.
     7. If the Operator:
        1. fails to submit or resubmit a Draft ME Cure Plan to the Commonwealth when required to do so pursuant to this clause 5.2;
        2. has submitted a draft ME Cure Plan which has been rejected by the Commonwealth and has resubmitted the draft ME Cure Plan which (subject to clause 5.2(i)) has also been rejected, each case in accordance with this Agreement;
        3. subject to clause 5.2(f), fails to commence the implementation of the ME Cure Plan as required pursuant to this clause 5.2 or otherwise fails to comply with the ME Cure Plan in any material respect, and does not remedy that failure within 20 Business Days after receipt of a notice from the Commonwealth requiring it to do so; or
        4. is complying with a ME Cure Plan but the Commonwealth becomes aware (acting reasonably) that the conditions specified in clause 5.2(b) will not be satisfied by the relevant date referred to in clause 5.2(b),

the Commonwealth may terminate this Agreement by notice to the Operator, this Agreement will terminate on the date set out in that notice and that termination will be deemed to be a termination pursuant to clause 22.2.

* + 1. The Commonwealth must not terminate this Agreement pursuant to clause 5.2(g) if the Operator has submitted a Draft ME Cure Plan to the Commonwealth under clause 5.2(a) and the Commonwealth has not yet approved or rejected the Draft ME Cure Plan under clause 5.2(c).
    2. Where the Operator submits a Draft ME Cure Plan which has been rejected in accordance with clause 5.2(c) and submits a revised Draft ME Cure Plan for approval in accordance with clause 5.2(d)(ii), in determining whether to approve or reject that resubmitted Draft ME Cure Plan the Commonwealth may only:
       1. review and provide comments on:
          1. the new and amended information provided by or on behalf of the Operator with that resubmitted Draft ME Cure Plan;
          2. previous information supplied in relation to the relevant Draft ME Cure Plan which is impacted by that new and amended information; and
          3. any information in the Draft ME Cure Plan which is impacted by any new circumstances which have arisen after the submission of the first version of the relevant Draft ME Cure Plan; and
       2. approve or reject that resubmitted Draft ME Cure Plan based on that new and/or amended information, the previous information which has been impacted by that new and amended information and those new circumstances.
  1. Failure to meet COD (Sunset)

If the Operator fails to achieve Commercial Operation on or before the COD (Sunset), this Agreement will automatically terminate on the day after the COD (Sunset) without the Commonwealth having to take any further action and that termination will be deemed to be a termination pursuant to clause 22.2.

* 1. Extension of dates related to Milestone Events

Each of the Milestone Event (Scheduled), COD (Target) and COD (Sunset):

* + 1. may be adjusted:
       1. in accordance with clause 8; or
       2. by written agreement between the parties including under a ME Cure Plan; and
    2. are not subject to adjustment for any other reason.
  1. Sole consequences
     1. Except in circumstances where the Commonwealth elects to terminate this Agreement and subject to clauses 5.5(b) and 5.5(e), the sole consequences for the Operator's failure to achieve Commercial Operation by the Final Support Commencement Date is limited to any resulting reduction in the length of the Operations Period (including Support Period) in accordance with the definition of that term and the amount of any Quarterly Payment and Annual Reconciliation Payments not required to be paid by the Commonwealth in those circumstances.
     2. The Operator acknowledges and agrees that clause 5.5(a) does not limit the Commonwealth's rights and Operator's Liability in respect of an event giving rise to the delay or the consequences of such event, other than the delay itself.
     3. Subject to clauses 5.5(d) and 5.5(e), where this Agreement terminates for a failure to achieve Commercial Operation on or before the COD (Sunset), the sole consequences for the Operator's failure to achieve Commercial Operation on or before the COD (Sunset) is termination of this Agreement in accordance with clause 5.3 and clause 22.2 and the Commonwealth's rights pursuant to clauses 22.3 and 23.
     4. The Operator acknowledges and agrees that clause 5.5(c) does not limit the Commonwealth's rights and Operator's Liability in respect of an event giving rise to the delay or the consequences of such event, other than the delay itself.
     5. This clause 5.5 is without prejudice to:
        1. any rights or remedies the Commonwealth may have in relation to matters arising under or in connection with this Agreement (other than those specifically referred to in this clause 5.5); and
        2. clause 5.2 to clause 5.4.

1. Construction obligations
   1. General construction obligations

On and from the Commencement Date, the Operator must, at its own cost and risk, promptly commence and carry out the design, construction, commissioning, testing and completion of the Facility:

* + 1. regularly, diligently and expeditiously and in accordance with Good Construction Industry Practice;
    2. in compliance with all Authorisations and Laws, including health and safety Laws;
    3. in accordance with this Agreement and the Operator’s Transaction Documents;
    4. so that the Facility (when designed, constructed, commissioned, tested and completed):
       1. is fit for its intended purpose as determined by reference to the COD Conditions;
       2. satisfies each of the COD Conditions;
       3. is capable of meeting the Operator's obligations under this Agreement; and
       4. is compliant with, and capable of being operated and maintained in accordance with all applicable Laws and Authorisations;
    5. in accordance with the Social Licence Commitments; and
    6. to the extent not inconsistent with the preceding clauses, in accordance with the recommendations and guidelines specified by the suppliers of any plant, equipment and materials forming part of the Facility or to be used in the operation and maintenance of the Facility.
  1. Testing and commissioning plan

The Operator must prepare and provide a copy of its testing and commissioning plan for the Facility to the Commonwealth which includes the testing and commissioning activities which the Operator will carry out to achieve Commercial Operations. That plan must as a minimum be prepared in accordance with Good Electricity Industry Practice. That testing and commissioning plan must be provided by the Operator to the Commonwealth at least 40 Business Days prior to the date when the testing and/or commissioning of the Facility which is designed to demonstrate Commercial Operations is scheduled to commence.

1. Commercial Operation
   * 1. Without limiting any other obligation which the Operator has under this Agreement, to achieve Commercial Operation, the following must have occurred:
        1. the Operator has completed the design, construction, commissioning and testing of the works on the Project site (which includes all ancillary plant, control systems and connection infrastructure on the Operator's side of the Connection Point required for the operation of the Facility) and the Operator has obtained all applicable Authorisations including registrations under the NEL, in each case which will enable the Facility to be operated and maintained in accordance with Good Industry Practice and all applicable Laws;
        2. the Facility must:
           1. be capable of exporting electrical energy through the Connection Point at a level of output that is equal to or exceeds the Maximum Capacity;
           2. be capable of importing electrical energy through the Connection Point at a level that is equal to or exceeds the Import Capacity; and
           3. have an energy storage capacity that is equal to or exceeds the Storage Capacity,

in each case when tested, operated and maintained in accordance with Good Industry Practices and all applicable Laws;

* + - 1. the relevant network service provider has confirmed that the Facility is unconditionally released from all hold points so that the Facility is permitted to:
         1. export electrical energy through the Connection Point at a level of output that is equal to or exceeds the Maximum Capacity; and
         2. import electrical energy through the Connection Point at a level that is equal to or exceeds the Import Capacity.
      2. the Operator has submitted and received approval (or a deemed approval) from the Commonwealth for its first annual maintenance plan under clause 9.3 and has provided the Commonwealth with a copy of its Trading Protocol in a form which complies with the applicable requirements of this Agreement;
      3. the Operator is:
         1. registered with AEMO as an integrated resource provider and the Facility is classified as a scheduled bidirectional unit in accordance with the NEL and NER; and
         2. licensed to generate, or undertake any other relevant activity, under any applicable jurisdictional energy legislation; and
      4. the Commonwealth has confirmed to the Operator pursuant to clause 14.2 that all Social Licence Commitments which are to be satisfied prior to Commercial Operations Date have been satisfied,

(each a **COD Condition**).

* + 1. The COD Conditions are for the benefit of the Commonwealth and may only be waived by the Commonwealth (in its absolute discretion) in writing.

1. Delay and extensions
   1. Extension of required dates
      1. Subject to clauses 8.1(b) and 8.2, if the Operator has been or will be delayed in:
         1. satisfying a Condition Precedent by the relevant Condition Precedent Date;
         2. satisfying the Conditions Precedent by the CP Target Date;
         3. satisfying the Conditions Precedent by the CP Sunset Date;
         4. achieving Commercial Operation by the COD (Target); or
         5. achieving Commercial Operation by the COD (Sunset),

due to a Force Majeure Event, provided the Operator has complied with all relevant requirements of clause 19, the relevant Condition Precedent Date, CP Target Date, CP Sunset Date, COD (Target) or COD (Sunset) (as applicable) will be extended by a period equal to the delay caused by the Force Majeure Event to the Operator satisfying the relevant Condition Precedent by the Condition Precedent Date, CP Target Date and CP Sunset Date (as applicable) or achieving Commercial Operation by the COD (Target) and COD (Sunset) (as applicable).

* + 1. Where:
       1. an extension of a date referred to in clause 8.1(a) is granted under that clause; and
       2. the relevant Force Majeure Event also directly delays the Operator in achieving:
          1. any Milestone Event (other than Commercial Operation) by its Milestone Date (Scheduled); and/or
          2. the Conditions Precedent or Commercial Operation by any of the other dates referred to in clause 8.1(a),

the Milestone Date (Scheduled) relating to that Milestone Event and the relevant other dates related to the Conditions Precedent or Commercial Operation will also be extended by a period equal to the extension granted under clause 8.1(a) (to the extent applicable). For example, where an extension to the COD (Target) is granted under clause 8.1(a) and the relevant Force Majeure Event also directly delays the Operator in achieving Commercial Operations by the COD (Sunset), the COD (Sunset) will also be extended by the a period equal to the extension granted under clause 8.1(a) to the COD (Target) to the extent applicable.

* + 1. For the avoidance of doubt, the Final Support Commencement Date is not subject to adjustment other than pursuant to the rights of the Commonwealth under clause 8.3.
  1. Cap on extensions

Subject to clause 8.3, the COD (Sunset) may not be extended:

* + 1. for any Project Force Majeure Event, beyond the date that is 6 months after the COD (Sunset) identified in Item 12 of Schedule 1 as at the Signing Date and disregarding any adjustments to that date other than pursuant to clause 8.3); and
    2. for any Connection Force Majeure Event, by more than the length of the relevant delay caused by that Connection Force Majeure Event.
  1. Unilateral Extensions
     1. Without limiting the Operator's rights to an extension under clause 8.1, the Commonwealth may, at any time, in its absolute and unfettered discretion and whether or not for any reason stated in this Agreement, grant an extension of any Condition Precedent Date, the CP Target Date, the CP Sunset Date, the COD (Target), the COD (Sunset) or any Milestone Date (Scheduled), or any other date by which any obligation is required to be performed under this Agreement.
     2. An extension granted by the Commonwealth under this clause 8.3 must be granted in writing to be effective

**[Drafting note: this right of the Commonwealth to unilaterally extend is in addition to the extension mechanism under clause 8.1 and therefore is in the Commonwealth's absolute discretion as it may relate to scenarios where the Operator is not entitled to an extension of time]**

1. Operation and maintenance requirements
   1. General operation obligations

Throughout the Operations Period, the Operator must:

* + 1. operate and maintain the Facility in accordance with:
       1. this Agreement and the Operator's Transaction Documents;
       2. the standards and skills of a reasonable and prudent operator and in a manner that will preserve the asset life of the Facility to the end of the Term;
       3. Good Industry Practice and all applicable Laws and Authorisations including health and safety Laws;
       4. the Social Licence Commitments; and
       5. to the extent not inconsistent with the preceding clauses, the recommendations and guidelines specified by the suppliers of any plant, equipment and materials forming part of the Facility or used in the operation and/or maintenance of the Facility;
    2. register and maintain its registration with AEMO as an integrated resource provider and ensure that the Facility is and remains classified as a scheduled bidirectional unit in accordance with the NEL and NER; and
    3. ensure that it is and remains licensed to generate, or undertake any other relevant activity, under any applicable jurisdictional energy legislation.
  1. Trading Protocol
     1. The Operator must provide the Commonwealth with a copy of its Trading Protocol for the information of the Commonwealth on or before Commercial Operation in accordance with clause 7. The Trading Protocol may only be used by the Commonwealth for assessing whether the Operator has complied with its obligations arising from or in connection with the Project Documents.
     2. As soon as reasonably practicable (and in any event within 15 Business Days) after the end of each Operations Year, the Operator must provide to the Commonwealth:
        1. an annual report for that Operations Year outlining whether it operated the Facility in accordance with the Trading Protocol and if not how the operations of the Facility differed from the Trading Protocol; and
        2. a revised Trading Protocol for the next Operations Year (to the extent that there is to be any change to the Trading Protocol).
  2. Maintenance plan
     1. The Operator must submit a proposed annual maintenance plan, setting out a two year forecast of planned maintenance activities for the Facility, to the Commonwealth for review and approval:
        1. prior to COD; and
        2. on the first day of each Operating Year.
     2. The Operator must prepare each proposed annual maintenance plan in accordance with Good Industry Practice.
     3. The Commonwealth may, following review of an annual maintenance plan and acting reasonably:
        1. approve the plan by notice in writing to the Operator; or
        2. notify the Operator that the plan is rejected, providing reasons and the Commonwealth may only reject that plan acting reasonably where that plan does not comply with Good Electricity Industry Practice.
     4. Without limitation, it will be will be unreasonable for the Commonwealth to reject the annual maintenance plan where it:
        1. is prepared in accordance with the requirements of this Agreement; and
        2. it has been prepared in accordance with Good Electricity Industry Practice.
     5. If the Commonwealth:
        1. gives notice under clause 9.3(c)(ii), the Operator must revise the annual maintenance plan accordingly and resubmit it for the approval of the Commonwealth pursuant to clause 9.3(c); or
        2. does not give notice under clause 9.3(c) within 20 Business Days after receipt of that annual maintenance plan, the Operator must issue a notice to the Commonwealth warning it that if it fails to respond to the annual maintenance plan within a further 10 Business Days, that annual maintenance plan will be deemed to be approved. If the Commonwealth fails to approve that revised annual maintenance plan or notify the Operator that the revised annual maintenance plan is rejected within that further 10 Business Day period, the revised annual maintenance plan will be deemed to be approved.
     6. The Operator must use reasonable endeavours to perform planned maintenance arising from or in connection with the Facility in a way that complies with the most recently approved annual maintenance plan and which mitigates the impact of planned maintenance on the Facility’s operations.
  3. Operation and scheduling

During the Support Period, the Operator must:

* + 1. minimise any disruption to the operation of the Facility in accordance with Good Electricity Industry Practice;
    2. use reasonable endeavours not to schedule or conduct any planned maintenance or planned outage for the Facility during the Peak Period;
    3. use reasonable endeavours to operate and maintain the Facility so as to optimise the amount of energy and timing of energy exported at the Connection Point to correspond with Peak Periods;
    4. use reasonable endeavours to minimise the amount of any payments payable by the Commonwealth pursuant to Schedule 4; and
    5. operate, contract, Bid and dispatch the Facility in Good Faith and:
       1. in accordance with market signals for a storage project of its nature as if it were a stand-alone project and not operated as part of a portfolio of assets; and
       2. having regard to any Offtake Contracts or any arrangements entered into pursuant to clause 9.5.
  1. Bona fide and Arm's Length Arrangements
     1. The Operator must not enter into:
        1. any Offtake Contract or any arrangement regarding Operational Revenue and/or Permitted Costs, in each case which applies during the Support Period unless that contract or the arrangement is entered into on a bona fide basis and on arm's length terms; and **[Drafting note: the purpose of applying an arm's length test to these concepts is to ensure that the Operator enters into arrangements on terms which reflect market terms and is intended to prevent gaming of (for example) Operational Revenues and Permitted Costs.]**
        2. any arrangement with a Related Body Corporate which applies during the Support Period unless it has demonstrated to the Commonwealth's reasonable satisfaction that the relevant arrangement is entered on a bona fide basis and on arm’s length terms.
     2. The Operator acknowledges that:
        1. the purpose of this Agreement is to provide an option for a revenue top up during the Support Period to support the development of the Project and is not intended to distort the market signals that would otherwise apply to the Project; and
        2. this Agreement including clause 9 is to be interpreted and applied consistent with that purpose.
  2. Emergency maintenance

Nothing in this Agreement prevents the Operator from undertaking emergency or unplanned maintenance or repairs in accordance with Good Electricity Industry Practice that are:

* + 1. necessary to prevent injury, death or damage to the Environment or the Facility; or
    2. required to maintain manufacturer's warranties,

and which is not able to be reasonably rescheduled or deferred.

1. Performance and Other Requirements
   1. Performance Requirement obligations

Subject to clause 10.3, the Operator must ensure that:

* + 1. Equivalent Availability Factor for the Facility for each Operating Year is equal to or exceeds 90%; and
    2. the energy storage capacity for the Facility for each Operating Year is equal to or exceeds the Storage Capacity,

each a performance requirement (**Performance Requirement**).

* 1. Measurement and validation
     1. The Operator must measure, test and calculate the performance of the Facility in respect of each of the Performance Requirements at the end of each Operations Year for that Operations Year.
     2. The Operator must conduct the Storage Capacity test in accordance with section 5 of Schedule 4 and that test must be conducted at the times when the appropriately qualified independent professional firm identified in clause 10.2(c)(i) is able to attend the relevant measurements, tests and calculations undertaken by the Operator.
     3. In addition to the Operator providing the relevant Reports pursuant to clause 32.3 in relation to a Performance Requirement for any Operations Year, a Performance Requirement will not be taken to have been achieved for the relevant Operations Year unless and until the Operator delivers to the Commonwealth:
        1. a report from an appropriately qualified independent professional firm nominated by the Operator and approved by the Commonwealth (acting reasonably) and which has no actual or perceived conflict of interest which confirms whether or not the relevant Performance Requirements has been satisfied. The Operator must ensure that the entity providing that report has agreed to permit the Commonwealth to rely on that report and is liable to the Commonwealth for the contents of that report (in each case subject to standard and reasonable limitations of liability and qualifications which that firm imposes on such reliance in the ordinary course of its business); and
        2. such other information or documentation as may be reasonably necessary to demonstrate that the Performance Requirements has been achieved in accordance with this Agreement.
  2. Performance Requirement failures
     1. Subject to this clause 10.3, where the Equivalent Availability Factor for the Facility in any Support Year is less than 90%, the Availability Rebate will apply in accordance with Schedule 4.
     2. Subject to this clause 10.3, where the energy storage capacity for the Facility for each Support Year is less than 100%, the Storage Rebate will apply in accordance with Schedule 4.
     3. If:
        1. the Equivalent Availability Factor for the Facility is less than 50%; and/or
        2. the energy storage capacity of the Facility is less than 50% of the Storage Capacity,

(**Performance Requirements (Minimum)**)in each case in any Operations Year the Operator must:

* + - 1. investigate the cause of the non-compliance; and
      2. within 20 Business Days after becoming aware of the relevant failure (**PR Cure Period**), provide a draft cure plan to the Commonwealth which demonstrates how the Operator will ensure that the relevant Performance Requirements (Minimum) will be achieved as soon as reasonably practicable (taking into account a reasonable period for contingency) in the following Operations Year (**Draft** **PR Cure Plan**).
    1. The Commonwealth must act reasonably in determining whether to approve or reject the Draft PR Cure Plan and must either approve or reject a Draft PR Cure Plan within 30 Business Days after that Draft PR Cure Plan (which complies with this Agreement) is submitted to the Commonwealth. Without limitation, it will be will be unreasonable for the Commonwealth to reject the Draft PR Cure Plan where it:
       1. is prepared in accordance with the requirements of this Agreement; and
       2. demonstrates how the Operator will ensure that the relevant Performance Requirements (Minimum) will be achieved as soon as reasonably practicable (including a reasonable period for contingency) in the following Operations Year.
    2. If the Commonwealth rejects a Draft PR Cure Plan:
       1. the Commonwealth must provide the Operator with written reasons for the rejection at the time the Draft PR Cure Plan is rejected; and
       2. the Operator may submit a revised Draft PR Cure Plan for approval by the Commonwealth in accordance with clause 10.3(d).
    3. Clauses 10.3(d) and 10.3(e)(i), but not clause 10.3(e)(ii), will apply to an amended Draft PR Cure Plan submitted by the Operator pursuant to clause 10.3(e)(ii).
    4. If the Commonwealth approves a Draft PR Cure Plan it must notify the Operator of that approval and that Draft PR Cure Plan becomes the approved cure plan on the date of that approval (**PR Cure Plan**). On and from the date on which the Commonwealth notifies the Operator of that approval, the Operator must:
       1. subject to clause 19, comply with the PR Cure Plan; and
       2. provide a report to the Commonwealth regarding its progress against the approved PR Cure Plan within 5 Business Days after the end of each Month until the Operator next satisfies the relevant Performance Requirements.
    5. If the Operator:
       1. fails to submit a Draft PR Cure Plan to the Commonwealth within the relevant PR Cure Period;
       2. has submitted a draft PR Cure Plan which has been rejected by the Commonwealth and has resubmitted the draft PR Cure Plan which (subject to clause 10.3(i)) has also been rejected, each case in accordance with this Agreement;
       3. subject to clause 10.3(g), fails to commence the implementation of the PR Cure Plan as required pursuant to clause 10.3 or otherwise fails to comply with the PR Cure Plan in any material respect, and does not remedy any such failure within 20 Business Days after receipt of a notice from the Commonwealth requiring it to do so; or
       4. fails to meet either Performance Requirement (Minimum) in respect of any two consecutive Operations Years,

the Commonwealth may terminate this Agreement by notice to the Operator, this Agreement will terminate on the date set out in that notice and that termination will be deemed to be a termination pursuant to clause 22.2.

* + 1. Where the Operator submits a Draft PR Cure Plan which has been rejected in accordance with clause 10.3(d) and submits a revised Draft PR Cure Plan for approval in accordance with clause 10.3(e)(ii), in determining whether to approve or reject that resubmitted Draft PR Cure Plan the Commonwealth may only:
       1. review and provide comments on:
          1. the new and amended information provided by or on behalf of the Operator with that resubmitted Draft PR Cure Plan;
          2. previous information supplied in relation to the relevant Draft PR Cure Plan which is impacted by that new and amended information; and
          3. any information in the Draft PR Cure Plan which is impacted by any new circumstances which have arisen after the submission of the first version of the relevant Draft PR Cure Plan; and
       2. approve or reject that resubmitted Draft PR Cure Plan based on that new and/or amended information, the previous information which has been impacted by that new and amended information and those new circumstances.
  1. The Operator is a special purpose vehicle

The Operator must: **[Drafting note: this special purpose vehicle requirement applies to the Project as a whole, including where the Contracted Percentage is less than 100%.]**

* + 1. be a special purpose vehicle established for the sole purpose of carrying on the Project and the business and activities contemplated by this Agreement; and
    2. not carry on, (or have previously carried on prior to the Signing Date), any other business or activity other than the Project or the business and activities contemplated by this Agreement.

1. Authorisations
   1. Authorisations

The Operator must obtain, maintain and comply with and ensure that the Facility complies with all Authorisations which are necessary for the performance of its obligations and/or exercise of any rights arising from or in connection with this Agreement including all conditions of such Authorisations, including those required to:

* + 1. design, construct, commission, test, complete, maintain, manage and operate the Facility; and
    2. perform its other obligations under this Agreement,

in each case in accordance with this Agreement and all applicable Laws.

* 1. Notice to Commonwealth

The Operator must promptly notify the Commonwealth if it becomes aware of any actual, pending or threatened litigation, Claim, dispute, action or circumstance of any kind concerning the Facility or the Project which is likely to have a material adverse effect on the Operator's ability to:

* + 1. perform its obligations under this Agreement;
    2. own, design, construct, commission, test, complete, operate, manage or maintain the Facility; or
    3. grant, renew, obtain, maintain or extend any Authorisation referred to in clause 11.1.

1. Insurance
   1. Insurances required

The Operator must, at its own cost, procure and maintain (or caused to be procured and maintained) insurance policies in relation to the Project consistent with Good Industry Practice, including the following insurances:

* + 1. during the Construction Period only, contract works insurance for the full replacement or reinstatement value of the Facility plus amounts sufficient to cover costs of demolition and removal of debris, including coverage for material and equipment in transit;
    2. during the Operations Period only, industrial special risks insurance for each Operations Year reflecting a combined limit of no less than the full replacement or reinstatement value of the Facility, plus amounts sufficient to cover costs of demolition and removal of debris, professional fees and an amount to cover additional costs and expenses to expedite the commencement and completion of the repair, replacement or reinstatement of the Facility;
    3. throughout the Term:
       1. public and products (completed operations) liability insurance for an amount of at least $20 million (Indexed) for each and every occurrence and in the annual aggregate regards to product liability and completion operations;
       2. workers' compensation scheme insurance and motor vehicle liability insurance as required by Law; and
       3. any other insurance required by Law.
  1. Insurer

The insurances required to be procured and maintained under each of clauses 12.1(a), 12.1(b) and 12.1(c)(i) must be maintained with an insurance company that has a Required Rating.

* 1. Maintenance of Insurance Policies

The Operator must maintain the Insurance Policies until the end of the relevant period specified in clause 12.1.

* 1. Evidence of insurance
     1. Within 10 Business Days after being requested to do, the Operator must provide the Commonwealth, with a current certificate of currency and any other evidence the Commonwealth may reasonably require as evidence that the Operator has complied with its obligations under this clause 12.
     2. If the Operator fails to provide evidence reasonably satisfactory to the Commonwealth of any insurance when required to do so under clause 12.4(a), the Commonwealth may procure the relevant insurance and the Operator must pay the costs of procuring that insurance to the Commonwealth within 20 Business Days after a receipt of a request to do so.
  2. Non-vitiation

The Operator must not commit, and must ensure that its Associates do not commit, any act or omission which is in contravention of an insurance policy maintained by the Operator or an Operator Associate or which may result in that insurance policy becoming void or voidable or which may result in the relevant insurer refusing liability under that policy.

1. Alterations to the Facility
   * 1. Subject to clause 13(f), the Operator must not (and must procure its Related Bodies Corporate not to) make or permit (or agree to make or permit) any alteration, expansion or change to the Facility without the Commonwealth’s written consent.
     2. The Commonwealth's consent under clause 13(a) must not be unreasonably withheld or delayed where the proposed alteration, expansion or change will not:
        1. materially or adversely impact:
           1. the Commonwealth’s rights and obligations under:

this Agreement, including its financial rights and obligations; or

any financial product which the Commonwealth has entered into with a third party in relation to this Agreement or the Capacity Investment Scheme; or

* + - * 1. the Operator’s performance of (or ability to perform) its obligations under the Project Documents including the Social Licence Commitments; or
      1. result in the Facility no longer:
         1. being capable of dispatching at or above its Maximum Capacity through the Connection Point or importing electrical energy capacity at or above its Import Capacity through the Connection Point; or
         2. having an energy storage capacity that is equal to exceeds the Storage Capacity,

in each case for any Operations Year (or Quarter in any Operations Year);

* + - 1. result in installation of a new generating system, energy storage system or load behind the Connection Point;
      2. result in any reduction to any one or more of the Registered Capacity, Maximum Capacity, Contracted Capacity, Storage Capacity or Import Capacity of the Facility.
    1. The Operator must notify the Commonwealth where the Operator proposes to make any alteration, expansion or change to the Facility (including where the Operator is not required to seek consent from the Commonwealth for that alteration, expansion or change) and with that notice provide the Commonwealth with sufficient information to assess the proposed alteration, expansion or change and its impact, including in respect of the matters referred to in clause 13(b). That notice must be provided by the Operator to the Commonwealth:
       1. at least 10 Business Days after the date on which the Operator commenced that alteration, expansion or change to the Facility where the alternation, expansion or change to the Facility arose from undertaking emergency or unplanned maintenance on the Facility in accordance with Good Electricity Industry Practice or was necessary to prevent injury, death or damage to the Environment or the Facility; and
       2. at least 20 Business Days prior to the date on which the Operator proposes to commence that alteration, expansion or change to the Facility in all other cases.
    2. Where reasonably requested by the Commonwealth, the Operator must, within 10 Business Days after receipt of that request, provide the Commonwealth with additional information in writing regarding any alteration, expansion or change to the Facility.
    3. For the avoidance of doubt, the Commonwealth is not required to provide such consent under clause 13(a) until after the Operator provides all information which the Operator is required to provide pursuant to this clause 13.
    4. The Operator is not required to seek consent pursuant to clause 13(a) where the relevant alternation, expansion or change to the Facility arises out of the Operator:
       1. undertaking maintenance and repairs on the Facility arising out of fair wear and tear;
       2. undertaking emergency or unplanned maintenance on the Facility in accordance with Good Electricity Industry Practice;
       3. any action which is necessary to prevent injury, death or damage to the Environment or the Facility or required to maintain manufacturer's warranties; or
       4. remedying any physical damage to the Facility,

and in each case, the alteration, expansion or change to the Facility would not have otherwise given the Commonwealth right to withhold its consent to such an alteration, expansion or change pursuant to clause 13(b) had this clause 13(f) not applied.

1. Social Licence
   1. Obligation to comply
      1. The Operator must comply with the Social Licence Commitments.
      2. The Operator must promptly notify the Commonwealth if it fails or becomes likely to fail to comply with any of the Social Licence Commitments.
   2. Reports and auditing
      1. The Operator must provide a report to the Commonwealth within:
         1. 10 Business Days after the Operator first satisfies all Social Licence Commitments which are required to be satisfied prior to the Commercial Operation Date, demonstrating the Operator's satisfaction of those commitments;
         2. 20 Business Days after the end of each Quarter thereafter until the date which is at the end of the second Operating Year, detailing the Operator's progress in satisfying the Social Licence Commitments during that Quarter;
         3. within 20 Business Days after the end of each Operating Year thereafter, detailing the Operator's progress in satisfying the Social Licence Commitments during that Operating Year provided however that where the Operator breaches any obligation to comply with any Social Licence Commitment, the obligation to report will immediately revert to a Quarterly basis in accordance with clause 14.2(a)(ii) from the date of the breach until to the end of the Term (unless otherwise determined by the Commonwealth acting reasonably).
      2. Each such report must:
         1. be in the reporting format specified by the Commonwealth (acting reasonably) from time to time (if any);
         2. be certified by a director of the Operator to be true and correct;
         3. include:
            1. sufficient information for the Commonwealth to assess the Operator's performance in satisfying the Social Licence Commitments; and
            2. any specific or additional information reasonably requested by the Commonwealth.
      3. Subject to clause 14.2(d), within 20 Business Days after receiving the Operator’s report under clause 14.2(a), the Commonwealth must:
         1. in the case of a report identified in clause 14.2(a)(i), confirm whether or not the Operator has satisfied all Social Licence Commitments that are required to be satisfied prior to the Commercial Operation Date;
         2. request any further information from the Operator that the Commonwealth reasonably requires in order to assess whether the Operator has satisfied those Social Licence Commitments; or
         3. reject that report where it does not comply with the requirements of this Agreement or the Social Licence Commitments set out that report have not been satisfied.
      4. If the Commonwealth requests any further information from the Operator under clause 14.2(c)(ii), within:
         1. 20 Business Days after the Operator receives the Commonwealth’s request, the Operator must provide the requested information to the Commonwealth; and
         2. 40 Business Days after receiving the requested information from the Operator, the Commonwealth must use reasonable endeavours to either confirm or reject the Operator’s report under clause 14.2(c).
      5. If the Operator does not provide the requested information under clause 14.2(c)(ii) within the period identified in clause 14.2(d)(i), the Commonwealth is deemed to have rejected the Operator’s report.
      6. If the Commonwealth rejects, or is deemed to reject, the Operator’s report:
         1. other than where the Operator's report is deemed to have been rejected by the Commonwealth pursuant to clause 14.2(e), the Commonwealth must provide reasonable details of its reasons; and
         2. within 20 Business Days after the Operator’s report is rejected, the Operator must amend and resubmit an updated report to the Commonwealth.
      7. Clauses 14.2(c) to 14.2(f) will apply to the updated report submitted by the Operator pursuant to clause 14.2(f).
   3. Audit
      1. The Commonwealth may audit or cause a third party to audit the Operator’s performance of the Social Licence Commitments at any time in accordance with clause 31.4.
   4. Non-compliance

If following:

* + 1. the receipt of the Operator’s report and any additional information requested by the Commonwealth under clause 14.2(c)(ii);
    2. the expiry of the 20 Business Day period in which the Operator must provide any additional information requested by the Commonwealth under clause 14.2(c)(ii); or
    3. the completion of an audit of the Operator’s performance of its Social Licence Commitments in accordance with clause 31.4,

the Commonwealth determines (acting reasonably) that the Operator is not complying with its obligation to perform the Social Licence Commitments, then the Commonwealth may give a notice to the Operator which:

* + 1. specifies each Social Licence Commitment with which the Operator has failed to comply; and
    2. may specify whether the Commonwealth considers the Operator’s non-compliance to be not remediable, in which case the Commonwealth will provide reasonable details of its reasons.
  1. SLC Cure Plan
     1. If:
        1. the Operator gives notice under clause 14.1(b); or
        2. the Commonwealth issues a notice under clause 14.4,

the Operator must submit a cure plan to the Commonwealth within 20 Business Days (**Draft SLC Cure Plan**).

* + 1. A Draft SLC Cure Plan must identify:
       1. the steps which the Operator is taking or will take to remedy its failure to comply with its Social Licence Commitments;
       2. the progress made by the Operator in satisfying the relevant Social Licence Commitments;
       3. the Operator’s estimate of when the non-compliance will be remedied where that estimate is provided on the basis that the Operator is required to remedy that non-compliance as soon as reasonably practicable (including a reasonable period for contingency); and
       4. if the Operator or the Commonwealth considers that a non-compliance cannot be remedied, an alternative proposal to the relevant Social Licence Commitment or part of a Social Licence Commitment. The alternative proposal may include:
          1. the payment of an amount to the Commonwealth in lieu of complying with the relevant Social Licence Commitment; or
          2. an alternative to the relevant Social Licence Commitment which is of equivalent or greater merit than that Social Licence Commitment.
    2. The Commonwealth will determine (acting reasonably) whether any proposed alternative to the Social Licence Commitment is acceptable to the Commonwealth, having regard to the original Social Licence Commitment.
    3. The Commonwealth must act reasonably in determining whether to approve or reject a Draft SLC Cure Plan submitted under clause 14.5(a) and must use reasonable endeavours to either approve or reject a Draft SLC Cure Plan by notice in writing to the Operator within 60 Business Days after that Draft SLC Cure Plan (which complies with this Agreement) is submitted to the Commonwealth. Without limitation, it will be unreasonable for the Commonwealth to reject the Draft SLC Cure Plan where it:
       1. is prepared in accordance with the requirements of this Agreement;
       2. identifies reasonable steps which if implemented by the Operator will remedy the Operator's failure to comply with its Social Licence Commitments;
       3. identifies a date for the satisfaction of the relevant Social Licence Commitments which is as soon as reasonably practicable (including a reasonable period for contingency) after the Operator submits the Draft SLC Cure Plan to the Commonwealth; and
       4. demonstrates that the Operator will be able to satisfy the relevant Social Licence Commitments on or before the proposed revised dates or includes an alternative proposal which includes payment of a reasonable amount in lieu of complying with the relevant Social Licence Commitment or which is of equivalent or greater merit than that Social Licence Commitment.
    4. If the Commonwealth rejects a Draft SLC Cure Plan:
       1. the Commonwealth must provide the Operator with reasonable details of its reasons at the time the Draft SLC Cure Plan is rejected and may suggest amendments to the Draft SLC Cure Plan, which may include an assessment of the merit of any alternative proposal made by the Operator; and
       2. within 20 Business Days after the draft SLC Cure Plan is rejected, the Operator must amend and resubmit the revised Draft SLC Cure Plan to the Commonwealth for approval in accordance with clause 14.5(d).
    5. Clauses 14.5(c), 14.5(d) and 14.5(e)(i), but not clause 14.5(e)(ii), will apply to an amended Draft SLC Cure Plan submitted by the Operator pursuant to clause 14.5(e)(ii).
    6. If the Commonwealth approves a Draft SLC Cure Plan it must notify the Operator of that approval and that Draft SLC Cure Plan becomes the approved cure plan on the date of that approval (**SLC Cure Plan**). On and from the date on which the Commonwealth notifies the Operator of that approval:
       1. subject to clauses 8 and 19, the Operator must comply with the SLC Cure Plan; and
       2. the Operator must provide a report to the Commonwealth regarding its progress against the SLC Cure Plan within 5 Business Days after the end of each calendar month until the relevant non-compliances the subject of the SLC Cure Plan have been satisfied by the Operator or waived by the Commonwealth.
  1. Termination regarding SLCs
     1. Subject to clause 14.6(b), if the Operator:
        1. fails to submit or resubmit a draft SLC Cure Plan when required under clause 14.5;
        2. has submitted a draft SLC Cure Plan which has been rejected by the Commonwealth and has resubmitted the draft SLC Cure Plan which (subject to clause 14.6(c)) has also been rejected, each case in accordance with this Agreement;
        3. subject to clause 14.5(g), fails to commence the implementation of the SLC Cure Plan or otherwise fails to comply with the SLC Cure Plan in any material respect, and does not remedy that failure within 10 Business Days after receipt of notice from the Commonwealth requiring it to do so; or
        4. fails to make any cash payment contemplated in an approved SLC Cure Plan and the Operator has not cured that failure within 20 Business Days after receipt of a request from the Commonwealth to do so,

the Commonwealth may terminate this Agreement by notice to the Operator, this Agreement will terminate on the date set in that notice and that termination will be deemed to be a termination pursuant to clause 22.2.

* + 1. The Commonwealth must not terminate this Agreement pursuant to clause 14.6(a) if the Operator has submitted or resubmitted a Draft SLC Cure Plan to the Commonwealth under clause 14.6(a) and the Commonwealth has not yet approved or rejected the Draft SLC Cure Plan under clause 14.5(d).
    2. Where the Operator submits a Draft SLC Cure Plan which has been rejected in accordance with clause 14.5(d) and submits a revised Draft SLC Cure Plan for approval in accordance with clause 14.5(e)(ii), in determining whether to approve or reject that resubmitted Draft SLC Cure Plan the Commonwealth may only:
       1. review and provide comments on:
          1. the new and amended information provided by or on behalf of the Operator with that resubmitted Draft SLC Cure Plan;
          2. previous information supplied in relation to the relevant Draft SLC Cure Plan which is impacted by that new and amended information; and
          3. any information in the Draft SLC Cure Plan which is impacted by any new circumstances which have arisen after the submission of the first version of the relevant Draft SLC Cure Plan; and
       2. approve or reject that resubmitted Draft SLC Cure Plan based on that new and/or amended information, the previous information which has been impacted by that new and amended information and those new circumstances.

1. Knowledge Sharing
   * 1. The Operator must provide the Knowledge Sharing Deliverables to the Commonwealth in accordance with, and otherwise comply with, the Knowledge Sharing Plan.
     2. The Operator must, acting reasonably and in Good Faith, categorise each Knowledge Sharing Deliverable it provides to the Commonwealth pursuant to this clause 15 as follows:
        1. **public information:** information that may be shared freely within the Commonwealth, with industry participants and with the general public; or
        2. **confidential information:** information that may only be shared in accordance with clause 15(c) or clause 30.
     3. The Commonwealth may disclose information received pursuant to this clause 15 that is marked by the Operator or identified in the Knowledge Sharing Plan as 'confidential information' to the public on an aggregated and anonymised basis.
     4. Where the Operator submits a Knowledge Sharing Deliverable to the Commonwealth the Commonwealth (acting reasonably) will notify the Operator within a reasonable period of receipt of the Knowledge Sharing Deliverable as to whether or not it approves the Knowledge Sharing Deliverable for the purposes of this Agreement. Without limitation, it will be unreasonable for the Commonwealth to reject that Knowledge Sharing Deliverable where it complies with the Knowledge Sharing Plan and this Agreement.
     5. Where the Commonwealth notifies the Operator under clause 15(d) that it does not approve the Knowledge Sharing Deliverable, the Commonwealth must, at the same time, notify the Operator of such further information or updates to the deliverable that the Commonwealth reasonably considers are required in order for the deliverable to meet the requirements of this Agreement and/or the Knowledge Sharing Plan and a reasonable timeframe within which the Operator must resubmit that Knowledge Sharing Deliverable. Where the Operator fails to resubmit that further information or updated Knowledge Sharing Deliverable within that timeframe, that failure will be deemed to be a failure to comply with clause 15 in a material respect and clause 22.2(e) will apply to that failure.
     6. Where the Operator resubmits that further information and/or an updated Knowledge Sharing Deliverable in accordance with clause 15(e), the Commonwealth (acting reasonably) will notify the Operator within a reasonable period of receipt of that further information and/or updated Knowledge Sharing Deliverable whether or not it approves that further information and/or updated deliverable for the purposes of this Agreement. Where the Commonwealth it does not approve that further information and/or updated deliverable, that failure by the Operator to submit further information and/or updated a Knowledge Sharing Deliverable to the Commonwealth in accordance with this clause 15 will be deemed to be a failure to comply with clause 15 in a material respect and clause 22.2(e) will apply to that failure.
     7. Without limitation, it will be unreasonable for the Commonwealth to reject a Knowledge Sharing Deliverable, further information provided by the Operator to the Commonwealth pursuant to this clause 15 and/or any updated Knowledge Sharing Deliverable where it complies with the Knowledge Sharing Plan and this Agreement.
2. Invoicing and Payment
   1. Payment Notice and Invoicing
      1. For each Quarter during the Support Period (other than the last Quarter in each Support Year), on or before the date which is 20 Business Days after the end of that Quarter the Operator must deliver to the Commonwealth a notice setting out for that Quarter:
         1. the amount of the Quarterly Payment (if any), determined in accordance with Schedule 4;
         2. the amount of GST (if any) payable in relation to each taxable supply related to that Quarterly Payment; and
         3. any other requirement notified by the Commonwealth to the Operator.
      2. For each Support Year, on or before the date which is 20 Business Days after the end of that Support Year, the Operator must deliver to the Commonwealth a notice setting out for that Support Year:
         1. each amount to which the Commonwealth or the Operator is entitled under this Agreement (if any);
         2. any adjustments to any previous Payment Notice or amount payable under this Agreement pursuant to clause 16.4;
         3. the amount of GST (if any) payable in relation to each taxable supply related to those amounts;
         4. the net amount of the above amounts which are payable either by the Commonwealth or the Operator (as applicable); and
         5. any other requirement notified by the Commonwealth to the Operator.
      3. If the Operator fails to issue a Payment Notice for a Quarter or Support Year or fails to include an amount to which the Commonwealth is entitled under this Agreement in a Payment Notice for a Quarter or Support Year, the Commonwealth may issue a notice to the Operator for that Quarter or Support Year which sets out the relevant information which the Operator should have included in that Payment Notice.
      4. On request by the Commonwealth, the Operator must provide information or other evidence reasonably requested by the Commonwealth to verify the information set out in any Payment Notice issued pursuant to clause 16.1(a) or 16.1(b) within 10 Business Days after receipt of that request.
      5. If the amount referred to in a Payment Notice:
         1. issued by the Operator pursuant to clause 16.1(a) or 16.1(b) is an amount payable by:
            1. the Commonwealth to the Operator, the Operator must issue an invoice for that amount to the Commonwealth on the same day that the Operator issues that Payment Notice; or
            2. the Operator to the Commonwealth, the Commonwealth must issue an invoice for that amount to the Operator on or before the date which is 5 Business Days after the Commonwealth receives the relevant Payment Notice; or
         2. issued by the Commonwealth pursuant to clause 16.1(c) is an amount payable by:
            1. the Commonwealth to the Operator, the Operator must issue an invoice for that amount to the Commonwealth on or before the date which is 5 Business Days after the Commonwealth receives that Payment Notice; or
            2. the Operator to the Commonwealth, the Commonwealth must issue an invoice for that amount to the Operator on the same day that the Commonwealth issues that Payment Notice.
      6. Any party making a taxable supply under this Agreement in relation to an invoice identified under clause 16.1(e) must also provide a tax invoice for that supply to the recipient of that supply, in accordance with clause 18.4.
   2. Payment

Subject to clause 16.3 and 16.6, if an amount is stated to be payable in a Payment Notice, the party which is obliged to pay that amount must pay that amount to the other party on the date which is:

* + 1. where the Operator is obliged to pay that amount, the date which is 20 Business Days after the date on which the Operator is obliged to provide the relevant Payment Notice related to that amount to the Commonwealth; and
    2. where the Commonwealth is obliged to pay that amount, the date which is 20 Business Days after the earlier of the date on which it either receives or issues that Payment Notice (as applicable).
  1. Disputed Invoice
     1. If a party that is required to pay an amount referred to in a Payment Notice or an invoice reasonably believes the Payment Notice or invoice or any component of the Payment Notice or invoice does not comply with the requirements of this Agreement:
        1. it must notify the other party of issues in dispute (including the amount in dispute (**Disputed Amount**)) and provide a statement of its reasons for disputing the Payment Notice or invoice (as applicable); and
        2. if a party is required to pay an amount identified in that Payment Notice or invoice, that party must pay that part of the Payment Notice or invoice which is not in dispute.
     2. If a party notifies the other party of any issue in dispute (including any Disputed Amount) pursuant to clause 16.3(a)(i), the parties must meet as soon as practicable after the other party receives that notice, and in any event within 10 Business Days after the other party receives that notice, to discuss the issues in dispute including that Disputed Amount.
     3. If following the end of that 10 Business Day period the parties have not agreed a resolution in respect of those issues in dispute (including any Disputed Amount), and a party wishes to progress the Dispute, that Dispute must be referred by that party for determination by an Independent Expert pursuant to clauses 35.4(b)(ii) and 35.6 and for the avoidance of doubt, clauses 35.4(b)(i) and 35.5 will not apply to that Dispute.
     4. A party must pay any Disputed Amounts within 10 Business Days after the date of resolution of the Dispute (whether by agreement or determination by an Independent Expert) in respect of the Disputed Amount.
  2. Adjustments
     1. Subject to clause 16.4(c), at any time after a Payment Notice has been issued pursuant to this Agreement, the Operator must adjust the next prepared Payment Notice (and any associated invoice issued by the Operator) to the extent required to reflect any changes to the inputs that were used to determine or prepare that Payment Notice, including any change under a Revised Statement.
     2. The Operator must include any adjustments in the next prepared Payment Notice (and invoice).
     3. Other than adjustments for Revised Statements, no adjustment will be made to a Payment Notice (or invoice) more than 3 years after the end of the Quarter or Support Year (as applicable) that is the subject of the Payment Notice (or invoice).
     4. If a party pays the other party an amount arising from or in connection with this Agreement and it is subsequently agreed or determined for any reason that the recipient was not entitled to that payment, in whole or in part, the recipient must refund that payment (or such part as constitutes an overpayment) as a debt due and payable to the party that made the payment together with interest calculated in accordance with clause 16.5 on that amount. That refund must be paid by the recipient to the party that made the payment on or before the date which is 40 Business Days after the date on which it is agreed or determined that the recipient was not entitled to that payment.
     5. The payment of any amount identified in any Payment Notice by the Commonwealth to the Operator and the issuing of any invoice or tax invoice related to that Payment Notice (as the case may be) is not evidence that the obligations the subject of that Payment Notice, invoice or tax invoice have been carried out by the Operator in accordance with the Project Documents, or an admission of liability, and is only to be taken as payment on account.
     6. Where the Operator believes that there is an error in any previous Payment Notice or invoice issued by the Operator, the Operator must notify the Commonwealth of that error and provide reasonable details regarding that error in that notice. The Commonwealth may, in any Payment Notice or invoice, correct any error in any previous Payment Notice or invoice issued by the Commonwealth or the Operator.
  3. Interest on late payments
     1. Subject to clause 16.5(b), if an amount payable by a party under this Agreement (including an amount determined to be payable as the result of a Dispute) is not paid by the due date, interest will accrue on the unpaid amount from day to day at the Default Interest Rate from (and including) the date the original payment was due and payable to:
        1. in the case of a Disputed Amount, the later of the date of resolution of the Dispute (whether by agreement or determination by an Independent Expert) in respect of the Disputed Amount and the date on which that part of the Disputed Amount which the parties have agreed or the Independent Expert has determined is paid; or
        2. otherwise, the date the original payment was due and payable to the date the unpaid amount is paid in full.
     2. Notwithstanding anything to the contrary in this Agreement, a Termination Payment will be deemed to be due and payable and interest will accrue on the unpaid amount of a Termination Payment from day to day at the Default Interest Rate from and including the date which is 60 Business Days after this Agreement is terminated until that unpaid amount is paid.
  4. Set off
     1. After providing prior written notice to the Operator of its intention to do so, the Commonwealth may deduct from any amounts due and payable by the Commonwealth to the Operator under any of the Project Documents or otherwise at Law:
        1. any amount due and payable by the Operator to the Commonwealth under any of the Project Documents or otherwise at Law; and
        2. the amount of any Claim that the Commonwealth may have against the Operator under any of the Project Documents or otherwise at Law.
     2. The Operator must make all payments to the Commonwealth free from any set-off or counterclaim and without deduction or withholding for or on account of any present or future Tax, unless the Operator is compelled by Law to make such a deduction or withholding.
     3. If a party is compelled by Law to make a deduction or withholding for the benefit of a Government Agency, it must:
        1. remit the deducted or withheld amount to the relevant Government Agency within the time required by Law; and
        2. provide to the other party all information and documentation relating to that deduction or withholding, including any information or documentation required to obtain a credit for or repayment of the deducted or withheld amount from a Government Agency.

1. Taxes

Subject to clause 18, as between the Commonwealth and the Operator, the Operator is solely liable for payment of all Taxes which may arise from or be payable in connection with any Project Document, any payments under any Project Document and/or the Project.

1. GST
   1. Definitions and interpretation

Words and phrases which have a defined meaning in the GST Law have the same meaning when used in this clause 18, unless the contrary intention appears.

* 1. GST Exclusive Consideration

Unless this Agreement expressly states otherwise, all consideration to be provided under this Agreement is exclusive of GST.

* 1. Barter supply

The parties have entered this Agreement on the assumption that, in accordance with the principles set out in public GST ruling *GSTR 2001/6 – GST and non-monetary consideration and GST Determination GSTD 2005/3 – Goods and services tax: are contracts for difference and financial spread betting contracts financial supplies?*, that:

* + 1. upon execution of this Agreement, the following supplies will be made for GST purposes:
       1. the Commonwealth is making an input taxed financial supply of entry into the arrangements specified under Schedule 4, in return for the Operator's entry into the arrangements specified under Schedule 4;
       2. the Operator is making an input taxed financial supply of entry into the arrangements specified under Schedule 4, in return for the Commonwealth's entry into the arrangements specified under Schedule 4;
    2. as a result, any payments by the parties to each other under Schedule 4 represent further consideration for the input taxed supply of entry (by the recipient of those payments) into the arrangements specified under Schedule 4, and therefore are not subject to GST – consistent with paragraph 27 of GSTD 2005/3; and
    3. neither party makes a taxable supply to the other party under the provisions of, or by agreeing to the obligations set out in, this Agreement.
  1. GST gross-up

Notwithstanding clause 18.3, if a party (**Supplier**) makes a supply under or in connection with this Agreement on which GST is imposed, in whole or in part (not being a supply the consideration for which is specifically described in this Agreement as inclusive of GST) then:

* + 1. the consideration payable or to be provided for that supply under this Agreement but for the application of this clause (**GST Exclusive Consideration**) is increased by, and the recipient of the supply (**Recipient**) must also pay to the Supplier, an amount equal to the GST payable on the supply (**GST Amount**); and
    2. the GST Amount must be paid to the Supplier by the Recipient without set off, deduction or requirement for demand, at the same time as the GST Exclusive Consideration is payable or to be provided, subject to the Supplier giving the Recipient a tax invoice in respect of that taxable supply.
  1. Payments and reimbursements
     1. If a payment to a party under this Agreement is a reimbursement or indemnification, calculated by reference to a loss, cost or expense incurred by that party, then the payment will be reduced by the amount of any input tax credit to which that party, or the representative member of a GST group of which that party is a member, is entitled for that loss, cost or expense.
     2. If a payment is calculated by reference to, or as a specified percentage of, another amount or revenue stream, that payment shall be calculated by reference to, or as a specified percentage of, the amount or revenue stream exclusive of GST.
  2. Adjustments

If an adjustment event arises in respect of a supply made under or in connection with this Agreement, then:

* + 1. the Supplier must issue an adjustment note to the Recipient within 7 days of the adjustment event occurring or otherwise as soon as it becomes aware of the adjustment event, outlining the revised amount of GST payable in respect of that supply (**Corrected GST Amount**);
    2. if the Corrected GST Amount is less than the previously attributed GST Amount, the Supplier shall refund the difference to the Recipient within 15 days of the adjustment note being issued by the Supplier; and
    3. if the Corrected GST Amount is greater than the previously attributed GST Amount, the Recipient shall pay the difference to the Supplier within 15 days of the adjustment note being issued by the Supplier.
  1. No Partnership

In reliance on Public GST Rulings GSTR 2003/13 and 2004/6, the parties acknowledge and agree that they do not intend to form a general law partnership or a tax law partnership in entering into this Agreement.

1. Force Majeure
   1. Project Force Majeure Event
      1. Subject to clause 19.1(b), a Project force majeure event (**Project Force Majeure Event**) means any event or circumstance or combination of events or circumstances occurring after the Signing Date which:
         1. is not within the reasonable control of the Affected Party or any of its Associates;
         2. could not have been prevented or overcome by the Affected Party or any of its Associates exercising reasonable care or complying with its obligations under this Agreement (including by implementing Good Industry Practice); and
         3. prevents or delays the Affected Party complying with any of its obligations (other than an obligation to pay amounts) under this Agreement including causing the Facility to be unable to export, import or store energy.
      2. For the purposes of clause 19.1(a), each of the following does not constitute a Project Force Majeure Event:
         1. a Connection Force Majeure Event;
         2. lack of funds, financial hardship, failure or inability of any person to pay any sum due and payable or the inability of the Affected Party or any of its Associates to obtain financing or insurance or to make a profit or achieve a satisfactory rate of return;
         3. a shortage or delay in delivery of materials, consumables, equipment or utilities required by the Affected Party or any of its Associates or any failure by the Affected Party or any of its Associates to hold sufficient stock of spares except to the extent that shortage or delay is caused by any Project Force Majeure Event or any event or circumstance which would have been a Project Force Majeure Event had this paragraph (iii) not applied;
         4. a malfunction, temporary unavailability, breakdown or failure of equipment, property or assets caused by fair wear and tear;
         5. any event or circumstance arising due to a failure by the Operator, any of its Related Bodies Corporate or any of its or their respective Associates to properly maintain any equipment, property or asset in accordance with Good Industry Practice except to the extent that failure to properly maintain is caused by any Project Force Majeure Event or any event or circumstance which would have been a Project Force Majeure Event had this paragraph (iv) not applied;
         6. strikes, industrial disputes or other industrial actions or disruption that only affect the Facility or the Affected Party or any of its Associates at the Project site;
         7. failure of any person (other than the party to this Agreement which is not an Affected Party) to perform an obligation it owes to the Affected Party or any of its Associates, except where such failure is caused by any event or circumstance that, if such event or circumstance had happened to the Affected Party under this Agreement, would have constituted a Project Force Majeure Event or any event or circumstance which would have been a Project Force Majeure Event had this paragraph (vii) not applied;
         8. a failure to obtain or delay in obtaining an Authorisation required to be held by a party to perform its obligations under this Agreement or at Law;
         9. any absence, failure, lack or excess of any Input Resource, at the site of the Facility;
         10. wet or inclement weather (other than extreme storms, floods, hurricanes, cyclones, tornados, typhoons, tsunamis, ice and ice storms); and
         11. any Change in Law (other than Pandemic Change in Law).
   2. Connection Force Majeure Event
      1. Subject to clause 19.2(b), a connection force majeure event (**Connection Force Majeure Event**) means any event or circumstance or combination of events or circumstances occurring after the Signing Date but before COD which:
         1. is not within the reasonable control of the Operator or any of its Associates (other than AEMO or the network service provider for the Facility);
         2. could not have been prevented or overcome by the Operator or any of its Associates (other than AEMO or the network service provider for the Facility) exercising reasonable care or complying with its obligations under this Agreement (including by implementing Good Industry Practice);
         3. occurs or is subsisting when the Facility is otherwise ready to be energised;
         4. solely relates to the connection of the Facility to the Network and/or the commissioning of the Facility in accordance with the NER, and not to the procurement, design, construction or completion of the Facility; and
         5. prevents or delays the Facility from exporting electrical energy at a level of output that is equal to or exceeds the Maximum Capacity.
      2. For the purposes of clause 19.2(a), each of the following does not constitute a Connection Force Majeure Event:
         1. a Project Force Majeure Event; and
         2. any Change in Law.
      3. Connection Force Majeure Event includes the Facility being unable to directly export Energy to the Network because:
         1. of the Operator's obligations under Law, including a legally binding direction from AEMO or a Network Service Provider; or
         2. the Network conditions are not in accordance with the requirements of the connection agreement related to the Facility,

other than where such obligations or Network conditions are due to an act or omission of the Operator or the Operator being in breach of that connection agreement, applicable Law or this Agreement.

* 1. Notification

If a Force Majeure Event occurs the Affected Party must:

* + 1. notify the other party of the event as soon as reasonably practicable (and in any event not later than 20 Business Days following the date on which the Affected Party first became aware of the occurrence of that event) and provide reasonable details of the event and related circumstances;
    2. within 10 Business Days after the Affected Party delivers the notice referred to in clause 19.3(a), provide to the other party reasonable details of:
       1. the facts and circumstances constituting the Force Majeure Event (to the extent not already notified under clause 19.3(a));
       2. any obligations affected or likely to be affected by the Force Majeure Event;
       3. the action being taken to mitigate the effects of the Force Majeure Event;
       4. the likely duration of the impact of the Force Majeure Event and any related delay in the performance of the affected obligations; and
    3. provide the other party with an update of those details every two weeks, or such other frequency as may be agreed between the parties in writing, on the impact of the Force Majeure Event.
  1. Suspension of obligations
     1. Subject to the remainder of this clause 19.4 and clause 19.5, if a Force Majeure Event occurs and prevents the Affected Party from performing its obligations under this Agreement, the Affected Party's obligations (other than an obligation to pay amounts) will be suspended to the extent that and for as long as the Affected Party is prevented from performing them by that Force Majeure Event or its impacts.
     2. An Affected Party will only be granted relief under clause 8 and this clause 19.4 if it has complied with clauses 19.3 and 19.7 in respect of the relevant Force Majeure Event and to the extent that it has not caused or contributed to that Force Majeure Event or its impacts.
  2. Accrued rights and obligations

Suspension of any obligations pursuant to clause 19.4 will not affect:

* + 1. any rights or obligations which may have accrued prior to the occurrence of the Force Majeure Event; or
    2. if the Force Majeure Event affects only some obligations, any other rights and obligations of the Affected Party or other rights and obligations of the other party.
  1. Extension
     1. Without limiting clause 19.4, if this Agreement requires an obligation to be performed or any act, matter, event, circumstance or thing to be achieved by a specified date (other than the Final Support Commencement Date), then to the extent that a Force Majeure Event directly delays the Operator's ability to perform that obligation or achieve that act, matter, event, circumstance or thing, the relevant date (other than the Final Support Commencement Date) will be extended by a period equal to the delay caused to the Operator performing that obligation or achieving that act, matter, event, circumstance or thing by the specified date.
     2. This clause 19.6:
        1. is without prejudice to clause 8.1; and
        2. does not apply to any obligation to be performed or thing to be achieved under this Agreement prior to the commencement of the Operations Period.
  2. Mitigation
     1. If a Force Majeure Event occurs the Affected Party must, as soon as practicable after the occurrence of that Force Majeure Event and for as long as the effects of that Force Majeure Event persist, use reasonable endeavours (including by implementing Good Industry Practice) to mitigate the consequences of that Force Majeure Event and (where applicable) mitigate any resulting impact on the performance of the obligations of the Affected Party.
     2. Any period of extension or suspension to which the Operator is expressly entitled under this Agreement due to a Force Majeure Event under this Agreement shall exclude any delay in the performance of the affected obligation attributable to a failure by the Affected Party to comply with clause 19.7(a).
  3. Impact on payments

Neither party is relieved of its obligations under clause 16 during the period of any suspension for a Force Majeure Event.

* 1. Termination for extended Force Majeure Event
     1. If a Force Majeure Event occurs and impacts at least:
        1. 50% of the Maximum Capacity (in MW); and/or
        2. 50% of the Storage Capacity (in MWh),

for a continuous period of 18 months commencing from the first date of the Force Majeure Event, the Commonwealth may terminate this Agreement by notice to the Operator, this Agreement will terminate on the date set out in that notice and that termination will be deemed to be a termination pursuant to clause 22.2.

* + 1. Termination under this clause 19.9 is without liability to either party, other than in respect of any Liability accrued as at the date of termination.
  1. Cessation
     1. Any relief or an extension to which an Affected Party is entitled pursuant to clause 19.4 or 19.6 (as applicable) ends, in respect of an obligation, immediately on the date on which the Affected Party ceases to be prevented from performing that obligation by the relevant Force Majeure Event and its impacts.
     2. The Affected Party must promptly notify the other party when a Force Majeure Event and it impacts cease or when it ceases to be prevented from performing any obligation in respect by the relevant Force Majeure Event and its impacts for which it has claimed relief or an extension under clause 19.4 or 19.6 (as applicable).
  2. Pre-existing Force Majeure Event

Each party represents and warrants that as at the date of this Agreement it is not aware of any event, combination of events or circumstance that constitutes or is likely to constitute a Force Majeure Event.

1. Reinstatement
   1. Reinstatement Event

If a Reinstatement Event occurs, the Operator must provide the Commonwealth with either:

* + 1. a notice that the Operator elects to reinstate the Facility (**Election to Reinstate**), including the Operator’s proposed plan to reinstate the Project to the condition it was in immediately prior to the Reinstatement Event and applying Good Industry Practice as soon as reasonably practicable (including a reasonable period of contingency) after that Reinstatement Event occurs (**Proposed Reinstatement Plan**); or
    2. a notice that the Operator elects to not reinstate the Facility,

provided that if the Operator does not provide an Election to Reinstate by the date that is 6 months after the occurrence of the Reinstatement Event (or any such longer period agreed by both parties, acting reasonably), the Operator will be deemed to have elected to not reinstate the Facility.

* 1. Reinstatement plan
     1. If the Commonwealth receives an Election to Reinstate:
        1. the Commonwealth must acting reasonably either:
           1. subject to clause 20.2(b), request any reasonable changes to the Proposed Reinstatement Plan; or
           2. approve the Proposed Reinstatement Plan,

provided that:

* + - * 1. if the Commonwealth does not request any changes to the Proposed Reinstatement Plan within 30 Business Days after receipt of the Election to Reinstate;
        2. the Operator provides a notice to the Commonwealth of that fact which includes an express warning that if the Commonwealth does not provide any comments on the Proposed Reinstatement Plan within a further 10 Business Days after receipt of that notice, the Commonwealth will be deemed to have approved the Proposed Reinstatement Plan; and
        3. the Commonwealth does not request any changes to the Proposed Reinstatement Plan within that further 10 Business Day period,

the Commonwealth will be deemed to have approved the Proposed Reinstatement Plan at the end of that further 10 Business Day period; and

* + - 1. if the Commonwealth acting reasonably requests any changes to the Proposed Reinstatement Plan in accordance with clause 20.2(a)(i), within 20 Business Days after receipt of:
         1. the Commonwealth’s request, the Operator must provide an amended Proposed Reinstatement Plan to the Commonwealth; and
         2. the Operator’s amended Proposed Reinstatement Plan, the Commonwealth must (acting reasonably) approve or reject the amended Proposed Reinstatement Plan.
    1. Without limitation, it will be unreasonable for the Commonwealth to request changes to the Proposed Reinstatement Plan where it:
       1. is prepared in accordance with the requirements of this Agreement;
       2. identifies an express date for the completion of the reinstatement which is as soon a reasonably practicable after the Reinstatement Event occurred;
       3. demonstrates that the Operator will be able to reinstate the Project to the condition it was in immediately prior to the Reinstatement Event and applying Good Industry Practice by that date.
    2. If the Commonwealth approves a Proposed Reinstatement Plan:
       1. that Proposed Reinstatement Plan will become an **Approved Reinstatement Plan** on and from the date it is approved; and
       2. the Operator must, at its sole cost and risk, comply with that Approved Reinstatement Plan in all material respects.
  1. Consequences of failing to reinstate

If, following a Reinstatement Event:

* + 1. the Operator elects not to (or is deemed to have elected not to) reinstate the Project;
    2. the Operator does not provide an amended Proposed Reinstatement Plan in accordance with clause 20.2(a)(ii)(A);
    3. the Commonwealth rejects a Proposed Reinstatement Plan in accordance with clause 20.2(a)(ii)(B); or
    4. the Operator:
       1. fails to comply with an Approved Reinstatement Plan in any material respect; and
       2. does not cure that failure within 2 months after being notified of that failure by the Commonwealth,

the Commonwealth may terminate this Agreement by notice to the Operator, this Agreement will terminate on the date set in that notice and that termination will be deemed to be a termination pursuant to clause 22.2.

* 1. Obligation to reinstate
     1. Where the Operator elects to reinstate the Facility following a Reinstatement Event, the Operator must:
        1. ensure that the repair and/or reinstatement results in the Facility being able to achieve or exceed the Performance Requirements; and
        2. apply the proceeds of any insurance payment received in respect of any loss, damage or destruction to the Facility to the repair or reinstatement of the Facility.
     2. The Operator must comply with its obligations under this clause 20.4:
        1. promptly and diligently, without unnecessary or unreasonable delay in the relevant circumstances; and
        2. in accordance with Good Industry Practice.

1. Change in Law
   1. Change in Law
      1. The Operator must notify the Commonwealth within 10 Business Days after becoming aware of any actual or impending Change in Law.
      2. Subject to clause 21.2, at any time after the date which is 12 months after the Signing Date, if a Change in Law occurs that prevents or materially interferes with the operation of this Agreement or any of the transactions contemplated by this Agreement, the parties must:
         1. use reasonable endeavours to mitigate the effect of the Change in Law; and
         2. consider and negotiate in Good Faith any specific amendment to this Agreement (other than to any Annual Payment Cap) requested by a party so as to preserve the efficacy of the operation of this Agreement in the manner intended as at the Signing Date.
      3. Subject to the parties rights pursuant to clauses 35 and 36, if the parties are unable to agree any changes to this Agreement as contemplated under clause 21.1(b)(ii), this Agreement will continue to operate in accordance with its terms.
      4. This clause 21.1 may operate in conjunction with clause 21.3 but is intended to address amendments to this Agreement other than those relating to Relevant Cost Changes.
   2. Exclusions

The following do not constitute a Change in Law at any time after the Signing Date:

* + 1. a change to a term (including any renaming or replacement of a term) in the NER of similar meaning or effect to the relevant term. The change to the term will apply in place of the relevant term in the NER;
    2. a change to the Reserve Level Declaration Guidelines or the NER in relation to the description, categorisation or thresholds of low reserve or lack of reserve (**LOR**); and
    3. a Pandemic Change in Law.
  1. Mitigation

If the Operator incurs a Relevant Cost Change, the Operator must use its reasonable endeavours to mitigate any additional costs incurred and to maximise the extent of any reduction in costs arising from the Relevant Cost Change.

* 1. Notice
     1. If the net impact of a Relevant Cost Change on the Operator is likely to result in a:
        1. net increase in the Relevant Cost Change that exceeds the Cost Change Threshold, the Operator may;
        2. net decrease in the Relevant Cost Change that exceeds the Cost Change Threshold, the Operator must,

in each case give the Commonwealth a notice under this clause 21.4 in respect of that Relevant Cost Change. Any such notice provided pursuant to clause 21.4(a) must be provided by the Operator to the Commonwealth on or before the date on which is 20 Business Days after the date on which the Operator became aware of the relevant Change in Law.

* + 1. The net impact of a Relevant Cost Change pursuant to this clause 21.4 is to be calculated on the basis that the Operator complies with its obligations under this Agreement including under clause 21.3.
    2. A notice given by the Operator pursuant to this clause 21.4 must specify:
       1. reasonable details of the Relevant Cost Change and the circumstances that gave rise to it;
       2. its best estimate of the amount of the Relevant Cost Change (together with reasonable supporting evidence);
       3. reasonable evidence demonstrating the Operator’s steps taken to use reasonable endeavours to mitigate additional costs and maximise reductions in costs in accordance with clauses 21.1(a) and 21.3; and
       4. the increase or decrease in the Annual Payment Cap, Annual Revenue Ceiling and Annual Revenue Floor, which the Operator considers is required to pass through 50% of the Relevant Cost Change to the Commonwealth with the Cost Change Principles.
  1. Adjustment to the Annual Payment Cap, Annual Revenue Ceiling and Annual Revenue Floor
     1. If the Operator provides notice to the Commonwealth in accordance with clause 21.4, the parties will negotiate in Good Faith an adjustment to the Annual Payment Cap, Annual Revenue Ceiling and Annual Revenue Floor which the parties consider is required to pass through 50% of the Relevant Cost Change to the Commonwealth in accordance with the Cost Change Principles.
     2. If the parties fail to agree the required adjustment under clause 21.5(a) by the later of the date that is:
        1. 60 Business Days after receipt of the notice under clause 21.4; and
        2. 120 Business Days after the commencement of the relevant Change in Law,

and a party wishes to progress the resolution of that adjustment, that party must refer the Dispute to an Independent Expert for determination under clause 35.6.

* + 1. If that Dispute regarding the adjustment is referred to an Independent Expert under clause 21.5(b), that Independent Expert must base its determination on the Cost Change Principles.

1. Termination
   1. Termination for Convenience by the Commonwealth
      1. Subject to clause 22.1(b), the Commonwealth may at its absolute discretion at any time terminate this Agreement by notice in writing to the Operator.
      2. A termination of this Agreement under this clause 22.1 will take effect at the date specified by the Commonwealth in the notice given pursuant to clause 22.1(a), provided that such date is no less than 6 months after the date the notice is given.
      3. Termination under this clause 22.1 will be without Liability to either party, other than:
         1. in respect of any Liability accrued as at the date of termination; and
         2. the Commonwealth's Liability to the Operator as expressly set out in clause 23.
   2. Termination by the Commonwealth for Operator Default

The Commonwealth may terminate this Agreement with immediate effect by notice in writing to the Operator if any of the following occur:

* + 1. the Commonwealth becomes entitled to terminate this Agreement under any of clauses 3.3(g) (Draft CP Cure Plans and CP Cure Plans), 5.1(g)(v) (Achievement of Milestone Events), 5.2(g) (Draft ME Cure Plans and ME Cure Plans), 10.3(h) (Performance Requirement failures), 14.6(a) (Termination regarding SLCs), 24.4 (Non-compliance) or sections 5.4(c), 5.5(c)(iii) or 5.5(e)(iii) of Schedule 11 (Significant Events);
    2. the Operator assigns, novates, transfers or otherwise deals (or agrees to or attempts to assign, novate, transfer or otherwise deal) with the Operator’s rights or obligations under, title to or interest in any Project Document or the Project other than in accordance with the requirements of this Agreement without the Commonwealth’s written consent and the Operator fails to remedy situation within 20 Business Days after receiving notice from the Commonwealth to do so;
    3. where the Operator undergoes (or agrees to or attempts to undergo) a Change in Control other than in accordance this Agreement and the Operator fails to remedy situation within 20 Business Days after receiving notice from the Commonwealth to do so;
    4. where each of the following occur, the Operator:
       1. fails to pay any amount by the date on which that payment is due and payable to the Commonwealth under this Agreement (other than an amount which is the subject of a Dispute in Good Faith); and
       2. does not pay the relevant amount (other than an amount which is the subject of a Dispute in Good Faith) in full within 20 Business Days after receiving notice of that failure from the Commonwealth;
    5. the Operator fails to comply in any material respect with any other obligation under this Agreement (other than an obligation to pay an amount due and payable) and:
       1. the Operator does not commence remedying that failure within 20 Business Days after receiving notice of that failure from the Commonwealth (**Breach Notice**);
       2. if the Operator has commenced remedying that failure within 20 Business Days after receiving the Breach Notice, the Operator:
          1. does not pursue that remedy in a diligent manner; or
          2. does not remedy the relevant failure within 40 Business Days after receiving the Breach Notice (or by any later date determined by the Commonwealth acting reasonably); or
       3. the failure is not reasonably capable of remedy:
          1. if the Commonwealth provides the Operator with reasonable requirements to overcome the consequences of, or compensate the Commonwealth for that failure and a reasonable date by which the Operator must comply with those requirements, the Operator fails to comply with those requirements by that date; or
          2. if the Commonwealth acting reasonably determines that there are no reasonable requirements that can be met by the Operator to overcome the consequences of, or compensate the Commonwealth for, that failure, stating that to be the case along with its reasons for forming that view;
    6. an express representation made by the Operator under this Agreement (other than under clause 26.3) is incorrect or misleading in any material respect when made and the Operator does not remedy that incorrect or misleading representation within 60 Business Days after receiving notice from the Commonwealth of that incorrect or misleading representation (including by the Operator paying the Commonwealth compensation reasonably acceptable to the Commonwealth on account of loss suffered by the Commonwealth);
    7. an express representation made by the Operator under clause 26.3 is incorrect or misleading in any material respect when made and:
       1. the Commonwealth forms the view that the Commonwealth would not have awarded the Operator this Agreement but for the materials and information which caused or contributed to that representation being materially incorrect or misleading;
       2. the Commonwealth notifies the Operator of that incorrect or misleading representation in writing no later than 2 years after the Commercial Operation Date; and
       3. the Operator does not remedy that incorrect or misleading representation within 60 Business Days after receiving notice from the Commonwealth of that incorrect or misleading representation (including by the Operator paying the Commonwealth compensation reasonably acceptable to the Commonwealth on account of loss suffered by it);
    8. the Operator:
       1. fraudulently, recklessly or knowingly provides a report or other information required under clauses 14, 32.1, 32.2, 32.3, 32.4, 32.6, 32.7 or 32.8 (**Reports**) that is incorrect or misleading in any material respect; and
       2. does not, within 60 Business Days after receiving notice from the Commonwealth of that incorrect or misleading representation:
          1. pay the Commonwealth compensation reasonably acceptable to the Commonwealth on account of loss suffered by it;
          2. ensure that the persons involved in preparing and/or providing the reports and/or information which gave rise to the incorrect or misleading representation will have no future involvement in respect of the Project or this Agreement;
          3. procure that an auditing firm approved by the Commonwealth conducts an audit of all previous Reports and provides the Commonwealth the results of such audit (in each case at the cost of the Operator); and
          4. undertake to procure that an appropriately qualified independent auditing firm nominated by the Operator and approved by the Commonwealth (acting reasonably) and which has no actual or perceived conflict of interest conducts an annual audit of all Reports provided to the Commonwealth in respect of each future Operations Year and provide the Commonwealth the results of such audits within 40 Business Days after the end of that Operations Year;
    9. the Operator is the subject of an Insolvency Event or the Operator wholly or substantially abandons all or any material (in scope or effect) part of the Facility and the Operator does not cure that Insolvency Event or abandonment within 10 Business Days after receiving notice from the Commonwealth to do so;
    10. the Commonwealth becomes entitled to terminate this Agreement in accordance with clause 19.9 (Termination for extended Force Majeure Event); and
    11. the Commonwealth becomes entitled to terminate this Agreement in accordance with clause 20.3 (Consequences of failure to reinstate).

For the avoidance of doubt, this Agreement is also deemed to be terminated pursuant to this clause 22.2 on the terms set out in clauses 3.4 and 5.3 and section 5.1(d)(ii) of Schedule 4.

* 1. Termination by the Operator for Commonwealth Default

The Operator may terminate this Agreement with immediate effect by notice in writing to the Commonwealth if any of the following occur:

* + 1. the Commonwealth assigns, novates, transfers or otherwise deals with the Commonwealth’s rights or obligations under, title to or interest in any Project Document other than in accordance with the requirements of this Agreement without the Operator’s written consent (such consent not to be unreasonably withheld or delayed) and the Commonwealth fails to remedy situation within 60 Business Days after receiving notice from the Operator to do so; and
    2. where each of the following occur, the Commonwealth:
       1. fails to pay any amount by the date on which that payment is due and payable to the Operator under this Agreement (other than an amount which is the subject of a Dispute in Good Faith); and
       2. does not pay the relevant amount (other than an amount which is the subject of a Dispute in Good Faith) in full within 60 Business Days after receiving notice of that failure from the Operator.
  1. Preservation of rights

Termination or expiry of this Agreement for any reason will not extinguish or otherwise affect any rights of either party against the other party that:

* + 1. accrued before the time of such termination or expiry; or
    2. otherwise relates to or may arise at any future time from any breach or non-observance of obligations under this Agreement that arose prior to the date of such termination or expiry.
  1. Sole basis of termination
     1. Clauses 22.1, 22.2 and 22.3 set out the sole bases at Law or otherwise upon which the Commonwealth or the Operator is entitled to terminate, rescind or accept a repudiation of this Agreement.
     2. Each party acknowledges and agrees that, it has no right to, and will not, terminate this Agreement notwithstanding any other provision of this Agreement or any rights which that party would have at Law or otherwise (including for repudiation) but for this clause 22.5(b).

1. Payments on Termination
   1. Fixed Termination Payment and Early Termination Payment
      1. If this Agreement is terminated by the Commonwealth in accordance with clause 22.1 or the Operator in accordance with clause 22.3, the Commonwealth must pay the Fixed Termination Payment to the Operator.
      2. If this Agreement is terminated by the Commonwealth in accordance with any of clause 22.2 (other than clauses 22.2(k) and 22.2(j)), pursuant to clause 3.4 or 5.3 or pursuant to section 5.1(d)(ii) of Schedule 4, the Operator must pay the Early Termination Payment to the Commonwealth.
      3. If this Agreement is terminated by the Commonwealth in accordance with clause 22.2(k):
         1. subject to clause 23.1(c)(ii), no Termination Payment is payable under this Agreement; or
         2. if:
            1. the relevant Reinstatement Event did not arise as a result of a Project Force Majeure Event; or
            2. the Operator or a Related Body Corporate of the Operator subsequently reinstates the Project (or a project which is similar to the Project) within 5 years after the Reinstatement Event occurred,

then the Operator must pay the Early Termination Payment to the Commonwealth.

* + 1. If this Agreement is terminated by the Commonwealth in accordance with clause 22.2(j), no Termination Payment is payable under this Agreement.
    2. Notwithstanding anything to the contrary under this clause 23.1, each party is entitled to recover from the other party amounts related to rights which accrued before the time of such termination or expiry of this Agreement or which otherwise relate to or may arise at any future time from any breach or non-observance of obligations under this Agreement that arose prior to the date of such termination or expiry.
  1. Sole remedy

Subject to clauses 22.3 and 23.3, the parties acknowledge and agree that:

* + 1. the Operator's sole financial remedy arising out of in connection with a termination under clause 22.1 is the Operator's right to be paid the Fixed Termination Payment by the Commonwealth in accordance with clause 23.1(a);
    2. the Fixed Termination Payment is a genuine pre-estimate of the Operator's anticipated liabilities and Losses arising from the termination of this Agreement under clause 22.1;
    3. the Commonwealth's sole financial remedy arising out of or in connection with a termination under clause 22.2 (other than clause 22.2(j) and where clause 23.1(c)(ii) applies other than clause 22.2(k)), pursuant to clause 3.4 or 5.3 or pursuant to section 5.1(d)(ii) of Schedule 4 is the Commonwealth's right to be paid the Early Termination Payment by the Operator in accordance with clause 23.1; and
    4. the Early Termination Payment is a genuine pre-estimate of the Commonwealth's anticipated liabilities under clause 22.2 (other than clause 22.2(j) and where clause 23.1(c)(ii) applies other than clause 22.2(k)) and Losses arising from the termination of this Agreement.
  1. Unenforceability
     1. If:
        1. any Termination Payment becomes payable by a party under the terms of this Agreement; and
        2. that Termination Payment is found to be a penalty or that party obligation to pay the Termination Payment pursuant to clause 23.1 is found to be void or unenforceable for any reason (whether in whole or in part),

that party indemnifies the other party against, and agrees to reimburse and compensate it for, any liability or Loss (including in respect of loss of bargain) suffered by the other party arising from or in connection with the termination of this Agreement, provided that the first party's aggregate Liability pursuant to this clause 23.3 will not exceed an amount equal to the relevant Termination Payment.

* 1. Invoice
     1. The party entitled to be paid a Termination Payment must provide an invoice to the other party for the Termination Payment within 60 Business Days after termination of this Agreement provided however where the party which has the obligation to pay the Termination Payment is the Commonwealth, the Commonwealth will not be obliged to provide that invoice until the later of that 60 Business Day period and 40 Business Days after the date on which the Commonwealth has received information requested from the Operator requested pursuant to section 2 of Schedule 5.
     2. The party required to pay a Termination Payment must pay the amount of any such Termination Payment within 30 Business Days after receipt of an invoice provided under clause 23.4(a).

1. Assignment and Change in Control
   1. Assignment or Novation By Operator
      1. The Operator must not assign, novate, transfer or otherwise deal with the Operator’s rights or obligations under, title to or interest in any Project Document or the Project without the Commonwealth’s written consent.
      2. Prior to the Commencement Date, the Commonwealth may provide or withhold its consent under clause 24.1(a) at its absolute discretion.
      3. On and from the Commencement Date, the Commonwealth must not unreasonably withhold or delay its consent under clause 24.1(a) where:
         1. the proposed assignee, novatee or transferee has the legal, commercial, financial and technical capability to comply with the Operator's obligations under the Project Documents;
         2. the proposed assignee, novatee or transferee is solvent and reputable, does not have an interest which conflicts in a material way with the interests of the Commonwealth and there is no prohibition or restriction imposed by Law which would prevent or impact its ability to assume the rights and/or obligations of the assignor, novator or transferor;
         3. the proposed assignment, novation or transfer is not against the national interests, would not have a material adverse effect on the Project nor would increase the Liability of, or risks accepted by the Commonwealth under any Project Documents or in any other way in connection with the Project; and
         4. the proposed assignee, novatee or transferee agrees to assume all obligations of the Operator arising from or in connection with the Project Documents:
            1. including those which arise prior to and after the novation, transfer or dealing on terms reasonably acceptable to the Commonwealth; or
            2. which arise after the novation, transfer or dealing and the outgoing Operator continues to remain responsible for those obligations of the outgoing Operator which arose prior to the novation, transfer or dealing, in each case on terms reasonably acceptable to the Commonwealth.
      4. The Operator must not assign, novate, transfer or otherwise deal with its rights or obligations under, title to or interest in this Agreement or the Project unless it also assigns, novates or otherwise transfers:
         1. its rights and obligations under, title to or interest in and its obligations under each other Project Document; and
         2. the Project and the Transaction Documents to which it is a party,

to the same person.

* + 1. If the Operator assigns, novates, transfers or otherwise deals with any of its rights, title or interests in any Operational Revenue, for the purpose of determining the Operational Revenue in a relevant Quarter and/or Support Year pursuant to this Agreement, the amount which the Operator receives in exchange for that assignment, novation, transfer or dealing will be ignored and the Operator will be deemed to have received that Operational Revenue in the relevant Quarter and Support Year that it would have been received but for that assignment, novation, transfer or dealing.
  1. Security Interest
     1. Notwithstanding anything else in clause 24.1, the parties agree that the Operator may grant a Security Interest in respect of its rights and obligations under this Agreement or the Project in favour of a secured lender (or a trustee acting on its behalf) who is providing financial accommodation on secured terms to the Operator (or to any of its Related Bodies Corporate) in connection with the Project.
     2. The parties acknowledge and agree that the provisions of clause 24.1 and any Tripartite Deed signed by the parties (amongst others) will apply to any assignment, novation, transfer of or dealing with the Operator’s rights and/or obligations under, title to and interest in this Agreement following the enforcement of a Security Interest granted by the Operator in accordance with clause 24.2(a).
  2. Assignment or Novation by Commonwealth
     1. The Commonwealth may assign, novate, transfer or otherwise deal with the Commonwealth’s rights or obligations under, title to or interest in any Project Document and the Operator’s consent is hereby given to that assignment, novation, transfer or dealing where:
        1. the Commonwealth assigns, novates or transfers to or enters into a dealing with a Government Agency (including the Clean Energy Finance Corporation and the Australian Renewable Energy Agency) but only to the extent which that Government Agency has been guaranteed by the Commonwealth; and
        2. the Commonwealth notifies the Operator no later than 20 Business Days after the relevant assignment, novation, transfer or dealing and that notice identifies that assignee, novatee, transferee or Government Agency and the terms and conditions of that assignment, novation, transfer or dealing.
     2. The Commonwealth must not otherwise assign, novate, transfer or otherwise deal with the Commonwealth’s rights or obligations under, title to or interest in any Project Document without the Operator’s prior written consent (such consent not to be unreasonably withheld or delayed).
  3. Non-compliance
     1. Any purported assignment, novation, transfer or dealing that is not in compliance with clauses 24.1 to 24.3 will not be effective as between the parties to this Agreement.
     2. Without limiting clause 24.4(a), if the Operator does not comply with any of clauses 24.1 to 24.3, the Commonwealth may terminate this Agreement by giving notice to the Operator, this Agreement will terminate on the date set in that notice and that termination will be deemed to be a termination pursuant to clause 22.2.
  4. Change in Control
     1. The Operator must not undergo, or agree to undergo, a Change in Control without the Commonwealth’s prior written consent.
     2. The Commonwealth must not unreasonably withhold or delay its consent under clause 24.5(a) where:
        1. the Operator’s legal, commercial, technical, managerial and financial capability to enable it to perform its obligations under this Agreement will not be adversely affected by the proposed Change in Control;
        2. in the case of Change in Control that would occur prior to the Commercial Operation Date, the Commonwealth considers (in its absolute discretion) that its assessment of the Operator or the Project during the Tender would not have been adversely affected in any way had the Change in Control occurred prior to the conclusion of the Tender;
        3. the proposed Controller is solvent and reputable and does not have any an interest which conflicts in a material way with the interests of the Commonwealth and there is no prohibition or restriction imposed by Law which would prevent or impact its ability to take Control of the Operator; or
        4. the proposed Change in Control of the Operator is not against the national interest, would not have a material adverse effect on the Project nor would increase the Liability of, or risks accepted by the Commonwealth under any Project Documents or in any other way in connection with the Project.
     3. The Operator must promptly provide such further information as the Commonwealth reasonably requires in order to determine whether to grant consent to a proposed Change in Control of the Operator pursuant to this clause 24.5.

1. Risk and Liability
   1. Indemnity
      1. Subject to clauses 25.2(a) to 25.2(c), the Operator indemnifies (and must keep indemnified) the Commonwealth and the Commonwealth's Associates (referred to in this clause 25.1 as **'those indemnified'**) from and against all Losses sustained or incurred by those indemnified and arising out of or as a consequence of:
         1. any:
            1. loss, damage or destruction to, or loss of use of, property including any real or personal property belonging to the Commonwealth, a Commonwealth Associate or a third party; or
            2. injury to, illness or death of, any person,

in each case which occurs or arises from or in connection with any breach by the Operator of any Project Document or any negligent, reckless, criminal or fraudulent act or omissions, wilful breach or wilful misconduct of the Operator or any Operator Party in connection with this Agreement or the Project; or

* + - 1. a negligent, reckless, criminal or fraudulent act or omission, wilful breach, wilful misconduct or unlawful act or omission, in each case of the Operator or an Operator Party in connection with this Agreement or the Project.
    1. The Operator's liability to indemnify those indemnified under this clause 25.1 and under clause 28.5 will be reduced proportionally to the extent that any negligent, reckless, wilful or unlawful act or omission or breach of this Agreement on the part of those indemnified directly caused or contributed to the relevant Loss and to the extent that those indemnified fail to take reasonable steps to mitigate any Loss any of them sustain as a result of the matters which are the subject matter of those indemnities.
    2. The right of those indemnified to be indemnified under this clause 25.1 and under clause 28.5 is in addition to, and not exclusive of, any other right, power, or remedy provided by Law, but those indemnified are not entitled to be compensated in excess of the amount of the relevant Loss.
  1. Consequential Loss and Limitation of liability
     1. Neither party is liable to the other party under this Agreement, at Law or otherwise for any:
        1. indirect or consequential loss or damage of any kind including indirect and consequential financial or economic loss;
        2. loss of profit, loss of revenue, loss of use, loss of production or loss of goodwill or loss of property; or
        3. business interruption,

in each case suffered by the other party however arising due to any causes including the default or sole or concurrent negligence of a party, or its Associates, and whether or not foreseeable at the Signing Date.

* + 1. Subject to clauses 25.2(a) and 25.2(c) to the extent permitted by Law:
       1. the Commonwealth's Liability arising from or in connection with this Agreement is limited to:
          1. $1 million (Indexed) in respect of any single event; and
          2. $2 million (Indexed) in aggregate in respect of all events occurring within any Financial Year; and
       2. the Operator's Liability arising from or in connection with this Agreement is limited to:
          1. $5 million (Indexed) in respect of any single event; and
          2. $10 million (Indexed) in aggregate in respect of all events occurring within any Financial Year.
    2. Nothing in clauses 25.2(a) or 25.2(b) limits or otherwise affects any of the following:
       1. any party's obligation to make payments of any Quarterly Payment, Annual Reconciliation Payment, any Termination Payment, Taxes (including GST) and/or any payment pursuant to any of clause 16.4 and 31.4(k);
       2. the right of the Commonwealth to make deductions from any payment to be made to the Operator as expressly permitted under this Agreement including the Availability Rebate and the Storage Capacity Rebate;
       3. the Operator's Liability arising:
          1. from loss, damage or destruction to, or loss of use of, property or injury to, illness or death of any person in connection with this Agreement or the Project including under any indemnity identified in clause 25.1(a); or
          2. under clause 28.5;
       4. any party's liability arising from reckless, criminal or fraudulent acts or omissions, wilful breach, wilful misconduct or unlawful act or omission in connection with this Agreement or the Project;
       5. Liability arising out of the Operator wholly or substantially abandoning all or any material (in scope or effect) part of the Facility;
       6. the Operator's liability to the extent that insurance proceeds:
          1. are payable to the Operator in respect of the event or circumstance giving rise to the liability; or
          2. would have been payable to the Operator in respect of the event or circumstance giving rise to the liability had the Operator complied with its obligations under this Agreement in relation to insurance and the relevant insurance policy itself.
    3. Except as expressly provided in this Agreement to the contrary, it is the responsibility of the Operator to perform its obligations under this Agreement and to carry out the Project at its own cost and risk.
  1. Benefits held on trust
     1. The Commonwealth holds on trust for each Commonwealth Associate the benefit of:
        1. each indemnity, release, limitation of Liability and exclusion of Liability given by the Operator pursuant to this Agreement in favour of the relevant Commonwealth Associate; and
        2. each right in this Agreement to the extent that such right is expressly stated to be for the benefit of the Commonwealth or any Commonwealth Associate.
     2. The Operator acknowledges the existence of such trusts and consents to the Commonwealth exercising rights in relation to, or otherwise enforcing such indemnities, releases, limitations, exclusions and rights on behalf of the Commonwealth Associates.
     3. The parties agree that the Commonwealth does not require the consent of any Commonwealth Associate to amend or waive any provision of any Project Document.

1. Representations and Warranties by the Operator
   1. General warranties

Each party warrants and represents to the other party for the benefit of the other party that:

* + 1. in the case of the Operator only, it is duly registered and validly existing under the laws of its place of incorporation and has power and authority to own its assets and carry on its business as it is now being conducted;
    2. it has the full power and authority to enter into, deliver and perform its obligations under the Project Documents and carry out the transactions contemplated by the Project Documents;
    3. it has taken all necessary action to authorise the entry into, delivery of and performance of its obligations under the Project Documents; and
    4. this Agreement constitutes a legal, valid and binding obligation on it enforceable in accordance with its terms.
  1. Operator warranties

The Operator warrants and represents to the Commonwealth for the benefit of the Commonwealth that:

* + 1. it, its directors and/or its Related Body Corporates are not engaged in any Claim or are aware of any pending or threatened Claim of which written or verbal communication has been given or received and there are no facts, matters, circumstances or events which are reasonably likely to give rise to any such Claims by any third party against it, its directors and/or its Related Body Corporates in each case which would have a material adverse effect on the subject matter of any Project Document;
    2. the execution, delivery and performance of its obligations under each Project Document to which it is a party does not and will not violate:
       1. any Law, or any document or agreement to which it is a party or which is binding on it or any of its assets;
       2. any authorisation, ruling, judgment, order or decree of any Government Agency; or
       3. its constitutional documents;
    3. it holds and will continue to hold all Authorisations that it is required by Law to hold in order to lawfully execute, deliver and perform its obligations under the Project Documents;
    4. unless otherwise expressly provided or permitted in this Agreement, it is not the trustee or Responsible Entity of any trust nor does it hold any property subject to or impressed by any trust;
    5. all information that has been provided to the Commonwealth by the Operator is true and correct at the time it was provided to the Commonwealth;
    6. it is not aware of any material facts or circumstances that have not been disclosed to the Commonwealth as at the Signing Date:
       1. that may have an adverse effect on the Operator's ability to meet its obligations under any Project Document; or
       2. which, had they been disclosed, may have made a prudent person in the Commonwealth's position, considering whether or not to enter into any Project Document, determine not to do so;
    7. it is not subject to an Insolvency Event;
    8. neither it nor any of its Related Bodies Corporate, or any of their respective Associates, have engaged in any activity or conduct in connection with the Project which would violate any applicable anti-bribery, anticorruption or anti-money laundering and counter-terrorism finance laws, regulations or rules in any applicable jurisdiction;
    9. it has not entered into any Offtake Contract or other arrangement which would have been a breach of clause 9.5 if it had entered into that arrangement during the Term;
    10. it has no subsidiaries;
    11. none of its assets are subject to any Security Interest other than a Permitted Security Interest;
    12. it is not a partner in a partnership, it is not a party to an unincorporated joint venture and it is not a participant in or a member of an association or other incorporated body;
    13. to the extent required by Law, it holds (or is exempt from the requirement to hold) an Australian financial services licence under Division 2 of Part 7.6 of the Corporations Act; and
    14. it is a "wholesale client" within the meaning of section 761G of the Corporations Act.
  1. Tender matters

The Operator represents and warrants that:

* + 1. each statement, representation, declaration, material and all information provided by the Operator to the Commonwealth as part of or in connection with the Tender Submission (other than forecasts or projections) was true, correct and not misleading in any material respect (whether by omission or otherwise) as at the Tender Date; and
    2. all forecasts and projections which were provided by or on behalf of the Operator to the Commonwealth as part of or in connection with the Tender Submission were prepared using due care and skill based on assumptions which the Operator or its Related Bodies Corporate believed, in Good Faith, were fair and reasonable assumptions as at the Tender Date.
  1. Repetition

Unless expressly stated otherwise, each representation and warranty given by the Operator (other than clauses 26.2(a), 26.2(f) and 26.3) is deemed to be given on the Signing Date and repeated on each day thereafter throughout the Term with references to the facts and circumstances then subsisting.

* 1. Trustee representations and warranties

**[Drafting note: clause to be included in this Agreement where the Operator enters into the Agreement in its capacity as trustee for a trust**]

[The Operator represents and warrants to the Commonwealth that:

* + 1. the Trust has been duly established and constituted;
    2. it is the sole trustee of the Trust;
    3. it has been validly appointed as trustee of the Trust and no action has been taken or proposed to remove it as trustee of the Trust;
    4. it has power under the terms of the Trust to enter into the Project Documents and comply with its obligations under it and them;
    5. it has in full force and effect the authorisations necessary for it to enter into each Project Document, perform obligations under it or them and allow it or them to be enforced (including any authorisation required under the Trust Deed and its constitution (if any));
    6. it has a right to be fully indemnified out of the Trust Property in respect of obligations incurred by it under this Agreement and there are no facts, matters or circumstances that would disentitle the Operator from being so indemnified;
    7. it is not, and never has been, in default under the Trust Deed;
    8. no action has been taken or proposed to terminate the Trust;
    9. it and its directors and other officers have complied with their obligations in connection with the Trust;
    10. it has not exercised its powers under the Trust Deed to release, abandon or restrict any power conferred on it by the Trust Deed; and
    11. no action has been taken, proposed or contemplated to remove the Operator as trustee of the Trust or to appoint a new trustee of the Trust in place of, or in addition to, the Operator; and
    12. entry into the documents to which it is a party is a valid exercise of its powers under the Trust Deed for the benefit of the Trust’s beneficiaries.
  1. Trustee undertakings

The Operator, in its personal capacity and as trustee of the Trust, undertakes to the Commonwealth during the term that the Operator will:

* + 1. do everything necessary to comply with its obligations under the Trust Deed and in performing its obligations under each Project Document;
    2. not do anything which might limit its right as trustee to be indemnified out of the assets of the Trust for any Liabilities it may incur arising from or in connection with each Project Document; and
    3. not otherwise do anything to compromise its ability to comply with its obligations in connection with each Project Document.
  1. Restrictions on the Trustee

Without the consent of the Commonwealth, the Operator may not, and may not agree, attempt or take any step to, do anything which:

* + 1. effects or facilitates the retirement, removal or replacement of the Operator as trustee of the Trust;
    2. may restrict the Operator’s right of indemnity from the Trust Property in respect of obligations incurred by the Operator under any Project Document;
    3. may restrict or impair the ability of the Operator to comply with its obligations under any Project Document;
    4. effects or facilitates the termination of the Trust;
    5. effects or facilitates the variation of the Trust Deed; or
    6. effects or facilitates the resettlement of the Trust Property.
  1. Trustee limitation of liability
     1. This clause 26.8 applies to the Operator as trustee of the Trust to the extent that the Operator is acting in that capacity.
     2. Subject to clause 26.8(c) to 26.8(e), the Operator’s Liability to any person in connection with this Agreement (or any transaction in connection with it) is limited to the extent to which the Liability is or can be satisfied out of the Trust Property by the Operator exercising its right of indemnity out of the Trust Property.
     3. Subject to clauses 26.8(c)(i) and 26.8(c)(ii), the Commonwealth may not seek to recover any amounts owing to it under this Agreement by bringing proceedings against the Operator in its personal capacity. However, the Commonwealth may:
        1. do anything necessary to enforce its rights in connection with the Trust Property; and
        2. take proceedings to obtain either or both:
           1. an injunction or other order to restrain any breach of this Agreement by the Operator; and
           2. declaratory relief or other similar judgment or order as to the obligations of the Operator under this Agreement.
     4. The limitations and restrictions under clauses 26.8(b) and 26.8(c) do not apply to a Liability to the extent that it is not satisfied because there is a reduction in the extent of the Operator’s indemnification out of the Trust Property either as a result of the Operator’s fraud, negligence or wilful default, or by operation of Law.
     5. The limitation of the Operator’s Liability under clause 26.8(b) is to be disregarded for the purposes of determining whether the Operator has failed to comply with or perform any obligation under this Agreement because of a failure by the Operator to pay an amount payable by it under this Agreement.]
  2. No reliance

Each party acknowledges that it has not relied on any representation or warranty (whether express or implied) about the subject matter of this Agreement other than those expressly set out in this Agreement.

1. Performance Security
   * 1. The Operator must procure and provide to the Commonwealth a performance bond or bank guarantee which has a face value at least equal to the Security Amount and which:
        1. is unconditional, irrevocable and payable on demand;
        2. is issued by a Authorised Bank;
        3. specifies a location in Melbourne or Sydney, Australia (or such other place as the Commonwealth may approve) where demand can be given and payment made, without further confirmation from the issuer on any Business Day;
        4. names the Commonwealth as the beneficiary; and
        5. is in the relevant form set out in Schedule 10 or such other form approved by the Commonwealth (such approval not to be unreasonably withheld where the amendments proposed by the Operator have no material effect on the Commonwealth),

which for the purpose of this Agreement is known as the performance security (**Performance Security**).

* + 1. The Performance Security must:
       1. be provided to the Commonwealth within 20 Business Days after the Signing Date or by such later date as otherwise agreed between the parties; and
       2. remain valid from and including the date on which it is provided to the Commonwealth until and including the date which is the earlier of:
          1. 20 Business Days after the COD; and
          2. if this Agreement is terminated prior to COD, 40 Business Days after the date on which all amounts payable under clause 23 in connection with that termination have been paid,

(**Validity Period**). To the extent it has not already done so, the Commonwealth must return the Performance Security to the Operator within 10 Business Days after the end of the Validity Period if so requested by the Operator.

* + 1. If the Performance Security provided by the Operator to the Commonwealth is due to expire in accordance with its terms prior to the last day of the period identified in clause 27(b)(ii), the Operator must procure and provide to the Commonwealth a replacement Performance Security. That replacement Performance Security must be of equal face value and must otherwise comply with all the requirements of this Agreement in respect of the Performance Security and must be provided to the Commonwealth on or before the date which is 20 Business Days prior to the date on which the Performance Security is due to expire.
    2. If the issuer of a Performance Security ceases to have a Required Rating, the Operator must procure and provide to the Commonwealth a replacement Performance Security of equal face value and otherwise complying with all the requirements of this Agreement in respect of the Performance Security on or before the date which is 20 Business Days after that issuer ceases to have a Required Rating. The Commonwealth will return the Performance Security issued by a bank or financial institution which no longer holds the Required Rating promptly after the Operator provides that replacement Performance Security to the Commonwealth.
    3. Without prejudice to the unconditional, irrevocable and on demand nature of the Performance Security, if:
       1. the Commonwealth believes that an amount is due and payable by the Operator to the Commonwealth arising from or in connection with this Agreement and that amount has not been paid; or
       2. the Operator fails to provide an replacement Performance Security pursuant to clause 27(c) or 27(d) (as applicable) within the relevant period identified in clause 27(c) or 27(d) (as applicable),

the Commonwealth may call upon, draw on or have recourse to the Performance Security. The Commonwealth must apply the proceeds of the drawing to pay any amount that it believes is due and payable by the Operator to the Commonwealth arising from or in connection with this Agreement or hold such proceeds and apply them to pay any amount which the Commonwealth believes subsequently becomes due and payable to the Commonwealth arising from or in connection with this Agreement.

* + 1. Notwithstanding anything to the contrary in this Agreement, if the Operator fails to comply with its obligations under this Agreement to provide any Performance Security in connection with this Agreement, the Operator must not issue any further Payment Notices , issue any further invoices (including tax invoices) nor make any further Claims under this Agreement and the Operator is not entitled to any payment under this Agreement until the Operator has provided that Performance Security to the Commonwealth.
    2. The Commonwealth may direct the Operator to provide the Performance Security to be held by a nominee selected by the Commonwealth rather than to the Commonwealth. If the Commonwealth does so:
       1. the Operator must comply with that direction;
       2. provision of the Performance Security by the Operator to the nominee will be deemed for the purposes of this clause 27 to constitute provision of the Performance Security to the Commonwealth;
       3. return of the Performance Security by the nominee to the Operator will be deemed for the purposes of this clause 27 to constitute return of the Performance Security by the Commonwealth; and
       4. for the avoidance of doubt, the Performance Security must name the "Commonwealth of Australia" as the beneficiary of the Performance Security (not the Commonwealth's nominee).

1. Intellectual Property
   1. Project Intellectual Property

As between the Operator and the Commonwealth, all Project Intellectual Property vests in the Operator upon creation.

* 1. Licence of Specified Material
     1. Subject to clause 28.2(b), the Operator grants to the Commonwealth a permanent, irrevocable, royalty‑free, world‑wide, non‑exclusive, transferrable licence (including a right to sub‑license) to use, copy and otherwise do any acts in relation to Specified Material for non‑commercial purposes and for purposes only connected to this Agreement and the Commonwealth's Capacity Investment Scheme including the future design of that scheme.
     2. If, despite using reasonable endeavours to do so, the Operator is unable to license (or, if applicable, procure a licence of) any Specified Material owned by a person (other than the Commonwealth, the Operator or any Related Body Corporate of the Operator (**Third Party**)) to the Commonwealth, as required under clause 28.2(a), the Operator must consult with the Commonwealth and do all things reasonably necessary to obtain for the Commonwealth's benefit such Third Party Intellectual Property Rights which the Operator is obliged to grant under clause 28.2(a) and which has not been granted or licensed to the Commonwealth provided that if the Third Party does not offer the licence on the applicable terms, as required under clause 28.2(a), the Operator must negotiate, subject to the Commonwealth's approval, the best available commercial terms from the Third Party and will offer those terms to the Commonwealth for its acceptance or rejection.
  2. Moral rights

If any Specified Material that is a copyright work contains information over which a third party (including the Operator's Associates) has 'Moral Rights' (as defined in the *Copyright* *Act 1968* (Cth)), the Operator must ensure that it has in place all necessary consents sufficient to allow the Commonwealth to deal with the Specified Material in accordance with any Project Document.

* 1. Warranties

The Operator warrants that:

* + 1. it is entitled to use for the Project and for the purposes of meeting its obligations under any Project Document:
       1. all Background Intellectual Property and Project Intellectual Property and
       2. all Specified Material,

(together, **Warranted Materials**); and

* + 1. it has the right to grant the licence in clause 28.2.
  1. Intellectual Property Indemnity
     1. The Operator indemnifies (and must keep indemnified) the Commonwealth, the Commonwealth's Associates (and its licensees or sub-licensees of any Intellectual Property Rights) (**Indemnified Party**) against any Liability, licence fee or royalty sustained or incurred by an Indemnified Party regarding:
        1. any Intellectual Property Rights which arises out of any Claim brought by any third party in respect of any infringement or alleged infringement of that third party's Intellectual Property Rights, Moral Rights (as defined in the *Copyright Act 1968* (Cth)) or any other rights when the infringement or alleged infringement arises out of any activity permitted under any licence or sublicence referred to in this clause 28 or otherwise under this Agreement; or
        2. any breach of clause 28.4.
     2. For the purposes of this clause 28.5, “infringement” includes unauthorised acts which would, but for the operation of section 163 of the *Patents Act 1990*, section 100 of the *Designs Act 2003*, section 183 of the *Copyright Act 1968*, and section 25 of the *Circuit Layouts Act 1989*, constitute an infringement.
  2. Remedy for breach of warranty

If the Operator breaches this clause 28, and as a result of that breach, a third party claims the Commonwealth's use of all or part of the Warranted Materials infringes its Intellectual Property rights, the Operator must, in addition to any other rights that the Commonwealth may have against the Operator, promptly, at the Operator's expense:

* + 1. use its best efforts to secure the rights for the Commonwealth to continue to use the affected Warranted Materials as permitted under clause 28.2 free of any Claim or Liability for infringement; or
    2. replace or modify the affected Warranted Materials so that the Commonwealth's use of them as permitted under this clause 28 does not infringe the Intellectual Property rights of any other person without any degradation of the performance or quality of the affected Warranted Materials.

1. Subcontracting
   1. Operator remains responsible

The Operator:

* + 1. is responsible to the Commonwealth for the management, coordination and supervision of all Subcontractors and for the acts, omissions, negligence and recklessness of its Associates (whether employed or engaged directly or indirectly by the Operator) in each case in connection with this Agreement and/or this Project as if they were the acts, omissions, negligence and recklessness of the Operator;
    2. remains fully responsible for the performance of all of its obligations under this Agreement which it has subcontracted to a Subcontractor and for all costs incurred with respect to its Subcontractors;
    3. must ensure that its Subcontractors comply with the Operator's obligations under this Agreement when carrying out any work or activities under a Subcontract; and
    4. agrees that a Subcontractor's failure to perform does not constitute a Force Majeure Event, except to the extent that the Subcontractor's failure to perform is caused or contributed to by a Force Majeure Event.
  1. Key Subcontractors
     1. Subject to clauses 29.2(b) and 29.2(c), the Operator must not (and must procure that its direct and indirect Subcontractors do not) enter into a Key Subcontract to perform any of its obligations under any Transaction Document without the prior written consent of the Commonwealth. The Commonwealth must consent or refuse that consent within 20 Business Days after receipt of such a request. If the Commonwealth fails to consent or refuse that consent within that 20 Business Day period, the Operator must issue a notice to the Commonwealth warning it that if the Commonwealth fails to consent or refuse that consent within a further 20 Business Days after receipt of that warning, the Commonwealth will be deemed to have consented to the Operator entering into that Key Subcontractor. If the Commonwealth then fails to consent or refuse that consent within that further 20 Business Day period, the Commonwealth will be deemed to have consented to the Operator entering into that Key Subcontractor. **[Drafting note: the requirements regarding Key Subcontractors are intended to reflect the fact that prospective Operators will be evaluated during the tender phase in part on their technical solution and proposed Key Subcontractors to the extent they are known. The Commonwealth therefore wishes to ensure that an Operator utilises the relevant Key Subcontractors and technologies referred to their Bid (to the extent that Key Subcontractors are known and form part of the evaluation of the relevant Bid of a Proponent). If changes to the proposed Key Subcontractors are warranted, the Operator may follow the process set out in this clause 29.2. If the identities of any Key Subcontractors are not known as at the Signing Date, the Commonwealth is open to preapproving a limited number of potential Key Subcontractors from which the Operator may seek proposals to perform the relevant Key Subcontract.]**
     2. The Operator is not required to seek prior written approval from the Commonwealth for any Key Subcontractor identified in Schedule 7 provided that the applicable Key Subcontractor is to be engaged to provide or perform or deliver the goods, services and parts of the work comprising or in relation to the Facility which they are approved to provide and perform as set out in Schedule 7.
     3. The Commonwealth may only refuse approval for a Key Subcontractor not identified in Schedule 7 where that proposed Key Subcontractor:
        1. does not have the legal, commercial, technical, managerial and financial capability to enable it to perform or deliver the relevant goods, services or parts of the works which it is being engaged to provide; or
        2. is insolvent or not reputable or has an interest which conflicts in a material way with the interests of the Commonwealth and there is no prohibition or restriction imposed by Law which would prevent or impact its ability to perform or deliver the relevant goods, services or parts of the works which it is being engaged to provide.
     4. The Operator is not discharged from any obligation or Liability under this Agreement by entering into any Subcontract.

1. Confidentiality
   1. Confidential Information not to be Disclosed
      1. Subject to clause 30.2, a party must not (and must procure its Associates not to) directly or indirectly disclose or make available any Confidential Information of the other party to a third party which would compromise the confidentiality of such Confidential Information, without the prior consent of the other party.
      2. In giving written consent to the disclosure of its Confidential Information, a party may impose such conditions as it thinks fit, and the other party agrees to comply with these conditions.
   2. Exception to obligations of Confidentiality

A party may disclose Confidential Information of the other party to the extent that the Confidential Information is:

* + 1. disclosed to any person in connection with an exercise of rights or a dealing, or proposed dealing, with rights or obligations in connection with any Project Document or other Transaction Document but only to the extent that such a person has a need to know and agrees with the disclosing party to act consistently with this clause;
    2. disclosed to its Associates solely in order to comply with the obligations or to exercise rights in relation to the Project Documents or other Transaction Documents or to a Related Body Corporate for internal management purposes, in each but only to the extent that such a person has a need to know and (other than disclosure to any Commonwealth officer, employees and servants who are already subject to confidentiality obligations) agrees with the disclosing party to act consistently with this clause;
    3. to the extent required or authorised by Law, in connection with any legal or recognised dispute resolution process to which the relevant party is a party or authorised or required by the rules of any recognised stock exchange on which that party's shares are listed;
    4. disclosed by the Commonwealth:
       1. to a Minister or Parliament in accordance with statutory or portfolio duties or functions or for public accountability reasons including following a request by a Minister, Parliament or a House or a Committee of the Parliament of the Commonwealth;
       2. to any Government Agency where this services the Commonwealth's legitimate interests including to the Australian National Audit Office;
       3. to AEMO or its Related Bodies Corporate and its or their Associates;
       4. to any person entitled to a licence or sublicence Specified Materials rights pursuant to this Agreement and its Associates;
    5. authorised or required by Law to be to be disclosed provided that:
       1. the party notifies the other party of the requirement to make that disclosure; and
       2. takes all reasonable steps to minimise the extent of the disclosure and to ensure the information is disclosed on a basis that the recipient agrees to maintain the confidentiality of the information;
    6. to:
       1. a bank or other financial institution (and its professional advisers) in connection with any existing or proposed loan or other financial accommodation or, or sought to be arranged by, the recipient of that information;
       2. any person who is proposing to acquire a direct or indirect interest in the party; or
       3. any Related Body Corporate of a party to this Agreement but only to the extent that such a person has a need to know,

and in each case provided the recipient agrees to act consistently with this clause;

* + 1. in the case of disclosure by the Commonwealth, Knowledge Sharing Deliverables that have been categorised by the Operator as "public information" pursuant to clause 15;
    2. to a rating agency;
    3. to the extent expressly permitted under this Agreement; and
    4. as otherwise agreed by the other party.
  1. Freedom of information
     1. Where the Commonwealth has received a request for access to a document created by, or in the possession of, the Operator or any Subcontractor that relates to the performance of this Agreement (and not to the entry into this Agreement), the Commonwealth may at any time by written notice require the Operator to provide the document to the Commonwealth and the Operator shall, at no additional cost to the Commonwealth, promptly comply with the notice.
     2. The Operator shall include in any first tier Subcontract (namely those which the Operator enters into directly with a Subcontractor) relating to the performance of any Transaction Document provisions that will enable the Operator to comply with its obligations under this clause 30.3.
     3. In this clause 30.3, 'document' has the same meaning as in the *Freedom of Information Act 1982* (Cth).
     4. Nothing in this clause 30 derogates from or restricts the Commonwealth's ability to comply with its obligations under the *Freedom of Information Act 1982* (Cth).

1. Access, records and reporting
   1. Operator to retain records
      1. The Operator must, throughout the Term and for a period of seven years after the expiry of the Term, keep true and accurate books of account, records and other documents (however stored) in relation to the Project including:
         1. operational data relating to the Project and the Facility including technical, metering, revenue, costs and financial data and Specified Materials; and
         2. those related to other matters relating to the Facility and the Project in accordance with Good Industry Practice,

(together the **Accounts and Records**).

* + 1. The Operator must:
       1. ensure that its Accounts and Records are prepared in accordance with the Corporations Act and generally accepted Australian Accounting Standards and practices consistently applied, and fairly represent its operations and financial condition or consolidated financial position (as the case may be); and
       2. procure that each Key Subcontractor's Accounts and Records truly reflect the status and scheduled achievement of the Project and are prepared in accordance with generally accepted Australian Accounting Standards (or equivalent) and fairly represent its operations and financial condition or consolidated financial position (as the case may be).
    2. The Operator must ensure that its Accounts and Records are available to the Commonwealth and its nominee at any time during business hours (subject to receiving 5 Business Days' prior notice from the Commonwealth) during the Term and for a period of seven years after the termination or expiry of this Agreement for examination, audit, inspection, transcription and copying and must ensure that each Key Subcontractor does likewise.
    3. If this Agreement is terminated or expires, the Operator must give the Commonwealth and its nominee access to all of its Accounts and Records which are necessary for the carrying out of the Operator's obligations under this Agreement and must ensure that each Key Subcontractor does likewise in relation to each of its or their Accounts and Records.
    4. The Operator must retain all Accounts and Records relating to the work and services undertaken pursuant to this Agreement for a period of seven years after termination or expiration of this Agreement or such longer period as may be required by Law. The Operator must procure that each Key Subcontractor retains all its Accounts and Records related to the work and services undertaken pursuant to this Agreement during:
       1. the Construction Period for a period of seven years after the earlier of termination of that Key Subcontract and COD; and
       2. the Operations Period for a period of seven years after termination or expiration of this Agreement or such longer period as may be required by Law.
    5. This clause 31.1 applies for the Term and for a period of seven years from the termination or expiry of this Agreement.
  1. Access to records
     1. During the performance of this Agreement, the Operator shall give the Commonwealth and its nominee access to:
        1. its premises during business hours and with at least 10 Business Days' prior notice; and
        2. any of its Accounts and Records,

relevant to or impacting on the performance of this Agreement, including the right to copy any Accounts and Records for the purposes of this Agreement.

* + 1. The Operator shall ensure that each Key Subcontractor gives the Commonwealth and its nominee, access to its or their:
       1. premises during business hours and with at least 10 Business Days' prior notice; and
       2. Accounts and Records,

relevant to or impacting on the performance of the Operator's obligations under this Agreement including the right to copy any Accounts or Records for the purposes of this Agreement, in each case for the following periods:

* + - 1. for Key Subcontractors undertaking works or services pursuant to this Agreement during the Construction Period, for a period of period of seven years after the earlier of termination of that Key Subcontract and COD; and
      2. for Key Subcontractors undertaking works or services pursuant to this Agreement during the Operations Period, for a period of seven years after termination or expiration of this Agreement or such longer period as may be required by Law.
    1. The Commonwealth's access to premises, systems, equipment and personnel will be subject to the Operator's or Key Subcontractor's (as applicable) reasonable instructions relating to site access and to physical and information security.
  1. Other information

The Operator must give to the Commonwealth the following information:

* + 1. details of any changes to the constitutions or trust deed of the Operator within 20 Business Days after the change; and
    2. such other financial and associated information relating to the Project as the Commonwealth may reasonably require from time to time and such information will be provided to the Commonwealth within 20 Business Days after it is requested.
  1. Right to access and audit
     1. The Commonwealth may elect to or commission a third party (**Auditor**) to audit and inspect the Accounts and Records of the Operator and, to the extent reasonably required by the Commonwealth, the Operator’s Related Bodies Corporate and/or Key Subcontractors, for the purpose of verifying:
        1. the accuracy of any report or information provided by the Operator arising from or in connection with this Agreement; and
        2. the Operator’s compliance with this Agreement.
     2. The Commonwealth may appoint either the Australian National Audit Office or an appropriately qualified independent professional firm as the Auditor.
     3. The Commonwealth must give the Operator at least 20 Business Days’ prior notice of any Audit.
     4. The Operator must comply with any such audit including that it must:
        1. subject to clause 31.4(e), allow the Auditor to access during business hours the Accounts and Records kept by the Operator and its Related Bodies Corporate and/or Key Subcontractors (as applicable) and any premises, systems, equipment, personnel and information of the Operator, its Related Bodies Corporate and/or Key Subcontractors relating to the Project or this Agreement;
        2. provide (and procure its Related Body Corporates and/or Key Subcontractors (as applicable) to provide) reasonable co-operation, information and assistance to the Auditor including answering reasonable questions relating to the audit and inspection in writing; and
        3. if an Audit reveals any breach of this Agreement by the Operator, the Operator must take remedial action including complying with any reasonable directions or instructions from the Commonwealth,

in each case in connection with Audit.

* + 1. The Auditor’s access to any premises, systems, equipment and personnel will be subject to the Operator’s reasonable instructions relating to site access and to physical and information security.
    2. In absence of fraud or manifest error, a finding of the Auditor in respect of any matter referred to in clause 31.4(a) will be binding on the parties.
    3. Subject to clause 31.4(h) and 31.4(i), the Operator must bear the reasonable costs associated with any Audit.
    4. Subject to clause 31.4(i), if the Commonwealth has required an audit under clause 31.4(a) more than once in any Financial Year (excluding any audits or investigations undertaken pursuant to Law including by the Auditor-General), the Commonwealth will bear the reasonable costs associated with any such second and subsequent audit undertaken in that Financial Year pursuant to clause 31.4(a) (excluding any costs incurred by or on behalf of the Operator).
    5. If any second or subsequent audit undertaken pursuant to clause 31.4(a) in any Financial Year (excluding any audits or investigations undertaken pursuant to Law including by the Auditor-General) does not identifies any breach of this Agreement by the Operator or demonstrates that any information or report provided by the Operator is not materially inaccurate, the Commonwealth will bear all the reasonable costs of that audit (excluding any costs incurred by or on behalf of the Operator).
    6. If an Audit is in respect of any amount to which the Operator is entitled and such Audit reveals that the Operator has overcharged the Commonwealth, the Operator must promptly reimburse the Commonwealth for those costs overcharged following any request by the Commonwealth to do so.
    7. If any Audit reveals that Operator's Payment Notice or invoices (including tax invoices) for the audited period are not correct for such period:
       1. the Operator must promptly reimburse the Commonwealth for the amount of any overcharges; or
       2. the Commonwealth must promptly pay to the Operator the amount of any undercharges,

in each case, as the case may be.

* + 1. The requirement for, and participation in, Audits does not in any way reduce the Operator's responsibility to perform its obligations in accordance with this Agreement.
    2. Any Audit, acceptance, certificate, approval, attendance, permission, comment or recommendation by, or on behalf of, the Commonwealth (or failure to do so) will not:
       1. constitute waiver of any default or acceptance of any act or omission on the part of the Operator; or
       2. affect or modify any of the Operator's obligation to perform this Agreement in accordance with its terms and conditions.
    3. Nothing in this Agreement modifies, limits or restricts the Auditor-General exercising any of its rights, functions or powers at Law including to undertake an audit of the Operator, any Project Document, the Project or the Capacity Investment Scheme program in part or as a whole.
  1. Site Inspection
     1. The Commonwealth may request access to the Project site from time to time for the purposes of undertaking a visual site inspection. The Commonwealth must give the Operator reasonable notice of the Commonwealth's requested Project site inspection under this clause 31.5, including details of preferred dates and times of it, and relevant Associates or nominees who will be present for it.
     2. The parties will agree (acting reasonably) a date and time for the Project site inspection.
     3. During the Project site inspection, the Commonwealth agrees to comply with the Operator's reasonable requirements, including in respect of site safety, occupational health and safety and other applicable site rules.

1. Reporting
   1. CP Period Reporting
      1. The Operator must:
         1. at least five Business Days before the end of each Quarter during the CP Period, provide a report to the Commonwealth detailing the Operator's progress towards satisfying each Condition Precedent; and
         2. promptly notify the Commonwealth if the Operator reasonably expects that it may not satisfy:
            1. a Condition Precedent on or before the relevant Condition Precedent Date;
            2. all of the Conditions Precedent on or before the CP Target Date; or
            3. all of the Conditions Precedent on or before the CP Sunset Date.
      2. A report or notification under clause 32.1(a) must include reasonable details and supporting evidence relating to and supporting its subject matter and, the Operator must promptly provide to the Commonwealth any further information reasonably requested by the Commonwealth regarding the subject matter of that report or notification within 5 Business Days after being requested to do so.
   2. Construction Period Reporting
      1. Within 20 Business Days after the end of each Quarter during the Construction Period, the Operator must provide the Commonwealth, in the form prescribed by the Commonwealth, a report setting out:
         1. the progress of achieving the Milestone Events as against the relevant Milestone Date (Scheduled), including information regarding any act, fact, matter, thing, event or circumstance which may cause the Operator not to achieve a Milestone by the relevant Milestone Date (Scheduled);
         2. the progress of design, construction, commissioning, testing and completion of the Facility and information regarding any act, fact, matter, thing, event or circumstance which may prevent the satisfaction of the COD Conditions by either one or more of the COD (Target), the Final Support Commencement Date and the COD (Sunset);
         3. if it is likely that any Milestone Event will not be achieved by its relevant Milestone Date (Scheduled), details of the steps being taken to remedy that delay and the date on which that Milestone Event is reasonably expected to be achieved including supporting evidence and construction programs which show the actual progress of the design, construction, commissioning, testing and completion of the Facility and the new proposed date for achieving the relevant Milestone Events against the Milestone Dates (Scheduled);
         4. the progress in obtaining Authorisations required for the design, construction, commissioning, testing, completion, operation and/or maintenance of the Project;
         5. any proposed changes to the scope of the Project;
         6. any material occupational health and safety incidents (including near misses);
         7. complaints received or legal proceedings issued in relation to the Project (other than those issued by the Commonwealth);
         8. any matter which constitutes a material breach, or could constitute a material breach, of the Operator’s obligations under any Project Document;
         9. a list of the Key Subcontractors which have been engaged to the date of the report, a high level description of the works and/or services for which they have been engaged and the period over which those works and/or services will be performed; and
         10. any other matter reasonably requested in writing by the Commonwealth, which may include information that is reasonably necessary for the Commonwealth to discharge its rights and obligations under this Agreement or at Law in respect of the Project.
      2. The Operator must notify the Commonwealth during the Construction Period:
         1. within 2 Business Days, after the occurrence of a death or serious injury related to the Project;
         2. within 5 Business Days, after the Operator becomes aware of any matter which constitutes any breach of the Operator’s material obligations under this Agreement; and
         3. within 10 Business Days, after the occurrence of a dangerous incident or a complaint made in relation to contamination, Environmental harm or breach of any Law relating to the Environment.
   3. Operating reports
      1. The Operator must provide the Commonwealth a report, in the form prescribed by the Commonwealth, setting out the following for the relevant periods:
         1. within 20 Business Days after the end of each Operating Year:
            1. a summary of all Deemed Availability Periods that occurred during that Operating Year;
            2. the Equivalent Availability Factor for the Project for that Operating Year;
            3. a summary of the timing and duration of any planned or unplanned maintenance or outages and any instances of reduced export, import or storage capacity of the Facility (including because of Input Resource availability and maintenance of the Facility) during that Operating Year together with reasonable supporting details of those matters; and
            4. for each unplanned maintenance event and/or outage and instance of reduced export, import or storage capacity of the Facility during that Operating Year, a summary of the cause and actions or proposed actions to be undertaken by or on behalf of the Operator to remedy and to prevent such unplanned maintenance events and/or outages together with reasonable supporting details of the cause, actions and proposed actions;
            5. a list of the Key Subcontractors which have been engaged to the date of the report related to the Operations Period, a high level description of the works and/or services for which they have been engaged and the period over which those works and/or services will be performed; and
         2. within 20 Business Days after the end of each Support Year:
            1. the Availability Rebate Percentagefor that Support Year; and
            2. the Availability Rebate (if any) payable in respect of that Support Year.
      2. The Operator must provide to the Commonwealth a report, in the form prescribed by the Commonwealth, setting out the following for the relevant periods:
         1. within 20 Business Days after the end of each Operations Year, the results of the Storage Capacity test identified in section 5.4 of Schedule 4 for that Operations Year;
         2. within 20 Business Days after the end of each Support Year:
            1. the Storage Capacity Rebate Percentage for that Support Year; and
            2. the Storage Capacity Rebate (if any) payable in respect of for that Support Year,

(each an **Annual** **Storage Capacity Report**).

* + 1. Within 20 Business Days after the end of each Quarter during the Operations Period, the Operator must provide the Commonwealth a report, in the form prescribed by the Commonwealth, setting out:
       1. the progress in obtaining (or confirmation that it holds and has maintained) as applicable the relevant Authorisations required for the operation and/or maintenance of the Project;
       2. any proposed changes to the Facility and/or the scope of the Project;
       3. any material occupational health and safety incidents;
       4. complaints received or legal proceedings in relation to the Project;
       5. any matter which constitutes a material breach, or may constitute a material breach, of the Operator’s obligations under any Project Document; and
       6. any other matter reasonably requested in writing by the Commonwealth, which may include information that is reasonably necessary for the Commonwealth to discharge its rights and obligations under this Agreement or at Law in respect of the Project.
    2. The Operator must notify the Commonwealth during the Operations Period:
       1. within 2 Business Days, after the occurrence of a death or serious injury related to the Project;
       2. within 5 Business Days, after the Operator becoming aware of any breach of the Operator’s material obligations under this Agreement; and
       3. within 10 Business Days, after the occurrence of a dangerous incident or a complaint made in relation to contamination, Environmental harm or breach of any Law related to the Environmental.
  1. Revenue reports

Within 20 Business Days after the end of each Support Year, the Operator must provide the Commonwealth, in the form prescribed by the Commonwealth, a report setting out:

* + 1. the Net Operational Revenue (including each of its respective components and the Contracted Percentage of the Net Operational Revenue (if applicable)) for; and
    2. the Annual Reconciliation Payment (if any) payable in respect of that Support Year,

that Support Year.

* 1. Capacity Products and Green Product reporting
     1. If the Operator holds Capacity Products or Green Products which were created, or referable to electricity exported from, capacity available from or operation of the Facility, during a Support Year, the Net Operational Revenue for that Support Year will be deemed to include an amount equal to the relevant market price for such products multiplied by number of each of those Capacity Products and Green Products the Operator holds.
     2. Unless otherwise agreed by the parties, the market price for such products will determined as the average of the quotations (stated on a GST exclusive basis) for the Support Year, obtained from two independent and appropriately qualified brokerage firms, one nominated by each of the parties.
     3. If a market price cannot be determined in accordance with clause 32.5(b), the matter will be referred to an Independent Expert for determination under clause 35.6.
  2. Foreign Acquisitions and Takeovers Act reporting
     1. If:
        1. the Operator receives a notice from or on behalf of the Treasurer of the Commonwealth of Australia under the *Foreign Acquisitions and Takeovers Act 1975* (Cth) which provides that the relevant Government Agency has approved an application made by Operator in respect of the Project and that approval is subject to certain conditions that may apply to either the Operator or the Project; or
        2. there is a change to, or satisfaction of such conditions referred to under clause 32.6(a)(i),

the Operator must notify the Commonwealth within 5 Business Days after receiving such notice under clause 32.6(a)(i) or of such occurrence under clause 32.6(a)(ii).

* + 1. The Operator must notify the Commonwealth within 5 Business Days after becoming aware of any breach of such conditions notified under 32.6(a). [**Drafting Note: the shortlisted Proponent must notify the Commonwealth in its Financial Value Bid Form for Stage B of the Tender Process whether or not it or the Project is subject to the *Foreign Acquisitions and Takeovers Act 1975* (Cth).]**
  1. Assurances

1. Each report issued under clauses 32.1, 32.2, 32.3 and 32.4 and, if requested by the Commonwealth, any notice provided pursuant to clause 32.1, 32.2, 32.3 and 32.6 and any further information provided by Operator pursuant to clause 32.8, must be certified by a director of the Operator to be:
   1. true and fair statements; and
   2. compliant with this Agreement and any relevant accounting standards (as applicable).
2. The Operator warrants and represents that each report issued under clauses 32.1, 32.2, 32.3 and 32.4 and any notice provided pursuant to clause 32.1, 32.2, 32.3 or 32.6 and any further information provided by Operator pursuant to clause 32.8 is true and fair.
3. The Operator acknowledges that the provision of any false or misleading information by it under this clause 32 is a material breach of Operator’s obligations under this Agreement.
   1. Provision of further information
      1. Each report issued under clauses 32.1, 32.2, 32.3 and 32.4 and each notice provided pursuant to clause 32.1, 32.2, 32.3 and 32.6 must include reasonable supporting details and evidence in respect of matters required to be included in a report issued under clause clauses 32.1, 32.2, 32.3 or 32.4 and each notice provided pursuant to clause 32.1 32.2, 32.3 or 32.6.
      2. If reasonably requested by the Commonwealth following receipt of a report issued under clauses 32.1, 32.2, 32.3 or 32.4 or any notice provided pursuant to clause 32.1, 32.2, 32.3 or 32.6, the Operator must promptly provide further supporting details and evidence in relation to any report or the operation, bidding and dispatch of the Facility in the relevant Quarter or Support Year (as applicable).
4. Publicity
   * 1. Unless required by Law or by a recognised stock exchange on which the Operator's shares or units are listed, the Operator must not make any public announcements relating to the subject matter of any Project Document without the Commonwealth's prior written consent.
     2. The Commonwealth may make public announcements relating to the subject matter of any Project Document (including in respect of the Facility's expected Maximum Capacity, Import Capacity and Storage Capacity and the Operator's Social Licence Commitments) without the Operator's prior written consent, provided that the Commonwealth must:
        1. consult with the Operator before making any such public announcement that contains commercially sensitive information (and for the avoidance of doubt, amount of support which the Commonwealth is providing the Operator under this Agreement and the Maximum Capacity, Import Capacity and Storage Capacity and the Operator's Social Licence Commitments are not commercially sensitive information); and
        2. reasonably consider any request from the Operator to not include that commercially sensitive information, or to only include that commercially sensitive information on an anonymised and aggregated basis, in the relevant public announcement.
5. Relevant Commonwealth Policies and Other Requirements

The Operator must comply with the requirements imposed on it in Schedule 11.

1. Dispute Resolution
   1. Dispute mechanism

Any dispute or difference of any kind arising between the parties arising from or in connection with this Agreement, whether during or after the Term (**Dispute**) must be resolved pursuant to this clause 35.

* 1. No proceedings

Subject to clause 35.9, a party must not commence or maintain a court action or proceedings in relation to a Dispute until the party has complied with this clause 35, and, if applicable, clause 36.

* 1. Disputes

If a party wishes to raise a Dispute, that party must deliver to the other party a notice of dispute (**Dispute Notice**) setting out the:

* + 1. nature of the Dispute;
    2. facts, matters and circumstances relied upon by the party serving the Dispute Notice; and
    3. anticipated quantum of the Dispute (in money and, if applicable, in time).
  1. Procedure to resolve Disputes
     1. If there is a Dispute, the parties must use reasonable endeavours to resolve that Dispute as soon as reasonably practicable.
     2. Subject to clause 36, the procedure that is to be followed to resolve a Dispute is as follows:
        1. first, negotiation of the Dispute under clause 35.5;
        2. second, if the Dispute is not resolved pursuant to clause 35.4(b)(i) and only if permitted under clause 35.5(b)(i), referral of the Dispute for determination by an Independent Expert under clause 35.6; and
        3. third, if the Dispute is not resolved pursuant to clause 35.4(b)(i) and if a referral of that Dispute for determination by an Independent Expert under clause 35.6 is permitted under this Agreement, that Dispute has not been resolved pursuant to clause 35.4(b)(ii), determination of the Dispute in a court of competent jurisdiction.
  2. Negotiation
     1. Within 10 Business Days after the receipt of a Dispute Notice by the other party pursuant to clause 35.3, a senior representative of each party must meet, negotiate and seek to resolve the Dispute in Good Faith.
     2. If the Dispute is not resolved within 30 Business Days after the receipt of the Dispute Notice by the other party pursuant to clause 35.3:
        1. where this Agreement expressly provides that it is a matter which is to be referred for determination by an Independent Expert, and a party wishes to progress that Dispute, that party must by written notice refer the Dispute for determination by an Independent Expert under clause 35.6; and
        2. where this Agreement does not expressly provide that it is a matter which is to be referred for determination by an Independent Expert and a party wishes to progress that Dispute, that party must commence proceedings in a court of competent jurisdiction.
  3. Independent Expert
     1. If this Agreement expressly provides that a Dispute is to be referred for determination by an independent expert and a party wishes to progress the Dispute, that party must refer that Dispute to be determined by an appropriately qualified independent expert (**Independent Expert**). The parties must use reasonable endeavours to agree the identity of that Independent Expert within 10 Business Days after a notice referring that Dispute to an Independent Expert being given (or such longer period the parties agree).
     2. Failing agreement within the period specified in clause 35.6(a), if a party wishes to progress the Dispute, that party must request the CEO of the Resolution Institute (or their independent nominee) to identify and appoint an Independent Expert.
     3. If an Independent Expert is not appointed within 20 Business Days after the date of the request being made to the CEO of the Resolution Institute (or their independent nominee) under clause 35.6(b), and a party wishes to progress the Dispute, that party must commence proceedings in a court of competent jurisdiction in relation to the Dispute.
     4. The Independent Expert appointed must have reasonable qualifications, and commercial and practical experience (including in the context of the National Energy Market) and no interest or duty which conflicts or may conflict with their function as an Independent Expert.
     5. The Independent Expert will act as an expert and not as an arbitrator.
     6. The parties must comply with all reasonable requests by an Independent Expert for information relating to the Dispute.
     7. The parties must ensure that the Independent Expert’s terms of appointment include the following requirements:
        1. the Independent Expert must consult with the parties concerning the matters under Dispute;
        2. the Independent Expert must make a draft report available to the parties within 30 Business Days after the appointment of the Independent Expert;
        3. the Independent Expert must meet with representatives of the parties to discuss any queries they may have in relation to the draft report;
        4. the Independent Expert must keep information provided by or on behalf of the parties to the Independent Expert confidential;
        5. the Independent Expert may investigate the matters under Dispute and make inquiries in relation to them, and take the advice of any other person the Independent Expert deems appropriate; and
        6. the Independent Expert will use best endeavours to notify the parties of the Independent Expert’s determination within 60 Business Days after the reference of the Dispute by a party to the Independent Expert.
     8. In the absence of fraud or manifest error, the parties agree that any decision or award made by an Independent Expert will be final and binding.
     9. Each party will bear its own costs in respect of or in connection with any determination by an Independent Expert.
     10. The costs of the Independent Expert will be borne equally between the parties.
  4. Other relief

The dispute resolution procedures in this clause 35 and/or clause 36 do not apply to impair, delay or otherwise prejudice the exercise by a party of its rights provided in any Project Document (including any right of termination).

* 1. Continued performance following a Dispute

Despite the existence of any Dispute, each party must continue to perform its obligations under each Project Document.

* 1. Interim relief

Nothing in this clause 35 or clause 36 prevents either party from seeking urgent injunctive or declaratory relief.

1. Pooled Disputes
   1. Referral of Pooled Disputes
      1. If in the Commonwealth's opinion (acting reasonably):
         1. a Dispute in relation to clause 35 is identical or similar to an Other Dispute; or
         2. the outcome of a Dispute or an Other Dispute could affect the entitlements and/or obligations of a party under this Agreement or an Other Agreement (as relevant),

and the Agreement and Other Agreement pursuant to which the Dispute and Other Dispute (as applicable) arise have the same governing law, the Dispute and/or Other Dispute is a **Pooled Dispute**.

* + 1. If the Commonwealth gives a Dispute Notice to or receives a Dispute Notice from:
       1. the Operator; or
       2. any Other Counterparty,

relating to a Pooled Dispute, the Commonwealth may refer the Pooled Dispute to a Pooled Dispute Panel for resolution in accordance with clause 36.2 (**Pooled Dispute Referral**).

* 1. Resolution by Pooled Dispute Panel
     1. If the Commonwealth gives a Pooled Dispute Referral in respect of a Pooled Dispute, then:
        1. each Pooled Dispute Participant may appoint a person to represent it on the Pooled Dispute Panel; and
        2. the Pooled Dispute Panel will meet within 1 month (or such other period as reasonably determined by the Commonwealth) from the Pooled Dispute Referral to resolve the Pooled Dispute.
     2. The Pooled Dispute Panel will determine (on a unanimous basis) its own procedures for meeting, and unless the Pooled Dispute Panel otherwise determines (on a unanimous basis), all meetings of the Pooled Dispute Panel will be held in Melbourne with an option provided for participation via video conference.
     3. If a party provides information or documents relevant to a Pooled Dispute to the other party, it must promptly provide the information and documents to each representative on the Pooled Dispute Panel.
     4. Subject to clause 36.3, if the Pooled Dispute Panel unanimously resolves the Pooled Dispute, then that resolution will be binding on the parties to this Agreement regardless of whether they participated in the Pooled Dispute Panel or not.
     5. If the Pooled Dispute Panel does not unanimously resolve the Pooled Dispute within 3 months after the Pooled Dispute Referral, the Commonwealth may refer the Pooled Dispute for resolution in accordance with clause 35.6, provided that:
        1. the Independent Expert will be identified and appointed by the CEO of the Resolution Institute (or their independent nominee);
        2. each Pooled Dispute Participant will be afforded equal treatment and equal opportunity to present its views and to reply to the comments and submissions presented by any other Pooled Dispute Participant;
        3. in the absence of fraud or manifest error, the parties agree that any decision or award made by an Independent Expert will be final and binding on all Pooled Dispute Participants; and
        4. the costs of the Independent Expert will be borne equally between the Pooled Dispute Participants.
  2. Bilateral resolution
     1. If the Operator and the Commonwealth bilaterally resolve a Pooled Dispute as it applies to this Agreement, clause 36.2 will cease to apply and Operator will:
        1. cease to be a Pooled Dispute Participant in respect of that Pooled Dispute; and
        2. not be required to participate in, and will not be bound by any resolution by, the Pooled Dispute Panel in respect of that Pooled Dispute.
     2. If the Commonwealth notifies the Operator that an Other Counterparty has bilaterally resolved the Pooled Dispute with the Commonwealth, then that Other Counterparty will cease to be a Pooled Dispute Participant.

1. Governing Law
   * 1. The Law in force in the Relevant Jurisdiction governs this Agreement.
     2. The parties irrevocably submit to the non-exclusive jurisdiction of the courts of the Relevant Jurisdiction and the courts competent to determine appeals from the courts of the Relevant Jurisdiction, with respect to any proceedings which may be brought in connection with this Agreement.
2. Notices
   1. Form
      1. Unless this Agreement expressly states otherwise, all notices, demands, certificates, consents, approvals, waivers and other communications in connection with this Agreement (**Communications**) must be in writing and signed by the sender (if an individual) or a director, secretary or any other person nominated by a party to act as an authorised officer of the sender.
      2. All Communications (other than email Communications) must also be marked for the attention of the person referred to in the Details (or, if the recipient has notified otherwise, then marked for attention in the way last notified).
      3. Email Communications must state the first and last name of the sender and are taken to be signed by the named sender.
   2. Delivery
      1. Communications must be:
         1. left at the address referred to in the Details;
         2. sent by regular ordinary post (airmail if appropriate) to the address referred to in the Details; or
         3. sent by email to the email address referred to in the Details provided however that email must not be used for any termination notice issued pursuant to this Agreement.
      2. If the intended recipient has notified changed contact details, Communications must be sent to the changed contact details.
   3. When effective

Communications take effect from the time they are received or taken to be received under clause 38.4 (whichever happens first) unless a later time is specified in the Communication.

* 1. When taken to be received

Communications are taken to be received:

* + 1. if sent by prepaid express post, 5 Business Days after posting (or 8 Business Days after the date of posting by airmail to if sent from one country to another);
    2. if sent by email:
       1. when the sender receives an automated message confirming delivery; or
       2. 4 hours after the time the email is sent (as recorded on the device from which the sender sent the email) unless the sender receives an automated message within that 4 hour period that the delivery failed,

whichever happens first.

* 1. Receipt outside business hours

Despite anything else in this clause 38, if Communications are received or taken to be received under clause 38.4 after 5.00pm on a Business Day or on a non-Business Day, they are taken to be received at 9.00am on the next Business Day. For the purposes of this clause 38.5, the place in the definition of Business Day is taken to be the place specified in the Details as the address of the recipient and the time of receipt is the time in that place.

1. General
   1. Variation and waiver

A provision of this Agreement, or right, power or remedy created under it, may not be varied or waived except in writing signed by the party to be bound.

* 1. Consents, approvals or waivers
     1. A failure to exercise or enforce, a delay in the exercise or enforcement of or the partial exercise or enforcement of a right provided by Law or under this Agreement by a party does not preclude, or operate as a waiver of, the exercise or enforcement, or further exercise or enforcement, of that or any other right provided by Law or under this Agreement.
     2. By giving any consent, approval or waiver a party does not give any representation or warranty as to any circumstance in connection with the subject matter of the consent, approval or waiver.
     3. No waiver of a breach of a term of this Agreement operates as a waiver of another breach of that term or of a breach of any other term of this Agreement.
  2. Discretion in exercising rights

Unless a Project Document expressly provides otherwise, a party may exercise a right, power or remedy or give or refuse its consent, approval or a waiver in connection with this Agreement in its absolute discretion (including by imposing conditions).

* 1. Partial exercising of rights

Unless this Agreement expressly states otherwise, if a party does not exercise a right, power or remedy in connection with this Agreement fully or at a given time, they may still exercise it later.

* 1. Remedies cumulative

The rights, powers and remedies in connection with this Agreement are in addition to other rights, powers and remedies given in any other agreement or by Law independently of any Project Document.

* 1. Indemnities and reimbursement obligations
     1. Any indemnity, reimbursement, payment or similar obligation in this Agreement:
        1. is a continuing obligation despite the satisfaction of any payment or other obligation in connection with this Agreement, any settlement or any other thing;
        2. is independent of any other obligations under this Agreement or any other agreement; and
        3. continues after this Agreement, or any obligation arising under it, ends.
     2. It is not necessary for a party to incur expense or make payment before enforcing a right of indemnity in connection with this Agreement.
  2. Supervening law

Subject to clause 21, any present or future Law which operates to vary the obligations of a party in connection with this Agreement with the result that another party’s rights, powers or remedies are adversely affected (including, by way of delay or postponement) is excluded except to the extent that its exclusion is prohibited or rendered ineffective by Law.

* 1. Counterparts
     1. This Agreement may be executed in any number of counterparts or copies, each of which may be executed by physical signature in wet ink or electronically (whether in whole or part). A party who has executed a counterpart of this Deed may exchange it with another party (the **Other Party**) by:
        1. emailing a copy of the executed counterpart to the Other Party; or
        2. utilising an electronic platform (including DocuSign) to circulate the executed counterpart,

and will be taken to have adequately identified themselves by so emailing the copy to the Other Party or utilising the electronic platform.

* + 1. Each party consents to signatories and parties executing this Agreement by electronic means and to identifying themselves in the manner specified in this clause 39.8.
    2. Each counterpart constitutes an original (whether kept in electronic or paper form), all of which together constitute one instrument as if the signatures (or other execution markings) on the counterparts or copies were on a single physical copy of this Agreement in paper form. Without limiting the foregoing, if any of the signatures or other markings on behalf of one party are on different counterparts or copies of this Agreement, this shall be taken to be, and have the same effect as, signatures on the same counterpart and on a single copy of this Agreement.
  1. Entire agreement

This Agreement constitutes the entire agreement of the parties on the subject matter and supersedes all prior agreements, understandings and negotiations on that subject matter.

* 1. Expenses and no liability for loss

Unless otherwise expressly provided in this Agreement, each party must pay its own costs and expenses in connection with negotiating, preparing, executing and performing this Agreement.

* 1. Rules of construction

No rule of construction applies to the disadvantage of a party because that party was responsible for the preparation of, or seeks to rely on, this Agreement or any part of it.

* 1. Severability

If the whole or any part of a provision of this Agreement is void, unenforceable or illegal in a jurisdiction, then it is severed for that jurisdiction. The remainder of this Agreement has full force and effect and the validity or enforceability of that provision in any other jurisdiction is not affected. This clause 39.12 has no effect if the severance alters the basic nature of this Agreement or is contrary to public policy.

* 1. Survival

Each of the following will survive the expiry or termination of this Agreement:

* + 1. clauses 1, 3, 15, 16, 17, 18, 22, 23, 25, 27, 28, 30, 31, 32, 33, 34, 35, 36, 37, 38 and 39;
    2. any provision that is required to enable a party to exercise rights accrued prior to the expiry, recission or termination of this Agreement; and
    3. any provision which (expressly or by implication) by its nature is intended to survive the expiry, recission or termination of this Agreement.
  1. Proportionate liability

The operation of Part IVAA (Proportionate Liability) of the *Wrongs Act 1958* (Vic) and Part 3 of the *Law Reform (Contributory Negligence and Apportionment of Liability) Act 2001* (SA) are excluded in relation to all and any rights of either party under this Agreement, whether such rights are sought to be enforced in contract, tort or otherwise.

* 1. Further steps

The Operator and the Commonwealth agree, at the Operator’s expense, to do anything the other reasonably requests (such as obtaining consents, signing and producing documents, producing receipts and getting documents completed and signed) as may be necessary or desirable to give full effect to the provisions of this Agreement and the transactions contemplated by it.

1. – Reference Details

| **Item #** | Item | Details |
| --- | --- | --- |
|  | Facility | **[Drafting note: the shortlisted Proponent is required to complete this Item 1 here as part of its Financial Value Bid in Stage B of the Tender Process.]**  The ‘[insert facility name]’, which will be a [insert resource type e.g. battery project] located at [insert location] with:  (a) a Registered Capacity that is equal to at least the Maximum Capacity;  (b) an import capacity that it equal to or greater than the Import Capacity; and  (c) an energy storage capacity that is equal to or greater than the Storage Capacity,  and which includes all ancillary plant, control systems and connection infrastructure on the Operator's side of the Connection Point required for the operation of the facility. |
|  | Maximum Capacity | **[Drafting note: the shortlisted Proponent is required to complete this Item 2 here as part of its Financial Value Bid in Stage B of the Tender Process. It is also required to provide this information in MC5 Returnable Schedule. This information must be consistent with the Maximum Capacity identified by the shortlisted Proponent in Stage A of the Tender Process.]**  [insert] MW which is the maximum export capacity of the Facility measured in accordance with Good Industry Practice at the Connection Point. |
|  | Import Capacity | **[Drafting note: the shortlisted Proponent is required to complete this Item 3 here as part of its Financial Value Bid in Stage B of the Tender Process. It is also required to provide this information in MC5 Returnable Schedule.]**  [insert] MW which is the maximum import capacity of the Facility measured in accordance with Good Industry Practice at the Connection Point. |
|  | Storage Capacity | **[Drafting note: the storage capacity set out here is to reflect degradation to the extent relevant for the technology type. The number of rows in the table below should reflect the number of Support Years which apply to this Agreement noting that if the first Support Year does not commence on 1 July, there will need to be one more Support Year in the table below than there are years of support being sought because the first and last Support Years will be only part of a year. The shortlisted Proponent is required to complete this Item 4 here as part of its Financial Value Bid in Stage B of the Tender Process. It is also required to provide this information in MC5 Returnable Schedule. This information must be consistent with the Storage Capacity identified by the shortlisted Proponent in Stage A of the Tender Process.]**  **Storage Capacity** means the storage capacity as at COD and for each Support Year as follows:  (a) as at COD [insert] MWh;  (b) for the first Support Year [insert] MWh;  (c) for the second Support Year [insert] MWh;  (d) for the third Support Year [insert] MWh; and  (e) [insert further rows to reflect the Support Period] [insert] MWh. |
|  | Contracted Capacity | **[Drafting note: this will be equal to the Maximum Capacity of the Facility if the whole Facility is to be supported and a lesser MW if the Proponent is only seeking support for part of the capacity of the Facility. The shortlisted Proponent is required to complete this Item 5 here as part of its Financial Value Bid in Stage B of the Tender Process. It is also required to provide this information in MC5 Returnable Schedule]**  means [insert] MW. |
|  | Contracted Percentage | **[Drafting note: for each Support Year, this will be calculated as the Contracted Capacity divided by the Maximum Capacity (expressed as a percentage). This will be 100% if the whole capacity of the Facility is to be supported and a lesser percentage if the Successful Proponent is only seeking support for part of the capacity. The shortlisted Proponent is required to complete this Item 6 here as part of its Financial Value Bid in Stage B of the Tender Process. It is also required to provide this information in MC5 Returnable Schedule.]**  [insert number]% |
|  | CP Target Date | **[Drafting note: the shortlisted Proponent is required to complete this Item 7 here as part of its Financial Value Bid in Stage B of the Tender Process.]**  [insert date] (as such date may be adjusted pursuant to the terms of this Agreement). |
|  | CP Sunset Date | [Drafting note: this date must be no later than the date which is 12 months after the initial CP Target Date (as may be extended pursuant to the terms of this Agreement). The shortlisted Proponent is required to complete this Item 8 here as part of its Financial Value Bid in Stage B of the Tender Process.]  [insert date] (as such date may be adjusted pursuant to the terms of this Agreement). |
|  | Notice to Proceed Date | **[Drafting note: this is the date on which the Notice to Proceed is scheduled to be issued under the relevant Construction Contracts. Construction Contracts do not include an early works contract. The shortlisted Proponent is required to complete this Item 9 here as part of its Financial Value Bid in Stage B of the Tender Process.]**  [insert date] |
|  | Registration Date | **[Drafting note: this is the date on which the Facility is scheduled to undergo hold point testing and achieve registration with the network operator. For NEM connected projects, this would be achieving R1 Registration with AEMO. The shortlisted Proponent is required to complete this Item 10 here as part of its Financial Value Bid in Stage B of the Tender Process.]**  [insert date] |
|  | COD (Target) | **[Drafting note: The shortlisted Proponent is required to complete this item 11 as part of its Financial Value Bid in Stage B of the Tender Process. It is also required to provide this information in MC5 Returnable Schedule. This information must be consistent with the COD (Target) identified by the shortlisted Proponent in Stage A of the Tender Process]**  [insert date] (as such date may be adjusted pursuant to the terms of this Agreement). |
|  | COD (Sunset) | **[Drafting note: this date is the COD (Target) plus 12 months. The shortlisted Proponent is required to provide this information as part of its Financial Value Bid in Stage B of the Tender Process.]**  [insert date] (as such date may be adjusted pursuant to the terms of this Agreement). |
|  | Final Support Commencement Date | **[Drafting note: this date is the initial COD (Target) plus 12 months. The shortlisted Proponent is required to complete this Item 13 here as part of its Financial Value Bid in Stage B of the Tender Process.]**  [insert date] and for the avoidance of doubt, this date is not subject to adjustment pursuant to this Agreement other than by the Commonwealth in its absolute discretion pursuant to clause 8.3. |
|  | Final Expiry Date | **[Drafting note: Proponent to proposes the relevant number which may be any whole number of years up to and including the fifteenth anniversary. The shortlisted Proponent is required to complete this Item 14 here as part of its Financial Value Bid in Stage B of the Tender Process. It is also required to provide this information in MC5 Returnable Schedule.]**  means the date which is the [insert number] anniversary after the earlier of the day after COD and the Final Support Commencement Date. |
|  | Security Amount | **[Drafting note: the amount to be calculated using the following formula: $20,000 per MW multiplied by the Maximum Capacity, up to a maximum amount of $4,000,000. The shortlisted Proponent is required to complete this item 15 here as part of its Financial Value Bid in Stage B of the Tender Process.]**  [insert amount] |
|  | Minimum Hours | **[Drafting note: the Minimum Hours must not be less than 2 hours. The shortlisted Proponent is required to complete this Item 16 here as part of its Financial Value Bid in Stage B of the Tender Process. This information must be consistent with the Minimum Hours identified by the shortlisted Proponent in Stage A of the Tender Process.]**  [insert number] hours. |
|  | Support Period Start Date | **[Drafting note: if the shortlisted Proponent is seeking a support for the full term, the Support Period Start Date should be COD. However, a Proponent may consider that it wants support for a shorter period. Proponents are permitted to bid back a date later than COD or a concept which for example could be a number of years after COD provided however that the Support Period Start Date must be no later than the date which is 14 years after COD. The shortlisted Proponent is required to complete this Item 17 here as part of its Financial Value Bid in Stage B of the Tender Process. It is also required to provide this information in MC5 Returnable Schedule.]**  means [insert date or concept such as a number of whole years after COD]. |
|  | Annual Revenue Floor | **[Drafting note: the shortlisted Proponent is required to complete this Item 18 here as part of its Financial Value Bid in Stage B of the Tender Process. It is also required to provide this information in MC5 Returnable Schedule.]**  The Annual Revenue Floor in respect of a Support Year is:  (a) for the first Support Year $[insert];  (b) for the second Support Year $[insert];  (c) for the third Support Year $[insert];  (d) for the fourth Support Year $[insert]; and  (e) [insert further rows to reflect the Support Period] $[insert]. |
|  | Annual Revenue Ceiling | **[Drafting note: the shortlisted Proponent is required to complete this Item 19 here as part of its Financial Value Bid in Stage B of the Tender Process. It is also required to provide this information in MC5 Returnable Schedule.]**  The Annual Revenue Ceiling in respect of a Support Year is:  (a) for the first Support Year $[insert];  (b) for the second Support Year $[insert];  (c) for the third Support Year $[insert];  (d) for the fourth Support Year $[insert]; and  (e) [insert further rows to reflect the Support Period] $[insert]. |
|  | Annual Payment Cap | **[Drafting note: the shortlisted Proponent is required to complete this Item 20 here as part of its Financial Value Bid in Stage B of the Tender Process. It is also required to provide this information in MC5 Returnable Schedule.]**  The Annual Payment Cap in respect of a Support Year is:  (a) for the first Support Year $[insert];  (b) for the second Support Year $[insert];  (c) for the third Support Year $[insert];  (d) for the fourth Support Year $[insert]; and  (e) [insert further rows to reflect the Support Period] $[insert];. |
|  | Metering Point | **[Drafting note: the shortlisted Proponent is required to complete this Item 21 here as part of its Financial Value Bid in Stage B of the Tender Process.]**  means [insert]. |
|  | Minimum State of Charge | **[Drafting note: the shortlisted Proponent is required to complete this Item 22 here as part of its Financial Value Bid in Stage B of the Tender Process to the extent relevant to the type of technology being proposed for the Facility.]**  means [insert] MWh |

1. - Conditions Precedent

|  | Condition Precedent | Condition Precedent Date  [Drafting note: the shortlisted Proponent is required to complete this column as part of its Financial Value Bid in Stage B of the Tender Process. ] |
| --- | --- | --- |
| 1 | **[Drafting note: the Commonwealth reserves the right to add conditions precedent after reviewing Bids and the relevant Proponent's potential equity funding and debt financing arrangements and transaction structure]** | [insert] |
| 2 | The Operator has secured all Tenure required for the Project. | [insert] |
| 3 | The Operator has obtained all Authorisations related to planning for the Projects which are required to commence works. | [insert] |
| 4 | The Operator has obtained notifications from AEMO under clauses 5.3.4A and 5.3.4B of the NER in respect of the Project. | [insert] |
| 5 | The Operator has obtained an offer to connect (on terms acceptable to the Operator) under clause 5.3.6 of the NER from the relevant Network Service Provider in respect of the Project | [insert] |
| 6 | The Commonwealth receiving a certified copy of the approval of the Foreign Investment Review Board of the Commonwealth Department of Treasury in respect of any foreign ownership of any equity investor in the Operator. | [insert] |
| 7 | Financial Close/Commercial Close has occurred in respect of the Project **[Drafting note: to be drafted to be Financial Close if the Project is funded by external debt and Commercial Close if not]** | [insert] |
| 8 | The Operator delivering to the Commonwealth an original counterpart of each Project Document (other than this Agreement) and certified copies of the other Transaction Documents) in each case duly executed by each of the parties to those documents other than the Commonwealth in a form and substance satisfactory to the Commonwealth (acting reasonably). | [insert] |
| 9 | The Commonwealth receiving legal opinions given for the benefit of the Commonwealth in form and substance satisfactory to the Commonwealth (acting reasonably) from an from an external law firm appointed by the relevant counterparties to the Project Documents (other than the Commonwealth) as to:  (a) the legal capacity and corporate power of those relevant counterparties to enter into and perform its relevant obligations under the Project Documents to which it is a party;  (b) due execution by the relevant counterparty of the Project Documents to which it is a party; and  (c) the enforceability against the relevant counterparty of the Project Documents to which it is a party. | [insert] |

1. - Milestone Events and Milestone Dates (Scheduled)

Each Milestone Event and Milestone Date (Scheduled) under this Agreement is set out or identified in the following table:

|  | Milestone Event | Description | Milestone Date (Scheduled) (CD + x Months) or the relevant date identified |
| --- | --- | --- | --- |
| 1 | Notice to Proceed | Where the Operator has issued the Notice to Proceed. | Notice to Proceed Date |
| 2 | AEMO Registration complete | Registration with AEMO is approved. | Registration Date |
| 3 | Construction completed | Construction of the Facility is complete and ready to be commissioned. | [insert date] |
| 4 | Commissioning and Hold Point tests completed | All required AEMO commissioning and relevant Network Service Provider hold point tests for the Project have been passed as determined by AEMO and the relevant Network Service Provider (respectively). | [insert date] |
| 5 | Commercial Operation | The Project has passed all requirements set out in this Agreement required for it to achieve Commercial Operation including those identified in clause 7. | COD (Target) |

**Notes to the table:**

(a) The description identifies a set of conditions that must be met in order for the relevant Milestone Event to be achieved.

(b) The Milestone Date (Scheduled) for a particular Milestone Event is the date that is the number of Months after the Commencement Date (**CD**) set out in the ‘Milestone Date (Scheduled) CD + x Months’ column in the above table or the relevant date specified.

(c) The letters N/A means "not applicable".

(d) The Milestone Events must be achieved sequentially. It is a precondition to achieving a Milestone Event that all other Milestone Events which appear above it in the table above have also been achieved.

1. – Payment Mechanism
   1. Definitions

In this Agreement, unless the context otherwise requires:

1. **Adjusted Net Operational Revenue** has the meaning given in section 11.
2. **Aggregate Annual Rebate** has the meaning given in section 8.
3. **Annual Reconciliation Payment** has the meaning given in section 6.
4. **Annual Revenue Sharing Amount** has the meaning given in section 10.
5. **Annual Support Amount** has the meaning given in section 9.
6. **Availability Rebate** has the meaning given in section 4.1.
7. **Availability Rebate Percentage** has the meaning given in section 4.2.
8. **Deemed Availability Period** has the meaning given in section 4.3(b).
9. **Equivalent Availability Factor** means the amount determined in accordance with section 4.3.
10. **Net Annual Payment** has the meaning given in section 7.
11. **Quarterly Payment** means the amount determined in accordance with section 3.
12. **Revenue Ceiling Sharing Percentage** means 50%.
13. **Revenue Floor Support Percentage** means 90%.
14. **Storage Capacity Rebate** means the rebate determined or calculate in accordance with sections 5.1 and 5.2.
15. **Storage Capacity Rebate Percentage** means the percentage calculated in accordance with section 5.3.
16. **Tested Storage Capacity** has the meaning given under section 5.4(c)(iv).
    1. Support payments
       * 1. In respect of each Support Year during the Support Period, the Commonwealth agrees to pay to the Operator in accordance with the terms of this Agreement:
            1. each Quarterly Payment; and
            2. any positive Annual Reconciliation Payment.
         2. In respect of each Support Year during the Support Period, the Operator agrees to pay to the Commonwealth in accordance with the terms of this Agreement the absolute value of any negative Annual Reconciliation Payment.
    2. Quarterly Payment
       1. Quarterly Payment Calculation

The Quarterly Payment for each Quarter of a Support Year (other than the last Quarter) is calculated as follows:

* + - 1. if Iq < NSY / 4, the Commonwealth must pay to the Operator the amount calculated as follows:

**Bq = Min((NSY/4 – Iq) x 0.9, HSY/4)**

* + - 1. if Iq > KSY/ 4, the Operator must pay to the Commonwealth the amount calculated as follows:

**Bq = Min((Iq - KSY/4) x 0.5, HSY/4)**

* + - 1. if NSY/4 < Iq < KSY/4

**Bq = nil.**

Where:

**Bq** = the Quarterly Payment for the relevant Quarter;

**NSY** = the Annual Revenue Floor;

**Iq** = the Adjusted Net Operational Revenue for the relevant Quarter; and

**HSY** = the Annual Payment Cap for the relevant Support Year; and

**KSY** = the Annual Revenue Ceiling.

* + 1. Pro rata calculation

Where any of paragraph (g) or (h) of the definition of Quarter applies, the Quarterly Payment will be adjusted proportionally, having regard to the number of days in the relevant partial quarter as a percentage of the total number of days in the full calendar quarter.

* + 1. No claim

No party will be entitled to make any Claim in connection with the Quarterly Payment in respect of the last Quarter in any Support Year because Claims in respect of that last Quarter in a Support Year are to be made pursuant to section 6.

* 1. Availability Rebate
     1. Calculation of Availability Rebate

The **Availability Rebate** for each Support Year during the Support Period is calculated as follows:

**ESY = PSY x CSY**

Where:

**ESY** = Availability Rebatefor the relevant Support Year;

**PSY** = the Availability Rebate Percentage for the relevant Support Year (as expressed as a percentage); and

**CSY** = the Annual Support Amount for the relevant Support Year (in $).

* + 1. Calculation of Availability Rebate Percentage

The **Availability Rebate Percentage** for each Support Year during the Support Period is calculated as follows:

**PSY = EAT - EAFSY**

Where:

**PSY =** the Availability Rebate Percentage for the relevant Support Year (expressed as a percentage);

**EAT =** the Equivalent Availability Threshold being 90%; and

**EAFSY =** the Equivalent Availability Factor of the Facility for the relevant Support Year (which is a number but that number shall be deemed to be a percentage for the purpose of this clause 4.2),

provided that:

* + - 1. if the Availability Rebate Percentage for the relevant Support Year is less than 0%, the Availability Rebate Percentage for that Support Year will be deemed to be 0%; and
      2. if the Equivalent Availability Factor (expressed as a percentage) for the relevant Support Year is less than 10%, the Availability Rebate Percentage for that Support Year will be deemed to be 100%.
    1. Calculation of Equivalent Availability Factor
       1. Subject to section 4.3(b), the Equivalent Availability Factor (expressed as a percentage) of the Facility for a Support Year is calculated in accordance with the first formula set out in paragraph 8.11 of IEEE 762-2006, provided that:
          1. a reference to “generation” is taken to be a reference to “export capability”; and
          2. a reference to “generating unit” is taken to be the Facility.
       2. If the Rated Capacity is impacted during a period as a direct result of:
          1. any Project Force Majeure Event subsisting during the relevant Operations Year, for which the Operator is entitled to an adjustment or relief pursuant to this Agreement and which the Operator has notified the Commonwealth of in accordance with clause 19; or
          2. a direction or instruction given by AEMO (in its capacity as a market body) under the National Electricity Rules that:

relates to the condition or capacity of the transmission network or the testing or operation of the Facility; and

was not issued as a response to or as a result of any breach or wrongful act or omission of the Operator or its Associates,

(**Deemed Availability Period**), that period will be disregarded for the purpose of calculating the Equivalent Availability Factor for the Project.

* 1. Storage Capacity Rebate
     1. Determination of Storage Capacity Rebate
        1. Within 20 Business Days after the date on which the Commonwealth receives the Annual Storage Capacity Report in respect of a Support Year, the Commonwealth must:
           1. notify the Operator that the Commonwealth agrees with the Storage Capacity Rebate set out in the Annual Storage Capacity Report; or
           2. notify the Operator that the Commonwealth disputes the Storage Capacity Rebate set out in the Annual Storage Capacity Report.
        2. If:
           1. the Commonwealth notifies the Operator that the Commonwealth agrees with the Storage Capacity Rebate set out in the Annual Storage Capacity Report; or
           2. the Commonwealth does not provide any notice under section 5.1(a) within the timeframe required by that section,

the Storage Capacity Rebate set out in the Annual Storage Capacity Report will be binding on the parties.

* + - 1. If the Commonwealth notifies the Operator that it disputes the Storage Capacity Rebate, and it wishes to progress the Dispute, it must refer the matter for determination by an Independent Expert under clause 35.6.
      2. If the Operator fails to provide the Commonwealth with that Annual Storage Capacity Report in accordance with section 32.3(b), the Commonwealth may at its absolute discretion take any one or more of the following steps:
         1. procure that Annual Storage Capacity Report the report referred to in section 5.1 itself, in which case the Operator must pay the Commonwealth within 20 Business Days after receipt of a request to do so, the costs incurred by the Commonwealth in obtaining that report; and
         2. after providing the Operator with a notice which allows the Operator a further 20 Business Days from receipt of that notice to provide the Annual Storage Capacity Report to the Commonwealth, if the Operator fails to provide that Annual Storage Capacity Report within that further 20 Business Days, the Commonwealth may suspend all payments which it is obliged to pay to the Operator until that Annual Storage Capacity Report is provided to the Commonwealth or terminate this Agreement by provision of a further notice to the Operator and this Agreement will terminate on the date set out in that notice and that termination will be deemed to be a termination pursuant to clause 22.2.
    1. Calculation of Storage Capacity Rebate

The **Storage Capacity Rebate** for a Support Year is calculated as follows:

**GSY = CSY x SCPSY**

where:

**GSY** = the Storage Capacity Rebate for the Support Year (in $);

**CSY** = the Annual Support Amount for the relevant Support Year (in $); and

**SCPSY** = the Storage Capacity Rebate Percentage for the Support Year (expressed as a percentage).

* + 1. Calculation of Storage Capacity Rebate Percentage

The Storage Capacity Rebate Percentage for a Support Year is calculated as follows:

**SCPSY = (SCSY - MSOC - TSCSY) / (SCSY - MSOC)**

where:

**SCPSY** = the Storage Capacity Rebate Percentage for the Support Year (expressed as a percentage);

**SCSY** = the Storage Capacity for that Support Year;

**MSOC** = the Minimum State of Charge; and

**TSCSY** = the Tested Storage Capacity as determined under section 5.4,

provided that if the Storage Capacity Rebate Percentage is less than 0% then it will be deemed to be 0%.

* + 1. Determination of Tested Storage Capacity
       1. In the last Quarter of a Support Year, the Operator must conduct a Storage Capacity test in accordance with this section 5.4.
       2. The Operator must use reasonable endeavours to undertake the Storage Capacity test at a time that is likely to maximise revenue.
       3. During the Storage Capacity test:
          1. the Operator will charge the Facility until it reaches the Storage Capacity for that Support Year or the available charge power (as reported by the Project’s SCADA system) is zero;
          2. the Operator will discharge the Facility for the Minimum Hours at the Maximum Capacity for that Support Year;
          3. all auxiliary loads must be operating normally and not restricted; and
          4. the **Tested Storage Capacity** is the quantity of electricity discharged by the Facility (in MWh) during the Minimum Hours as measured at the AC side of the Connection Point.
       4. No adjustments will be made for ambient temperature. **[Drafting note: given the Operator has a three month window to run the test it is not proposed to include testing conditions / limitations on the basis that the Operator can choose one or more times to run the test when conditions are appropriate]**
       5. The Operator must include full details of the Storage Capacity test in the Annual Storage Capacity Report, including:
          1. the ambient temperature;
          2. the power at the Connection Point during the Minimum Hours;
          3. auxiliary load use;
          4. the state of charge during the Minimum Hours; and
          5. the Tested Storage Capacity.

**[Drafting note: a Storage Capacity Rebate may not be appropriate for all projects and may be deleted depending on the technology type bid by a Proponent]**

* 1. Annual Reconciliation Payment
     1. Annual Reconciliation Payment Calculation

The **Annual Reconciliation Payment** for each Support Year during the Support Period is calculated as follows:

**ASY = BSY - ∑ Bq**

Where:

**ASY** = the Annual Reconciliation Payment for the relevant Support Year;

**BSY** = the Net Annual Payment for the relevant Support Year; and

**∑ Bq =** the aggregate of the Quarterly Payments to which the Operator is entitled for the first three Quarters of the relevant Support Year.

* + 1. Pro rata calculation

Where any of paragraphs (a) and (c) of the definition of Support Year apply, the Annual Revenue Floor and Annual Revenue Ceiling will be adjusted proportionally, having regard to the number of days in the relevant partial year as a percentage of the total number of days in a full calendar year.

* 1. Calculation of Net Annual Payment

The **Net Annual Payment** for each Support Year during the Support Period is calculated as follows:

**BSY = CSY - DSY - ZSY**

Where:

**BSY =** the Net Annual Payment for the relevant Support Year;

**CSY =** the Annual Support Amount for the relevant Support Year (in $);

**DSY =** the Annual Revenue Sharing Amount for the relevant Support Year; and

**ZSY =** the Aggregate Annual Rebate for the relevant Support Year.

* 1. Calculation of Aggregate Annual Rebate

The **Aggregate Annual Rebate** for a Support Year is calculated as:

**ZSY = ESY + GSY**

where:

**ZSY** = the Aggregate Annual Rebate for the relevant Support Year;

**ESY** = the Availability Rebate;

**GSY** = the Storage Capacity Rebate,

each for the relevant Support Year, provided that if the Aggregate Annual Rebate is greater than CSY then it will be deemed to be equal to CSY.

* 1. Calculation of Annual Support Amount

The **Annual Support Amount** for each Support Year is calculated as follows:

**CSY = Min((NSY - ISY) x J, HSY)**

Where:

**CSY** = the Annual Support Amount for the relevant Support Year;

**NSY =** the Annual Revenue Floor;

**HSY** = the Annual Payment Cap;

**ISY** = the Adjusted Net Operational Revenue; and

**J** = the Revenue Floor Support Percentage,

each for the relevant Support Year provided that if the Annual Support Amount is less than zero, then it will be deemed to be zero.

* 1. Calculation of Annual Revenue Sharing Amount

The **Annual Revenue Sharing Amount** for each Support Year is calculated as follows:

**DSY = Min((ISY - KSY) x L, HSY)**

Where:

**DSY =** the Annual Revenue Sharing Amount for the relevant Support Year;

**ISY =** the Adjusted Net Operational Revenue;

**HSY =** the Annual Payment Cap;

**KSY =** the Annual Revenue Ceiling; and

**L** = the Revenue Ceiling Sharing Percentage,

each for the relevant Support Year provided that, if the Annual Revenue Sharing Amount is less than zero then it will be deemed to be zero.

* 1. Calculation of Adjusted Net Operational Revenue

The **Adjusted Net Operational Revenue** for each Support Year during the Support Period is calculated as follows:

**ISY = XSY x CP**

Where:

**ISY** = the Adjusted Net Operational Revenue;

**XSY** = the Net Operational Revenue; and

**CP** = the Contracted Percentage (expressed as a percentage),

each for the relevant Support Year provided that, if the Adjusted Net Operational Revenue is less than zero then it will be deemed to be zero.

1. – Termination Payments
   1. Early Termination Payment

The Early Termination Payment is calculated as follows in the periods identified:

1.1 For the period from and including the Signing Date to the immediately prior to the COD, the Early Termination Payment is $[insert amount].

**[Drafting note: for the purpose of liquidating the amount payable as an Early Termination Payment for termination by the Commonwealth for default prior to the COD, the Commonwealth has calculated its genuine pre-estimate of its loss at greater than $4 million. However, to recognise that Facilities will be of different Maximum Capacities, the Commonwealth is willing to set the amount to which it is entitled under this section at a lower amount for value for money reasons. The amount will be calculated using the following formula: $20,000 per MW multiplied by the Maximum Capacity, up to a maximum amount of $4,000,000. The shortlisted Proponent is required to provide that amount here as part of its Financial Value Bid in Stage B of the Tender Process.]**

1.2 For the period from and including the COD to the end of the Term, the Early Termination Payment is calculated as follows:

ETA = A + B + C + D + E - F

Where:

ETA = the Early Termination Payment

A = the aggregate of the net increase in the Annual Support Amount to which the Commonwealth is exposed under a replacement agreement on substantially the same terms as this Agreement with a new operator over and above the Annual Support Amount to which the Commonwealth would have been exposed under this Agreement had it not been terminated (assuming for that comparison that the Commonwealth would be exposed to pay the Operator the maximum Annual Support Amount under this Agreement and the new operator the maximum Annual Support Amount under the new agreement in each case as determined over the remaining Support Years over the remainder of the Term under this Agreement determined on the assumption that this Agreement has not been terminated) which for the purpose of this section 1 is calculated as follows:

A = (∑MCRSY) x 10%

Where ∑MCRSY = the sum of the maximum Annual Support Amounts over the remaining Support Years in the remainder of the Term under this Agreement, determined on the assumption that this Agreement has not been terminated;

B = the reasonable and proper internal and external costs incurred by or on behalf of the Commonwealth in carrying out a tender to identify another project to replace the Maximum Capacity of the Facility which for the purpose of this section 1 is fixed at $15 million (Indexed);

C = any Liability of the Operator to the Commonwealth under this Agreement as at the date on which this Agreement is terminated;

D = any other additional costs reasonably incurred by the Commonwealth as a direct result of the termination of this Agreement;

E = any gains which have accrued, or will accrue to the Operator (and reductions in the Liability of the Operator to the Commonwealth) in each case as a result of the termination of this Agreement;

F = any Liability of the Commonwealth to the Operator under this Agreement as at the date on which this Agreement is terminated.

1.3 Where the outcome of the calculation of the Early Termination Payment is a negative number, the Early Termination Payment will be deemed to be zero. In calculating items A to F, there will be no double counting of amounts.

1.4 For the purpose of this section 1 of Schedule 5, the Operator must continue to provide to the Commonwealth such information at the times requested which will enable the Commonwealth (or its nominee) to calculate the Early Termination Payment.

* 1. Fixed Termination Payment

2.1 The Fixed Termination Payment is calculated as follows:

FTA = A - C - E - F + G

Where:

FTA = the Fixed Termination Payment

A = the aggregate of the maximum Annual Support Amount for each of the remaining Support Years over the remainder of the Term provided however that for the basis of determining that aggregate amount, this Agreement must be read on the assumption that it has not been terminated;

C = any Liability of the Operator to the Commonwealth under this Agreement as at the date on which this Agreement is terminated;

E = any gains which have accrued, or will accrue to the Operator (and reductions in the Liability of the Operator to the Commonwealth) in each case as a result of the termination of this Agreement;

F = the aggregate of any insurance proceeds related to loss of revenue or profit or to business interruption (howsoever named) received or receivable (or which should have been received) by the Operator or any of its Related Body Corporate regarding the Project (other than those insurance proceeds required to be applied to repair or reinstate the Facility or to indemnify a third party);

G = any Liability of the Commonwealth under this Agreement as at the date on which this Agreement is terminated (other than the Liability of the Commonwealth to the Operator regarding this Fixed Termination Payment.

2.2 Where the outcome of the calculation of the Fixed Termination Payment is a negative number, the Fixed Termination Payment will be deemed to be zero. In calculating items A to G, there will be no double counting of amounts.

2.3 For the purpose of this section 2 of Schedule 5, the Operator must continue to provide to the Commonwealth such information at the times requested which will enable the Commonwealth to calculate the Fixed Termination Payment.

1. – Knowledge Sharing Plan
   1. Knowledge sharing context

The Commonwealth may use the Knowledge Sharing Deliverables for the following purposes:

* + - 1. to perform the Commonwealth's obligations under this Agreement;
      2. to monitor and evaluate the performance of the Commonwealth's Capacity Investment Scheme;
      3. to accurately inform and engage key stakeholders on the following aspects of electricity storage projects in Australia:
         1. actual CAPEX and OPEX costs for such projects, including pathways for cost reductions particularly around risk premiums applied by suppliers as they build experience and confidence in these types of projects;
         2. challenges and lessons learned about the integration of the various systems and technologies at commercial scale;
         3. what commercial, regulatory and social barriers the Project encounters, and how they are effectively addressed;
         4. the capabilities, depth and maturity of the various supply chains required to deliver this Project;
         5. how social licence and genuine support for the Project is established and maintained with relevant communities; and
         6. how the actual operation of the completed Project compares to the design forecasts, and how this could be optimised for future projects.
  1. Knowledge Sharing Deliverables

All deliverables are to be prepared to a standard acceptable to the Commonwealth and, where relevant, reflect any guidelines provided by the Commonwealth relating to the preparation and delivery of Knowledge Sharing Deliverables.

| No | Knowledge Sharing Deliverable | Purpose | Frequency | When? | Public information or confidential information | Content and delivery |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Annual Survey | Efficient qualitative and quantitative data gathering. The Commonwealth may use this information in anonymised portfolio analysis and reporting.  Share key lessons from the Project, and implications for industry. This should focus in particular on the Project’s experiences during the planning, construction, commissioning and operations phases.  The Operator to provide a set of clearly defined and consistent data metrics, over time, to allow the performance of the Project to be analysed against forecasts and compared to other relevant projects. | Annually | Undertaken during the first Quarter commencing on 1 July in each year of the Term | Confidential | Commonwealth to provide survey template which the Operator must complete |
| 2 | Site Visit | On ground experience and demonstration of Facility. | Every 3 years | Once in each 3 year period commencing at COD until the end of the Operations Period and on the Expiry Date. | Public | In person tour of the Facility. |
| 3 | Technology and Market Report | To document and disseminate the plans for the Project and the market context within which it has been developed. This should provide a valuable and credible confirmation of the current state of play for key stakeholders.  The Commonwealth will notify the Operator of the key questions to be answered in each report at least six months prior to the due date of the report. | At the time requested by the Commonwealth provided however the Commonwealth may only issue two such requests and those requests may only be made during the Operations Period. | Commonwealth to give minimum 6-months’ notice to provide report | Public | Written report which comprehensively responds to each of the key questions provided by the Commonwealth and such report must be prepared in accordance with Good Industry Practice.  Confidential Information to be included in an addendum to the report |
| 4 | Support Mechanism Reflection | Report outlining how the support mechanism has or has not helped the Project to information future market design | At the time requested by the Commonwealth provided however the Commonwealth may only issue two such requests and those requests may only be made during the Operations Period. | Commonwealth to give minimum 6-months’ notice to provide report | Confidential Information provided however that the Commonwealth may publish such information and commentary on that information where it is anonymised or deidentified and commentary | Written report which comprehensively outlines how this Agreement has or has not helped the Project, prepared in accordance with Good Industry Practice.  Confidential Information to be included in an addendum to the report |

1. – Key Subcontractors

The following Subcontractors are Key Subcontractors for the purpose of this Agreement:

**[Drafting note: the shortlisted Proponent is required to complete the table below as part of its Financial Value Bid in Stage B of the Tender Process. If a shortlisted Proponent does not complete the table below, it will deemed to have not requested preapproval for any of its Key Subcontractors]**

|  | Key Subcontractor and Address | Relevant goods, services or work | Engaged By | Country of Headquarters and from which the relevant goods, services or work will be provided |
| --- | --- | --- | --- | --- |
| [# insert] | [insert] | [insert] | [insert] | [insert] |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

1. – Social Licence Commitments

**[Drafting note: the shortlisted Proponent is required to complete and provide an updated version of this Schedule 8 as part of both this and MC 7 Returnable Schedule for its Financial Value Bid in Stage B of the Tender Process.]**

* 1. Definitions

In this Agreement, unless the context otherwise requires:

**Apprentice** means a person undertaking an approved structured employment-based training program (apprenticeship) under a registered training contract that leads to a nationally recognised qualification who is working on the Project.

**First Nations Businesses** means a business that is at least 50 per cent First Nations -owned and is recognised as a First Nations business through an appropriate organisation, such as Supply Nation or a Victorian or South Australian Indigenous Chamber of Commerce or equivalent.

**Full-time Equivalent (FTE)** means the estimated FTE number for a group which is calculated as estimated working hours of a group / Working days x 7.5 hours.

**Local** means Australia and New Zealand.

**Local Content** means goods, services and labour procured from Australia and New Zealand.

**Social Licence Commitments** means the social licence commitments described in section 2 below.

**Training** means undertaking an accredited vocational education and training (VET) or nationally recognised professional qualifications that meet the needs of the Project and can be full or part qualifications (such as one or more units of competency). It may be subsidised by government funding or through a fee-for service arrangement.

* 1. Social Licence Commitments

The Operator must provide the shared community benefits to the community beneficiaries to at least the value identified and within the timeframes specified in Table 1.

**Table 1 – Shared community benefits**

|  |  |  |
| --- | --- | --- |
| **Shared community benefit (including community beneficiaries)** | **Period over which the shared community benefits will be delivered to community beneficiaries** | **Aggregate value of shared community benefits to community beneficiaries (Real $A as at the Tender Date)** |
| Example Commitment 1.1 | Between [insert date] and [insert date] | [insert] |
| Example Commitment 1.2 | Between [insert date] and [insert date] | [insert] |
| Example Commitment 1.3 | Between [insert date] and [insert date] | [insert] |
| Example Commitment 1.4 | Between [insert date] and [insert date] | [insert] |
| Example Commitment 1.5 | Between [insert date] and [insert date] | [insert] |
| Example Commitment 1.6 | Between [insert date] and [insert date] | [insert] |

The Operator must provide Local employment to at least the value identified and within the timeframes specified in Table 2.

**Table 2 – Commitments to Local employment**

|  |  |  |
| --- | --- | --- |
| **Commitment to Local employment** | **Period over which commitments to Local employment will be delivered** | **Aggregate value of commitment to Local employment (Real $A as at the Tender Date)** |
| Example Commitment 2.1 | Between [insert date] and [insert date] | [insert] |
| Example Commitment 2.2 | Between [insert date] and [insert date] | [insert] |
| Example Commitment 2.3 | Between [insert date] and [insert date] | [insert] |

The Operator must use Local Content to at least the value identified and within the timeframes specified in Table 3.

**Table 3 – Commitments to Local Content**

|  |  |  |
| --- | --- | --- |
| **Commitment to Local Content** | **Period over which commitments to Local Content will be delivered** | **Aggregate value of commitment to Local Content (Real $A as at the Tender Date)** |
| Pre-COD | Between [insert date] and [insert date] | [insert] |
| Post-COD | Between [insert date] and [insert date] | [insert] |

The Operator must provide the commitments to First Nations to at least the values specified in Table 4.

**Table 4 – Commitments to First Nations**

|  |  |  |
| --- | --- | --- |
| **Commitments to First Nations** | **Period over which that value will be provided (start and end date)** | **Aggregate value of commitment to First Nations (Real $A as at the Tender Date)** |
| Subcontracted First Nations participation | Between [insert date] and [insert date] | [insert] |
| Workforce First Nations participation | Between [insert date] and [insert date] | [insert] |
| First Nations Training and capacity building | Between [insert date] and [insert date] | [insert] |
| Example Commitment 4.4 | Between [insert date] and [insert date] | [insert] |
| Example Commitment 4.5 | Between [insert date] and [insert date] | [insert] |
| Example Commitment 4.6 | Between [insert date] and [insert date] | [insert] |

1. – Form of Tripartite Deed



|  |  |
| --- | --- |
|  | Tripartite Deed  Capacity Investment Scheme  [Insert Facility name]  Dated [Insert]  The Commonwealth of Australia represented by the Department of Climate Change, Energy, the Environment and Water (**Commonwealth**)  [Insert name] (**Operator**)  [Insert name] (**Security Trustee**)  **[Important Notice**  This is a copy of the draft Tripartite Deed provided in connection with the Capacity Investment Scheme tender process being conducted by the Australian Government pursuant to the Capacity Investment Scheme South Australia and Victoria Tender Guidelines issued by the Australian Government on 15 December 2023 (**Tender Guidelines**). Capitalised terms in this Important Notice have the meaning in the Tender Guidelines.  The draft Project Documents are not an offer by the Australian Government or AEMO to enter into those documents with any entity which receives a copy of those documents and does not impose any legal commitment on the Australian Government or AEMO.  The provision of the draft Project Documents to Proponents is not intended to create legal rights for any party or to form a legally binding relationship, obligation or commitment by or involving the Australian Government or AEMO. Recipients of the draft Project Documents should not rely on its or their contents as the sole basis for making any financial, investment or business decisions. The Australian Government reserves the right to withdraw or amend the draft Project Documents at any time.] |

[Details 115](#_Toc165647660)

[Parties 115](#_Toc165647661)

[Background 115](#_Toc165647662)

[Agreed terms 116](#_Toc165647663)

[1. Definitions and interpretation 116](#_Toc165647664)

[1.1 Definitions 116](#_Toc165647665)

[1.2 Terms defined in the CISA 117](#_Toc165647666)

[1.3 General interpretation 117](#_Toc165647667)

[1.4 Order of precedence 118](#_Toc165647668)

[1.5 Project Documents 118](#_Toc165647669)

[1.6 Commonwealth's rights, duties and functions 118](#_Toc165647670)

[1.7 Reasonable endeavours of the Commonwealth 119](#_Toc165647671)

[1.8 Prior approval or consent 119](#_Toc165647672)

[1.9 Action without delay 119](#_Toc165647673)

[1.10 Provisions limiting or excluding Liability, rights or obligations 119](#_Toc165647674)

[1.11 Relationship of the parties 119](#_Toc165647675)

[1.12 Capacity of Security Trustee 120](#_Toc165647676)

[1.13 Replacement of Security Trustee 121](#_Toc165647677)

[1.14 Consideration 121](#_Toc165647678)

[1.15 Condition precedent 121](#_Toc165647679)

[2. Representations and warranties 121](#_Toc165647680)

[2.1 Operator and Security Trustee representations and warranties 121](#_Toc165647681)

[2.2 Commonwealth representations and warranties 122](#_Toc165647682)

[2.3 Reliance 122](#_Toc165647683)

[2.4 Repetition 122](#_Toc165647684)

[3. Consents and undertakings 122](#_Toc165647685)

[3.1 Consent by the Operator 122](#_Toc165647686)

[3.2 Consent and undertakings by the Commonwealth 122](#_Toc165647687)

[3.3 Notification by Security Trustee 123](#_Toc165647688)

[4. Termination Events – cure and termination 123](#_Toc165647689)

[4.1 Termination Event Notices to Security Trustee 123](#_Toc165647690)

[4.2 Cure rights 123](#_Toc165647691)

[4.3 Restriction on Termination 123](#_Toc165647692)

[4.4 Termination by the Commonwealth 124](#_Toc165647693)

[4.5 Rights and obligations not affected 125](#_Toc165647694)

[4.6 Deemed cure 125](#_Toc165647695)

[5. Transfer following enforcement 125](#_Toc165647696)

[5.1 Transfer 125](#_Toc165647697)

[5.2 Transfer documentation 125](#_Toc165647698)

[6. GST 126](#_Toc165647699)

[6.1 Definitions and interpretation 126](#_Toc165647700)

[6.2 GST exclusive consideration 126](#_Toc165647701)

[6.3 No taxable supply 126](#_Toc165647702)

[6.4 GST gross-up 126](#_Toc165647703)

[6.5 Non-monetary consideration 126](#_Toc165647704)

[6.6 Payments and reimbursements 126](#_Toc165647705)

[6.7 Adjustments 126](#_Toc165647706)

[6.8 No Partnership 127](#_Toc165647707)

[7. Confidentiality 127](#_Toc165647708)

[7.1 Confidential Information not to be Disclosed 127](#_Toc165647709)

[7.2 Exceptions to obligations of Confidentiality 127](#_Toc165647710)

[7.3 Publicity 128](#_Toc165647711)

[8. Assignment and Novation 128](#_Toc165647712)

[8.1 Assignment or Novation by the Operator 128](#_Toc165647713)

[8.2 Assignment or Novation by the Commonwealth 129](#_Toc165647714)

[8.3 Non-compliance and release 129](#_Toc165647715)

[9. Governing Law 130](#_Toc165647716)

[9.1 Governing Law and jurisdiction 130](#_Toc165647717)

[9.2 Serving documents 130](#_Toc165647718)

[10. Notices and other communications 130](#_Toc165647719)

[10.1 Form 130](#_Toc165647720)

[10.2 Delivery 130](#_Toc165647721)

[10.3 When effective 130](#_Toc165647722)

[10.4 When taken to be received 130](#_Toc165647723)

[10.5 Receipt outside business hours 131](#_Toc165647724)

[11. General 131](#_Toc165647725)

[11.1 Duration of this Deed 131](#_Toc165647726)

[11.2 Variation and waiver 131](#_Toc165647727)

[11.3 Consents, approvals or waivers 131](#_Toc165647728)

[11.4 Discretion in exercising rights 131](#_Toc165647729)

[11.5 Partial exercising of rights 131](#_Toc165647730)

[11.6 Remedies cumulative 131](#_Toc165647731)

[11.7 Supervening Law 131](#_Toc165647732)

[11.8 Counterparts 132](#_Toc165647733)

[11.9 Entire agreement 132](#_Toc165647734)

[11.10 Expenses and no liability for loss 132](#_Toc165647735)

[11.11 Rules of construction 132](#_Toc165647736)

[11.12 Severability 132](#_Toc165647737)

[11.13 Survival 132](#_Toc165647738)

[11.14 Proportionate liability 133](#_Toc165647739)

[11.15 Limitation of the Commonwealth liability 133](#_Toc165647740)

[11.16 Further steps 133](#_Toc165647741)

[Signing page 134](#_Toc165647742)

Details

|  |  |
| --- | --- |
| Date |  |

Parties

|  |  |
| --- | --- |
| Name | The Commonwealth of Australia represented by the Department of Climate Change, Energy, the Environment and Water |
| Short form name | **Commonwealth** |
| Notice details | [insert address]  Email: [insert] |

|  |  |
| --- | --- |
| Name | [insert name] (ACN/ABN [insert]) |
| Short form name | **Operator** |
| Notice details | [insert address]  Email: [insert] |

|  |  |
| --- | --- |
| Name | [insert name] (ACN/ABN [insert]) |
| Short form name | **Security Trustee** |
| Notice details | [insert address]  Email: [insert] |

Background

1. The Commonwealth and the Operator have entered into the CISA in connection with the Facility and the Project.
2. The Operator has requested that the Beneficiaries provide financial accommodation to the Operator or its Related Bodies Corporate to enable it to carry out the Project.
3. The provision of financial accommodation is conditional on, among other things:
   1. the Operator granting Security to Security Trustee over its rights under the Agreement; and
   2. the Operator and the Commonwealth entering into this Deed with Security Trustee.

Agreed terms

* 1. Definitions and interpretation
     1. Definitions

1. Unless the contrary intention appears, these meanings apply:
2. **Beneficiary** has the meaning it has in the Security Trust Deed.
3. **CISA** means the long-term revenue support agreement dated [insert] between the Commonwealth and the Operator with respect to the Project.
4. **Controller** has the meaning it has in the Corporations Act.
5. **Cure Period Start Date** means, for a Termination Event which the Commonwealth is relying on for the purposes of clause 4.4 (Termination), the date on which all of the following are satisfied:
   1. the Termination Event which the Commonwealth is relying on has occurred; and
   2. the Commonwealth has given Security Trustee:
      1. a copy of the Termination Event Notice (if any) it has given to the Operator which states that the Termination Event which the Commonwealth is relying on has occurred; or
      2. if the Commonwealth has not given Security Trustee a Termination Event Notice which complies with paragraph (b)(i) above, including for example because it was not required to give such a notice to the Operator under the CISA, it has notified the Operator and Security Trustee of the Termination Event it is relying on (and the notice includes reasonable details of that event); and
   3. all cure periods (if any) specified in, or agreed under, the CISA for that Termination Event have expired or ended.
6. **Details** means the section of this Deed headed “Details”.
7. **Enforcing Party** means Security Trustee or any Controller or attorney appointed under any Security.
8. **[Event of Default** has the meaning given to the term "Event of Default" (howsoever named) in the Security Trust Deed.]
9. **GST Law** has the meaning given to that term in *A New Tax System (Goods and Services Tax) Act 1999* (Cth).
10. **Security** means: [**Drafting note: the Security will be limited to security granted over the Project, the assets of the Operator and any Related Body Corporate established for the Project and the ownership interests in the Operator and those Related Bodies Corporate and will only be to secure debt related to the Project**]
    1. [insert]; and
    2. any other Security Interest granted by or entered into by the Operator or any of its Related Bodies Corporate (whether alone or with other grantors) in favour of Security Trustee (in its capacity as trustee of the Security Trust).
11. **Security Trust** has the meaning it has in the Security Trust Deed.
12. **Security Trust Deed** means the security trust deed executed by Security Trustee before this Deed was signed and which relates to the Security.
13. **Security Trustee** has the meaning it has in the Details.
14. **Terminate** includes terminate, end, close out, determine, rescind, cancel, revoke, repudiate, avoid, release, surrender, forfeit, discharge (other than by performance) or accept the termination, rescission or repudiation of the CISA and includes claiming that an obligation under the CISA is void, voidable or unenforceable.
15. **Termination Event** means each of the events set out in clause 27.2 (Termination by the Commonwealth for Operator Default) of the CISA and for the avoidance of doubt includes those events which are deemed to be a termination pursuant to clause 27.2 (Termination by the Commonwealth for Operator Default) of the CISA.
16. **Termination Event Notice** meansany notice given by the Commonwealth to the Operator notifying the Operator of the occurrence of a Termination Event.
17. **Transferee** has the meaning given in clause 5.1 (Transfer).
    * 1. Terms defined in the CISA

Unless the contrary intention appears, a term which has a defined meaning in the CISA has the same meaning when used in this Deed.

* + 1. General interpretation

Headings are for convenience only and do not affect interpretation. Unless the contrary intention appears, in this Deed:

* + - 1. labels used for definitions are for convenience only and do not affect interpretation;
      2. the singular includes the plural and vice versa and a word indicating gender includes every other gender;
      3. another grammatical form of a defined word or expression has a corresponding meaning;
      4. the meaning of general words is not limited by specific examples introduced by “including”, “for example”, “such as” or similar expressions;
      5. a reference to a Deed also includes any variation, replacement, novation or supplement of it;
      6. a reference to a "**person**" includes an individual, a corporation, a body corporate, a partnership, a joint venture (whether incorporated or unincorporated), an unincorporated association, an Entity, a trust and any Government Agency or any other entity or organisation;
      7. a reference to a particular person includes the person's executors, administrators, successors, permitted substitutes (including persons taking by novation) and assigns and in the case of a trustee, includes any substituted or additional trustee;
      8. unless otherwise indicated:
         1. a reference to a party, clause, Schedule, Annexure or Attachment is a reference to a party, clause, Schedule, Annexure or Attachment of or to this Deed; and
         2. a reference to a section, table, item or part is a reference to the relevant numbered section, table, item or part within the Schedule, Annexure or Attachment (as applicable in which they are located;
      9. a reference to a time of day is to the time in the capital city of the Relevant Jurisdiction;
      10. a reference to dollars, $ or A$ is a reference to the currency of Australia;
      11. a reference to any legislation includes regulations under it and any consolidations, amendments, re-enactments or replacements of any of them;
      12. a reference to “**regulations**” includes instruments of a legislative character under legislation (such as regulations, rules, by- laws, subordinate legislation, ordinances, statutory instruments (however described) and proclamations);
      13. a reference to a group of persons is a reference to any two 3 or more of them jointly and to each of them individually and a reference to an obligation or a liability assumed by, or a right conferred on, two or more persons binds or benefits them jointly and severally;
      14. a reference to any thing (including an amount) is a reference to the whole and each part of it;
      15. a period of time dating from a given day or the day of an act or event is to be calculated exclusive of that day;
      16. if the day on which a party must do something under this Deed is not a Business Day, then the party must do it on the next Business Day;
      17. this Deed is comprised of the Details, the Background, clauses 1 to 11 and any Schedules, Annexures and Attachments to this Deed;
      18. a reference to a right includes any benefit, remedy, function, discretion, authority or power;
      19. where there is a reference to a Government Agency, institute, association or other body referred to in a Project Document which:
          1. is reconstituted, renamed or replaced or if its powers or functions are transferred to, or assumed by, another entity, that Project Document is deemed to refer to that other entity; or
          2. ceases to exist, that Project Document is deemed to refer to the new entity (if any) which serves substantially the same purpose or object as the former entity; and
      20. a reference to “property” or “asset” includes any present or future, real or personal, tangible or intangible property, asset or undertaking and any right, interest or benefit under or arising from it;
      21. a reference to cure includes any deemed cure contemplated or effected by clause 4.6 (Deemed cure);
      22. a reference to remedy, rectify, cure or overcoming the effects of, or similar, includes a reference to any of them; and
      23. a reference to “cure period” includes a reference to any cure, grace, notice or other period or requirement, or similar.
    1. Order of precedence
       1. If there is an ambiguity, inconsistency or discrepancy between this Deed and any other Project Document, then the following order of precedence applies to the extent of any ambiguity, inconsistency or discrepancy:
          1. this Deed;
          2. the CISA; and
          3. the remaining Project Documents (if any).
       2. If any party (other than the Commonwealth) discovers any ambiguity, inconsistency or discrepancy within or between any one or more of the Project Documents, that party must give the other parties notice of such ambiguity, inconsistency or discrepancy within a reasonable time after discovering it.
       3. The resolution of any ambiguity, inconsistency or discrepancy pursuant to this clause 1.4 does not entitle the Operator of the Security Trustee to make any Claim against the Commonwealth and each of the Operator and Security Trustee waives any such right.
    2. Project Documents

The Security Trustee acknowledges that as at the date it signed this Deed, it has received a final signed version of the CISA and it has reviewed the CISA (or is deemed to have received and reviewed the final signed version of the CISA).

* + 1. Commonwealth's rights, duties and functions
       1. Unless otherwise expressly stated in this Deed, nothing in this Deed gives rise to any duty on the part of the Commonwealth to consider interests other than its own interests when exercising any of its rights or carrying out any of its obligations under this Deed.
       2. Notwithstanding anything expressly provided or implied in this Deed to the contrary:
          1. the Commonwealth is not obliged:

to exercise any executive or statutory right, duty or function, or to influence, over-ride, interfere with or direct any part of the Commonwealth or any other Government Agency in the proper exercise and performance of any of its executive or statutory rights, duties or functions;

to develop or implement any new Commonwealth policy or change any Commonwealth policy;

to enact any new legislation or implement a change in Law or make or revoke any regulation including any statutory instrument or delegation;

to provide an interpretation of any legislation, regulation or Commonwealth policy; and

* + - * 1. nothing expressly stated or implied in this Deed has the effect of constraining the Commonwealth or placing any fetter on the Commonwealth's discretion to exercise or not to exercise any of its executive or statutory rights, duties or functions.
    1. Reasonable endeavours of the Commonwealth

In this Deed, a requirement for the Commonwealth to use 'best endeavours', 'reasonable endeavours', 'act reasonably', to not act unreasonably, to act in 'Good Faith' or to take 'reasonable' or 'all reasonable' steps or action, does not require the:

* + - 1. exercise or non-exercise of any executive or statutory discretion, right or power;
      2. development or implementation of any new Commonwealth policy or change in Commonwealth policy;
      3. enactment of any new legislation or making of a change in Law or the making or revocation of any statutory instrument or delegation; or
      4. Commonwealth to act in a way it regards as not in the public interest.
    1. Prior approval or consent

If the Operator is required by this Deed to obtain the Commonwealth's consent or approval to an action, document or thing, unless otherwise expressly stated, that consent or approval must be obtained as a condition precedent to the action, document or thing occurring or coming into effect.

* + 1. Action without delay

Unless there is a provision in this Deed which specifies a period of time in which something must be done by the Operator, all things must be done by the Operator without undue delay.

* + 1. Provisions limiting or excluding Liability, rights or obligations
       1. A right or obligation of the Commonwealth, the Operator or the Security Trustee under this Deed will not limit or exclude any other right or obligation of the Commonwealth, the Operator or the Security Trustee under this Deed unless otherwise expressly stated.
       2. Any provision of this Deed which seeks, either expressly or by implication, to limit or exclude any Liability of a party is to be construed as doing so only to the extent permitted by Law.
    2. Relationship of the parties

Nothing in this Deed:

* + - 1. creates a partnership, joint venture, fiduciary, employment or agency relationship with the Commonwealth; or
      2. imposes any duty of Good Faith on the Commonwealth,

unless otherwise expressly provided.

* + 1. Capacity of Security Trustee
       1. Security Trustee enters into and performs this Deed and the transactions it contemplates only as the trustee of the Security Trust, except where expressly stated otherwise. This applies also in respect of any past and future conduct (including omissions) relating to this Deed or those transactions.
       2. Under and in connection with this Deed and those transactions and conduct:
          1. Security Trustee’s liability (including for negligence) is limited to the extent it can be satisfied out of the assets of the Security Trust. Security Trustee need not pay any such liability out of other assets; and
          2. another party may only do the following with respect to Security Trustee (but any resulting liability remains subject to the limitations in this clause):

prove and participate in, and otherwise benefit from, any form of insolvency administration of Security Trustee but only with respect to Security Trust assets;

exercise rights, powers and remedies with respect to Security Trust assets, including set-off;

enforce its security (if any) and exercise contractual rights; and

bring any proceedings against Security Trustee seeking relief or orders that are not inconsistent with the limitations in this clause,

and may not:

bring other proceedings against Security Trustee;

take any steps to have Security Trustee placed in any form of insolvency administration or to have a receiver or receiver and manager appointed; or

seek by any means (including set-off) to have a liability of Security Trustee to that party (including for negligence) satisfied out of any assets of Security Trustee other than Security Trust assets.

* + - 1. Clauses 1.12(a) and 1.6(b) apply despite any other provision in this Deed but do not apply with respect to any liability of Security Trustee to another party (including for negligence):
         1. to the extent that Security Trustee has no right or power to have Security Trust assets applied towards satisfaction of that liability, or its right or power to do so is subject to a deduction, reduction, limit or requirement to make good, in either case because Security Trustee’s behaviour was beyond power or improper in relation to the Security Trust; or
         2. under any provision which expressly binds Security Trustee other than as trustee of the Security Trust (whether or not it also binds it as trustee of the Security Trust).
      2. The limitation in clause 1.12(b)(i) is to be disregarded for the purposes (but only for the purposes) of the rights and remedies described in clause 1.6(b)(b)(ii), and interpreting this Deed and any security for it, including determining the following:
         1. whether amounts are to be regarded as payable (and for this purpose damages or other amounts will be regarded as a payable if they would have been owed had a suit or action barred under clause 1.12(b)(ii) been brought);
         2. the calculation of amounts owing; or
         3. whether a breach or default has occurred,

but any resulting Liability will be subject to the limitations in this clause.

* + 1. Replacement of Security Trustee
       1. If Security Trustee is replaced as trustee under the Security Trust Deed, then:
          1. Security Trustee may assign, transfer or novate (or do any combination of these things in respect of) its rights and obligations under this Deed to the replacement trustee if it has all the required qualifications, consents, authorisations and approvals necessary to carry on a business similar to the Security Trustee;
          2. Security Trustee may be released from its obligations under this Deed when the replacement security trustee provides, in a form and substance reasonably acceptable to the Operator and the Commonwealth:

copies of a deed poll under which the replacement security trustee undertakes to be bound by this Deed as if it were the Security Trustee with effect from the date of that deed poll; and

evidence that it has undertaken to be bound by each other document to which the Security Trustee is bound in its capacity as security trustee; and

* + - * 1. the other parties agree to co-operate and to execute such documents as are reasonably necessary to give effect to any such assignment, transfer or novation (or any combination of them).
      1. The Operator must pay the Commonwealth’s legal and other costs and expenses incurred in complying with this clause 1.13.
    1. Consideration

Each party acknowledges entering into this Deed and incurring obligations and giving rights under this Deed for valuable consideration received from each other party.

* + 1. Condition precedent
       1. The provisions of this Deed (other than this clause 1 and clauses 6, 7, 9 and 11) are of no force or effect unless and until the Commencement Date occurs.
       2. The condition precedent in clause 1.15(a) is for the benefit of each party to this Deed and may only be waived by notice in writing given by each party.
  1. Representations and warranties
     1. Operator and Security Trustee representations and warranties

Each party represents and warrants in respect of itself for the benefit of the other parties as follows:

* + - 1. (**corporate existence**) in the case of the Operator and the Security Trustee only, it is duly registered and validly existing under the laws of its place of incorporation and has power and authority to own its assets and carry on its business as it is now being conducted;
      2. (**power and authority**) it has full power and authority to enter into, deliver and perform its obligations under this Deed and carry out the transactions contemplated by this Deed;
      3. (**execution authorised**) it has taken all necessary action to authorise the execution, delivery and the performance of this Deed;
      4. (**binding nature**) this Deed constitutes its legal, valid and binding obligations, enforceable in accordance with its terms;
      5. (**no breach**) the execution, delivery and performance of this Deed does not and will not violate, breach or result in a contravention of:
         1. any Law, or any document or agreement to which it is a party or which is binding on it or any of its assets;
         2. any authorisation, ruling, judgment, order or decree of any Government Agency;
         3. in the case of the Operator and Security Trustee only, the constitutional documents of that party; or
         4. any Security Interest by which it is bound; and
      6. (**no insolvency**) in the case of the Operator and the Security Trustee only, it is not subject to an Insolvency Event.
    1. Commonwealth representations and warranties

The Commonwealth represents and warrants for the benefit of the other parties as follows:

* + - 1. (power and authority) it has full power and authority to enter into, deliver and perform its obligations under this Deed and carry out the transactions contemplated by this Deed; and
      2. (binding nature) this Deed constitutes its legal, valid and binding obligations, enforceable in accordance with its terms.
    1. Reliance

The Commonwealth acknowledges that the Beneficiaries may provide financial accommodation to the Operator or any of its Related Bodies Corporate in reliance on the representations and warranties made by the Operator in clause 2.1 (Operator and Security Trustee representations and warranties).

* + 1. Repetition

Unless expressly stated otherwise, each representation and warranty given by the Operator and the Security Trustee is deemed to be given on the date on which the last party signs this deed and repeated on each day thereafter until it is terminated with references to the facts and circumstances then subsisting.

* 1. Consents and undertakings
     1. Consent by the Operator

The Operator:

* + - 1. consents to this Deed; and
      2. agrees to be bound by and co-operate in the implementation of this Deed.
    1. Consent and undertakings by the Commonwealth

The Commonwealth:

* + - 1. consents to the creation of the Security;
      2. agrees that none of:
         1. the creation or existence of the Security;
         2. the entry into of this Deed by the Operator;
         3. the appointment of any Enforcing Party to the Operator or a person who has Control over the Operator under the Security; or
         4. the exercise by Security Trustee or any Enforcing Party of any rights, powers or remedies in connection with this Deed or the Security (in compliance with the applicable provisions of this Deed (including compliance with clause [5] (Transfer following enforcement) in effecting a sale of an ownership interest in a person who has Control over the Operator)),

will, of itself:

* + - * 1. contravene or constitute a default or breach of the CISA; or
        2. entitle the Commonwealth to exercise any rights, powers or remedies to terminate the CISA;
      1. (enforcement) agrees that an Enforcing Party may, but need not, exercise all or any of the rights, powers and remedies, and perform all or any of the obligations of the Operator, in connection with the CISA, as if it were the Operator to the exclusion of the Operator; and
      2. (no assumption) agrees that an Enforcing Party will not be liable nor have any obligations, and will not be taken to have assumed any liability or obligations, in connection with the CISA as a result of the entry into of the Security or this Deed or the exercise of any rights, powers or remedies by an Enforcing Party in connection with the Security or this Deed. However, this does not:
         1. apply to any obligation of the Operator under the CISA expressly assumed by Security Trustee by written notice to the Commonwealth (with a copy to the Operator); or
         2. affect any liability or obligation of the Operator for acts and omissions of an Enforcing Party where the Enforcing Party is acting as the agent of the Operator.
    1. Notification by Security Trustee

The Security Trustee must notify the Commonwealth of:

* + - 1. any Event of Default as soon as it becomes aware of the same (together with details of that Event of Default); and
      2. any intention to exercise its rights under the Security to take enforcement action or appoint an Enforcing Party to do so.
  1. Termination Events – cure and termination
     1. Termination Event Notices to Security Trustee

If a Termination Event occurs, the Commonwealth agrees to:

* + - 1. give Security Trustee a copy of any Termination Event Notice and all other documents issued by the Commonwealth to the Operator in connection with the Termination Event at or about the same time as the notice is given to the Operator; and
      2. give the Enforcing Party copies of any information issued by the Commonwealth to the Operator under the CISA in connection with a Termination Event.
    1. Cure rights
       1. The parties agree that Security Trustee, or any other Enforcing Party, may but need not, take steps to cure, or procure the cure of, a Termination Event or (where relevant) prevent the occurrence of a Termination Event.
       2. The Commonwealth agrees that a Termination Event no longer exists under or for the purposes of the CISA after:
          1. it is cured or procured to be cured by Security Trustee or any other Enforcing Party; or
          2. it is taken to be cured in accordance with clause 4.6 (Deemed cure).
    2. Restriction on Termination
       1. The Commonwealth agrees that despite anything in the CISA and any rights, powers or remedies it may otherwise have (including at Law), it can and will only:
          1. Terminate; or
          2. give any notice which would (or with the expiration of time would) Terminate,

the CISA only in reliance on a Termination Event and only as expressly permitted by clause 4.4 (Termination).

* + - 1. Any actual or purported Termination of the CISA in breach of this clause 4.3 is ineffective.
      2. Clause 4.2 (Cure rights) and the rest of this clause 4.3 do not apply to any Termination or notice in respect of clause 27.1 (Termination for Convenience by the Commonwealth) of the CISA.
    1. Termination by the Commonwealth

The Commonwealth may terminate this Deed:

* + - 1. (**payment default**) in reliance on a Termination Event under the CISA which relates to a failure by the Operator to pay money due under the CISA, if the failure has not been cured within 10 Business Days after the applicable Cure Period Start Date;
      2. **(insolvency or Change in Control**) in reliance on a Termination Event under the CISA which is or relates to an Insolvency Event or a Change in Control:
         1. if an Enforcing Party has not been appointed (or become a Controller) to or over:

for only a Change in Control, shares in the Operator; or

the Operator’s rights under the CISA,

within 15 Business Days after the applicable Cure Period Start Date; and

* + - * 1. if having been so appointed, the Insolvency Event or Change in Control has not been cured within 365 days after the applicable Cure Period Start Date (or by any later date agreed to in writing by the Commonwealth in its absolute discretion);
      1. (**fraudulent project reports**) in reliance on a Termination Event which is an event set out in clause 27.2(h) (Termination by the Commonwealth for Operator Default) of the CISA, if an Enforcing Party has not satisfied, or procured the satisfaction of, all of the requirements in clause 27.2(h)(ii)(A) to (D) of the CISA within 20 Business Days after the applicable Cure Period Start Date;
      2. (**other** **events**) in reliance on a Termination Event under the CISA which is not described above, if:
         1. an Enforcing Party has not commenced remedying that Termination Event within 30 Business Days after the applicable Cure Period Start Date (or by any later date agreed to in writing by the Commonwealth in its absolute discretion); or
         2. if the Enforcing Party has commenced remedying that Termination Event within 30 Business Days after the applicable Cure Period Start Date (or by any later date agreed to in writing by the Commonwealth in its absolute discretion):

without prejudice to clause 4.4(d)(B), the Enforcing Party does not pursue that remedy in a diligent manner; or

in any event, the Enforcing Party has not remedied the relevant Termination Event within 60 Business Days after the applicable Cure Period Start Date (or by any later date agreed to in writing by the Commonwealth, acting reasonably); and

* + - 1. (**no cure**) in reliance on a Termination Event under the CISA, if Security Trustee notifies the Commonwealth in writing that it does not intend to take any steps or further steps to cure that Termination Event,

by written notice to the Operator and Security Trustee (given after the applicable requirement above is satisfied), if the Commonwealth is still entitled under the CISA to Terminate the CISA in reliance on the relevant event and which event remains uncured.

* + 1. Rights and obligations not affected

The Commonwealth agrees that if a Termination Event occurs, the Operator’s rights, and the Commonwealth’s obligations, under the CISA are not, and will not be, affected while Security Trustee or any other Enforcing Party is able to or is exercising any right, power or remedy (including those described in this clause 4 or in connection with any Security) in connection with that Termination Event.

* + 1. Deemed cure

The Commonwealth agrees that a Termination Event is taken to be cured under and for the purposes of the CISA and this Deed (as applicable):

* + - 1. if it relates to a failure to pay money due under the CISA, when an Enforcing Party has paid or procured the payment of the amount of that money to the Commonwealth;
      2. if it relates to a failure to do anything under the CISA, when an Enforcing Party has done, or procured to be done, that thing;
      3. if it is or relates to a Change in Control or an Insolvency Event, when an Enforcing Party has procured:
         1. the assignment, transfer or novation of (or any combination of these things to be done in respect of) the Operator’s rights and obligations under the CISA to a Transferee; or
         2. the transfer of the shares in the Operator to a Transferee,

in each case, in accordance with clause 5.1 (Transfer); and

* + - 1. for any other Termination Event or if Security Trustee reasonably considers that the Termination Event is not able to be cured, or will not be or is unlikely to be cured by the end of any applicable cure period provided under the CISA or this Deed, when an Enforcing Party makes arrangements (which may include the taking of steps to prevent a recurrence of the Termination Event or the payment of compensation to the Commonwealth (or both)) which are satisfactory to the Commonwealth.
  1. Transfer following enforcement
     1. Transfer

The Commonwealth agrees that after Security Trustee has commenced enforcing the Security in accordance with its terms, an Enforcing Party may:

* + - 1. transfer the shares in the Operator in accordance with clauses 29.1 (Assignment or Novation by the Operator) and 29.5 (Change in Control) of the CISA; or
      2. assign, transfer or novate (or do any combination of these things) in respect of the Operator’s rights and obligations under the CISA in accordance with clause 29.1 (Assignment or Novation by the Operator) of the CISA,

to any person (including Security Trustee) (**Transferee**), but not otherwise.

* + 1. Transfer documentation

The Commonwealth and the Operator agree to co-operate with Security Trustee and to execute all documents as are reasonably necessary to give effect to any assignment, transfer or novation (or any combination of these things) under clause 5.1 (Transfer).

* 1. GST
     1. Definitions and interpretation

Words and phrases which have a defined meaning in the GST Law have the same meaning when used in this clause 6, unless the contrary intention appears.

* + 1. GST exclusive consideration

Unless this Deed expressly states otherwise, all consideration to be provided under this Deed is exclusive of GST.

* + 1. No taxable supply

The parties have entered this Deed on the assumption that, in accordance with the principles set out in public GST ruling *GSTR 2001/6 – GST and non-monetary consideration*, that no party makes a taxable supply to any other party under the provisions of, or by agreeing to the obligations set out in, this Deed.

* + 1. GST gross-up

Notwithstanding clause 6.3 and subject to clause 6.5, if a party (**Supplier**) makes a supply under or in connection with this Deed on which GST is imposed, in whole or in part (not being a supply the consideration for which is specifically described in this Deed as inclusive of GST) then:

* + - 1. the consideration payable or to be provided for that supply under this Deed but for the application of this clause (**GST exclusive consideration**) is increased by, and the recipient of the supply (**Recipient**) must also pay to the Supplier, an amount equal to the GST payable on the supply (**GST Amount**); and
      2. the GST Amount must be paid to the Supplier by the Recipient without set off, deduction or requirement for demand, at the same time as the GST exclusive consideration is payable or to be provided, subject to the Supplier giving the Recipient a tax invoice in respect of that taxable supply.
    1. Non-monetary consideration

To the extent that consideration for a supply under this Deed includes non-monetary consideration, the parties agree to act in good faith to agree on the GST exclusive market value of the non-monetary consideration provided for the supply. In such circumstances, the parties agree to exchange tax invoices for their respective supplies and to set off any amounts payable on account of GST so that only the net amount of GST is payable to the appropriate party.

* + 1. Payments and reimbursements
       1. If a payment to a party under this Deed is a reimbursement or indemnification, calculated by reference to a loss, cost or expense incurred by that party, then the payment will be reduced by the amount of any input tax credit to which that party, or the representative member of a GST group of which that party is a member, is entitled for that loss, cost or expense.
       2. If a payment is calculated by reference to, or as a specified percentage of, another amount or revenue stream, that payment shall be calculated by reference to, or as a specified percentage of, the amount or revenue stream exclusive of GST.
    2. Adjustments

If an adjustment event arises in respect of a supply made under or in connection with this Deed, then:

* + - 1. the Supplier must issue an adjustment note to the Recipient within 7 days of the adjustment event occurring or otherwise as soon as it becomes aware of the adjustment event, outlining the revised amount of GST payable in respect of that supply (**Corrected GST Amount**);
      2. if the Corrected GST Amount is less than the previously attributed GST Amount, the Supplier shall refund the difference to the Recipient within 15 days of the adjustment note being issued by the Supplier; and
      3. if the Corrected GST Amount is greater than the previously attributed GST Amount, the Recipient shall pay the difference to the Supplier within 15 days of the adjustment note being issued by the Supplier.
    1. No Partnership

In reliance on Public GST Rulings GSTR 2003/13 and 2004/6, the parties acknowledge and agree that they do not intend to form a general law partnership or a tax law partnership in entering into this Deed.

* 1. Confidentiality
     1. Confidential Information not to be Disclosed
        1. Subject to clause 7.2, a party must not (and must procure its Associates not to) directly or indirectly disclose or make available any Confidential Information of the other party to a third party which would compromise the confidentiality of such Confidential Information, without the prior consent of the other party.
        2. In giving written consent to the disclosure of its Confidential Information, a party may impose such conditions as it thinks fit, and the other party agrees to comply with these conditions.
     2. Exceptions to obligations of Confidentiality

A party may disclose Confidential Information of the other party to the extent that the Confidential Information is:

* + - 1. disclosed to any person in connection with an exercise of rights or a dealing, or proposed dealing, with rights or obligations in connection with any Project Document or other Transaction Document but only to the extent that such a person has a need to know and agrees with the disclosing party to act consistently with this clause;
      2. disclosed to its Associates solely in order to comply with the obligations or to exercise rights in relation to the Project Documents or other Transaction Documents or to a Related Body Corporate for internal management purposes, in each but only to the extent that such a person has a need to know and agrees with the disclosing party to act consistently with this clause;
      3. to the extent required by Law, in connection with any legal or recognised dispute resolution process to which the relevant party is a party or authorised or required by the rules of any recognised stock exchange on which that party's shares are listed;
      4. disclosed by the Commonwealth:
         1. to a Minister or Parliament in accordance with statutory or portfolio duties or functions or for public accountability reasons including following a request by a Minister, Parliament or a House or a Committee of the Parliament of the Commonwealth;
         2. to any Government Agency where this services the Commonwealth's legitimate interests including to the Australian National Audit Office;
         3. AEMO or its Related Bodies Corporate and its or their Associates;
         4. to any person entitled to a licence or sublicence of Specified Materials rights pursuant to the CISA and its Associates;
      5. authorised or required by Law to be to be disclosed provided that:
         1. the party notifies the other party of the requirement to make that disclosure; and
         2. takes all reasonable steps to minimise the extent of the disclosure and to ensure the information is disclosed on a basis that the recipient agrees to maintain the confidentiality of the information;
      6. to:
         1. a bank or other financial institution (and its professional advisers) in connection with any existing or proposed loan or other financial accommodation or, or sought to be arranged by, the recipient of that information;
         2. any person who is proposing to acquire a direct or indirect interest in the party; or
         3. any Related Body Corporate of a party to this Deed,

provided the recipient agrees to act consistently with this clause;

* + - 1. in the case of disclosure by the Commonwealth, Knowledge Sharing Deliverables that have been categorised by the Operator as "public information" pursuant to clause 16 (Knowledge Sharing) of the CISA;
      2. to a rating agency;
      3. to the extent expressly permitted under this Deed; and
      4. as otherwise agreed by the other parties.
    1. Publicity
       1. Clause 39 (Publicity) of the CISA is incorporated into this Deed as if set out in full in this Deed, *mutatis mutandis*.
       2. Unless required by Law, the Security Trustee must not make any public announcements relating to the subject matter of any Project Document without the Commonwealth's prior written consent.
  1. Assignment and Novation
     1. Assignment or Novation by the Operator
        1. The Operator must not assign, novate, transfer of or otherwise deal with the Operator’s rights or obligations under, title to or interest in this Deed without the Commonwealth’s and Security Trustee's written consent.
        2. Prior to the Commencement Date, each of the Commonwealth and the Security Trustee may provide or withhold its consent under clause 8.1(a) at its absolute discretion.
        3. On and from the Commencement Date, each of the Commonwealth and the Security Trustee must not unreasonably withhold or delay its consent under clause 8.1(a) where :
           1. the assignee, novatee or transferee has the legal, commercial, financial and technical capability to comply with the Operator's obligations under this Deed; and
           2. the proposed assignee, novatee or transferee is solvent and reputable, does not have an interest which conflicts in a material way with the interests of the Commonwealth and there is no prohibition or restriction imposed by Law which would prevent or impact its ability to assume the rights and/or obligations of the assignor, novator or transferor;
           3. the proposed assignment, novation or transfer is not against the national interests, would not have a material adverse effect on the Project nor would increase the Liability of, or risks accepted by the Commonwealth under any Project Documents or in any other way in connection with the Project;
           4. the proposed assignee, novatee or transferee agrees to assume all obligations of the Operator arising from or in connection with this Deed:

including those which arise prior to and after the novation, transfer or dealing on terms reasonably acceptable to the Commonwealth and the Security Trustee; or

which arise after the novation, transfer or dealing and the outgoing Operator continues to remain responsible for those obligations of the outgoing Operator which arose prior to the novation, transfer or dealing, in each case on terms reasonably acceptable to the Commonwealth and the Security Trustee.

* + - 1. The Operator must not assign, novate, transfer or otherwise deal with its rights or obligations under, title to or interest in this Deed unless it also assigns, novates or otherwise transfers:
         1. its rights and obligations under, title to or interest in and its obligations under each other Project Document; and
         2. the Project and the Transaction Documents to which it is a party,

to the same person.

* + 1. Assignment or Novation by the Commonwealth
       1. The Commonwealth may assign, novate, transfer or otherwise deal with the Commonwealth's rights or obligations under, title to or interest in any Project Document and each of the Operator's and the Security Trustee's consent is hereby given to that assignment, novation, transfer or dealing where:
          1. the Commonwealth assigns, novates or transfers to or enters into a dealing with a Government Agency (including Clean Energy Financial Corporation and the Australian Renewable Energy Agency) but only to the extent which it has been guaranteed by the Commonwealth; and;
          2. the Commonwealth notifies each of the Operator and the Security Trustee no later than 20 Business Days after the relevant assignment, novation, transfer or dealing and that notice identifies that assignee, novatee, transferee or Government Agency and the terms and conditions of that assignment, novation, transfer or dealing.
       2. The Commonwealth must novate its rights and obligations under this Deed to a person to whom it novates its rights and obligations under the CISA.
       3. The Commonwealth must not otherwise assign, novate, transfer or otherwise deal with the Commonwealth's rights or obligations under, title to or interest in any Project Document without the prior written consent of each of the Operator and the Security Trustee (such consent not to be unreasonably withheld or delayed).
    2. Non-compliance and release
       1. Any purported assignment, novation, transfer or dealing by the Operator, Security Trustee or the Commonwealth that is not in compliance with clauses 1.13, 8.1 or 8.2 will not be effective as between the parties to this Deed.
       2. Without limiting clauses 1.13 and 8.3(a), if the Commonwealth or the Operator assigns, novates, transfers or otherwise deals with its rights and obligations under, title to or interest in any Project Document in accordance with this clause 8.1 or 8.2 (as applicable), the other parties each agree to release the first party from its obligations under the Project Documents arising on and from the date of the assignment, novation, transfer or dealing to the extent that those obligations are assumed in writing by the assignee, novatee, transferee or person receiving the dealing on terms reasonably acceptable to the other parties.
  1. Governing Law
     1. Governing Law and jurisdiction

The Law in force in the Relevant Jurisdiction governs this Deed. The parties irrevocably submit to the non-exclusive jurisdiction of the courts of the Relevant Jurisdiction and the courts competent to determine appeals from the courts of the Relevant Jurisdiction, with respect to any proceedings which may be brought in connection with this Deed.

* + 1. Serving documents

Without preventing any other method of service, any document in an action in connection with this Deed may be served on a party by being delivered or left at that party’s address for service of notices under clause 10.2 (Delivery).

* 1. Notices and other communications
     1. Form
        1. Unless this Deed expressly states otherwise, all notices, demands, certificates, consents, approvals, waivers and other communications in connection with this Deed (**Communications**) must be in writing and signed by the sender (if an individual) or a director, secretary or any other person nominated by a party to act as an authorised officer of the sender.
        2. All Communications (other than email communications) must also be marked for the attention of the person referred to in the Details (or, if the recipient has notified otherwise, then marked for attention in the way last notified).
        3. Email Communications must state the first and last name of the sender and are taken to be signed by the named sender.
     2. Delivery
        1. Communications must be:
           1. left at the address referred to in the Details;
           2. sent by regular ordinary post (airmail if appropriate) to the address referred to in the Details; or
           3. sent by email to the email address referred to in the Details provided however that email must not be used for any termination notice issued pursuant to this Agreement.
        2. If the intended recipient has notified changed contact details, Communications must be sent to the changed contact details.
     3. When effective

Communications take effect from the time they are received or taken to be received under clause 10.4 (When taken to be received) (whichever happens first) unless a later time is specified in the Communication.

* + 1. When taken to be received

Communications are taken to be received:

* + - 1. if sent by prepaid express post, 5 Business Days after posting (or 8 Business Days after the date of posting by airmail to if sent from one country to another);
      2. if sent by email:
         1. when the sender receives an automated message confirming delivery; or
         2. 4 hours after the time the email is sent (as recorded on the device from which the sender sent the email) unless the sender receives an automated message within that 4 hour period that the delivery failed,

whichever happens first.

* + 1. Receipt outside business hours

Despite anything else in this clause 10, if Communications are received or taken to be received under clause 10.4 (When taken to be received) after 5.00pm on a Business Day or on a non-Business Day, they are taken to be received at 9.00am on the next Business Day. For the purposes of this clause, the place in the definition of Business Day in the CISA is taken to be the place specified in the Details as the address of the recipient and the time of receipt is the time in that place.

* 1. General
     1. Duration of this Deed

Security Trustee must give notice to the Commonwealth (copied to the Operator) if it has fully and finally discharged all of the Security. This Deed terminates (without prejudice to any accrued right or liability) upon the giving of the notice.

* + 1. Variation and waiver

A provision of this Deed, or right, power or remedy created under it, may not be waived or varied except in writing signed by the parties to this Deed.

* + 1. Consents, approvals or waivers
       1. A failure to exercise or enforce, a delay in the exercise or enforcement of or the partial exercise or enforcement of a right provided by Law or under this Deed by a party does not preclude, or operate as a waiver of, the exercise or enforcement, or further exercise or enforcement, of that or any other right provided by Law or under this Deed.
       2. By giving any consent, approval or waiver a party does not give any representation or warranty as to any circumstance in connection with the subject matter of the consent, approval or waiver.
       3. No waiver of a breach of a term of this Deed operates as a waiver of another breach of that term or of a breach of any other term of this Deed.
    2. Discretion in exercising rights

Unless this Deed expressly provides otherwise, a party may exercise a right, power or remedy or give or refuse its consent, approval or a waiver in connection with this Deed in its absolute discretion (including by imposing conditions).

* + 1. Partial exercising of rights

Unless this Deed expressly states otherwise, if a party does not exercise a right, power or remedy in connection with this Deed fully or at a given time, they may still exercise it later.

* + 1. Remedies cumulative

The rights, powers and remedies of a party in connection with this Deed are in addition to other rights, powers and remedies given in any other document or given by Law independently of this Deed.

* + 1. Supervening Law

Any present or future Law which operates to vary the obligations of a party in connection with this Deed with the result that another party’s rights, powers or remedies are adversely affected (including by way of delay or postponement) is excluded except to the extent that its exclusion is prohibited or rendered ineffective by Law.

* + 1. Counterparts
    2. This Deed may be executed in any number of counterparts or copies, each of which may be executed by physical signature in wet ink or electronically (whether in whole or part). A party who has executed a counterpart of this Deed may exchange it with another party (the **Other Party**) by:
       1. emailing a copy of the executed counterpart to the Other Party; or
       2. utilising an electronic platform (including DocuSign) to circulate the executed counterpart,

and will be taken to have adequately identified themselves by so emailing the copy to the Other Party or utilising the electronic platform.

* + 1. Each party consents to signatories and parties executing this Deed by electronic means and to identifying themselves in the manner specified in this clause.
    2. Each counterpart constitutes an original (whether kept in electronic or paper form), all of which together constitute one instrument as if the signatures (or other execution markings) on the counterparts or copies were on a single physical copy of this Deed in paper form. Without limiting the foregoing, if any of the signatures or other markings on behalf of one party are on different counterparts or copies of this Deed, this shall be taken to be, and have the same effect as, signatures on the same counterpart and on a single copy of this Deed.
    3. Entire agreement

This Deed and the CISA together constitute the entire agreement of the parties about their subject matter and supersede all previous agreements, understandings and negotiations on that subject matter.

* + 1. Expenses and no liability for loss
    2. Unless otherwise expressly provided in this Deed, each party must pay its own costs and expenses in connection with negotiating, preparing, executing and performing this Deed.
    3. The Operator agrees to pay the Commonwealth’s and the Security Trustee's legal and other costs and expenses (including any stamp duty) in connection with the negotiation, preparation, execution and completion of this Deed.
    4. Unless this Deed expressly states otherwise, the Security Trustee will not be liable to any party for any Loss in relation to the exercise or attempted exercise of, failure to exercise, or delay in exercising, a right, power or remedy in connection with this Deed.
    5. Rules of construction

No rule of construction applies to the disadvantage of a party because that party was responsible for the preparation of, or seeks to rely on, this Deed or any part of it.

* + 1. Severability

If the whole or any part of a provision of this Deed is void, unenforceable or illegal in a jurisdiction, then it is severed for that jurisdiction. The remainder of this Deed has full force and effect and the validity or enforceability of that provision in any other jurisdiction is not affected. This clause 11.12 has no effect if the severance alters the basic nature of this Deed or is contrary to public policy.

* + 1. Survival

Each of the following will survive the expiry or termination of this Deed:

* + - 1. clauses 1, 7 and 11 and Schedule 5;
      2. any provision that is required to enable a party to exercise rights accrued prior to the expiry, recission or termination of this Deed; and
      3. any provision which (expressly or by implication) by its nature is intended to survive the expiry, recission or termination of this Deed.
    1. Proportionate liability

The operation of Part IVAA (Proportionate Liability) of the *Wrongs Act 1958* (Vic) and Part 3 of *the Law Reform (Contributory Negligence and Apportionment of Liability) 2001* (SA) are excluded in relation to all and any rights of either party under this Deed, whether such rights are sought to be enforced in contract, tort or otherwise.

* + 1. Limitation of the Commonwealth liability

Despite any other provision of this Deed, the parties acknowledge and agree that the Commonwealth’s total aggregate liability in connection with this Deed and the CISA at any time, will be no greater than the Commonwealth’s total aggregate liability in connection with the CISA at that time (assuming the CISA is enforceable in accordance with its terms) and will be subject to the same limitations of liability set out in the CISA.

* + 1. Further steps

The Operator and the Commonwealth agree, at the Operator’s expense, to do anything another party reasonably asks (such as obtaining consents (in relation to the Operator only), signing and producing documents, producing receipts and getting documents completed and signed) as may be necessary or desirable to:

* + - 1. give full effect to the provisions of this Deed and the transactions contemplated by it; and
      2. without limiting clause 11.16(a), ensure any assignment, transfer or novation (or any combination of them) contemplated by clause 5 (Transfer following enforcement), and any document the subject or product of any such dealing, is in registerable form, enforceable and registered with the agreed priority.

**EXECUTED** as a deed

Signing page

**EXECUTED** as an agreement.

**[Drafting note: Execution blocks to be inserted into execution version.]**

|  |  |  |
| --- | --- | --- |
| **Signed[insert sealed and delivered, if applicable]** by [insert name of signatory] in the presence of |  |  |
|  |  |  |
|  |  |  |
| Signature of witness |  | [insert name of signatory] |
|  |  |  |
| Name of witness (print) |  |  |

|  |  |  |
| --- | --- | --- |
| **Signed[insert sealed and delivered, if applicable]** by [insert name of signatory] in the presence of |  |  |
|  |  |  |
|  |  |  |
| Signature of witness |  | [insert name of signatory] |
|  |  |  |
| Name of witness (print) |  |  |

|  |  |  |
| --- | --- | --- |
| **Signed [insert, sealed and delivered, if applicable]** by [insert name of signatory] in the presence of |  |  |
|  |  |  |
|  |  |  |
| Signature of witness |  | [insert name of signatory] |
|  |  |  |
| Name of witness (print) |  |  |

1. – Form of Performance Security

**Form of Performance Bond**

[***insert Lender Letterhead***]

[***Date***]

**Performance Bond No. [*insert*]**

|  |  |
| --- | --- |
| **Lender** | [***Lender***] |
| **Beneficiary** | **The Commonwealth of Australia** represented by the **Department of Climate Change, Energy, the Environment and Water** of [# insert] |
| **Operator** | [insert name of ***Operator***] of [***insert address***] |
| **Agreement** | Capacity Investment Scheme Agreement (**Project**) dated on [**insert** ***date***] |
| **Sum** | [***insert*** ***Amount***] |

At the request of the Operator, and in consideration of the Beneficiary accepting this undertaking in respect of the Agreement, the Lender irrevocably and unconditionally undertakes to pay to the Beneficiary on demand and without deduction or set off any sum or sums which may from time to time be demanded by the Beneficiary to a maximum aggregate sum of the Sum.

This undertaking is to continue until notification has been received from the Beneficiary that the Sum is no longer required by the Beneficiary or until this undertaking is returned to the Lender or until payment to the Beneficiary by the Lender of the whole of the Sum.

Should the Lender be notified in writing, purporting to be signed by or on behalf of the Beneficiary that the Beneficiary desires payment to be made of the whole or any part or parts of the Sum, it is irrevocably and unconditionally agreed that the Lender must make the payment or payments to the Beneficiary immediately, in Australian dollars and in same day funds without reference to the Operator and notwithstanding any notice given by the Operator not to pay same.

Provided always that the Lender may at any time without being required so to do pay to the Beneficiary the Sum less any amount or amounts it may previously have paid under this undertaking or such lesser sum as may be required and specified by the Beneficiary and thereupon the liability of the Lender hereunder shall immediately cease.

The Beneficiary's rights under this undertaking may not be assigned, novated or transferred, other than to an entity to which the Beneficiary is assigning, novating or transferring the Beneficiary's rights under the Agreement (where such assignment, novation or transfer is in accordance with the terms of the Agreement).

This undertaking is governed by the laws of [insert as appliable Victorian/New South Wales]. Each of the Lender, the Operator and the Beneficiary irrevocably and unconditionally submits to the exclusive jurisdiction of the courts of [insert as applicable Victorian/New South Wales] and any courts which have jurisdiction to hear appeals from any of those courts and waives any right to object to any proceedings being brought in those courts.

Signed for and on behalf of

[***Lender***]

1. - Commonwealth Policy and Other Requirements

The Operator is required to comply with the Commonwealth policies and other requirements as set out in this Schedule 11. Please note that some of the Commonwealth policies identified below have been modified to suit the subject matter of this Agreement and the Operator is only required to comply with that part of the Commonwealth policy and requirements referred to and set out below.

* 1. Taxation and Shadow Economy Policy
     1. Definitions

In this section 1:

* 1. **Satisfactory**, in respect of a Statement of Tax Record, means the Statement of Tax Record meets the conditions set out in Part 6.b of the Shadow Economy Policy or, if the circumstances in Part 6.c of the Shadow Economy Policy apply, the conditions set out in Part 8 of the Shadow Economy Policy;
  2. **Statement of Tax Record** means a statement of tax record issued by the Australian Taxation Office following an application made in accordance with the process set out at <https://www.ato.gov.au/Business/Bus/Statement-of-tax-record/?page=1#Requesting_an_STR>;.
  3. **Shadow Economy Policy** means the *Shadow economy – increasing the integrity of government procurement: Procurement connected policy guidelines March 2019* available at *https://treasury.gov.au/publication/p2019- t369466;* and
  4. **Valid** means valid in accordance with Part 7.e of the Shadow Economy Policy.
     1. Taxation
        1. The Operator must comply with all applicable Laws relating to taxation.
        2. The Operator must ensure that any first tier Subcontract (namely those which the Operator enters into directly with a Subcontractor) for the purposes of fulfilling its obligations under this Agreement imposes on the first tier Subcontractor the same obligations that the Operator has under this section 1.2.
     2. Valid Statement of Tax Record
        1. In this section 1.3, **Required Entity** includes each of the applicable entities listed in the table below. If more than one row of the table below applies to the Operator, Required Entity includes all relevant entities listed in each row that applies to the Operator.

|  |  |
| --- | --- |
| **If the Operator is:** | **Required Entity includes:** |
| a body corporate or natural person | that body corporate or person. |
| a trustee acting in its capacity as trustee of a trust | a) the Operator; and  b) the trust. |
| a member of a Consolidated Group | a) the Operator; and  b) the head company in the Consolidated Group. |
| a member of a GST Group | a) the Operator; and  b) the GST Group representative. |

* + - 1. The Operator:
         1. warrants that at the date of this Agreement each Required Entity holds a Valid and Satisfactory Statement of Tax Record; and
         2. must ensure that each Required Entity holds a Valid and Satisfactory Statement of Tax Record at all times from the date of this Agreement until the end of the Term.
      2. The Operator, in relation to each Subcontractor it has engaged to deliver goods or services with an estimated value of over $4 million (Indexed) (GST inclusive):
         1. warrants that such Subcontractor holds a Satisfactory Statement of Tax Record for the Subcontractor that was Valid at the commencement of the term of the relevant Subcontract;
         2. must ensure that such Subcontractor holds a Valid and Satisfactory Statement of Tax Record at all times during the term of the relevant Subcontract; and
      3. must retain a copy of any Statement of Tax Record held by such Subcontractor.
      4. The Commonwealth may, by notice in writing to the Operator at any time, require the Operator to provide a copy of any Statement of Tax Record held or retained by the Operator or required to be held or retained by the Operator under this section 1.3. The Operator must provide a copy of the relevant Statement of Tax Record held or retained by the Operator to the Commonwealth within 5 Business Days after receiving the notice under this section 1.3(d).
      5. The Operator must notify the Commonwealth where it is in breach of this section 1 and that notice must be provided by the Operator to the Commonwealth within 10 Business Days after the Operator becomes aware of that breach.
  1. Workplace Gender Equality
     1. Workplace Gender Equality
        1. In this section 2.1, **WGE Act** means the *Workplace Gender Equality Act* (Cth) 2012.
        2. The Operator must:
           1. comply with its obligations (if any) under the WGE Act;
           2. immediately notify the Commonwealth of any non-compliance by the Operator with the WGE Act; and
           3. if requested by the Commonwealth at any time, provide a current letter of compliance with the WGE Act issued by the Workplace Gender Equality Agency.
        3. The Operator must not enter into a Subcontract with a Subcontractor named by the Workplace Gender Equality Agency as an employer currently not complying with the WGE Act.
        4. The Operator must ensure that any Subcontract entered into by the Operator for the purposes of fulfilling its obligations under this Agreement imposes on the Subcontractor the same obligations that the Operator has under this section 2.1, including this requirement to impose obligations on any further subcontractor.
  2. Modern Slavery
     + 1. The Operator must comply with the *Modern Slavery Act 2018* (Cth)). The Operator must take reasonable steps to identify, assess and address risks of Modern Slavery (as defined in the *Modern Slavery Act 2018* (Cth)) practices in its operations and supply chains used by it and its Subcontractors in the procurement or provision of the goods and/or services in relation to the Project.
       2. If at any time the Operator becomes aware of Modern Slavery (as defined in the *Modern Slavery Act 2018* (Cth)) practices in its operations and supply chains used by it and its Subcontractors in the procurement or provision of the goods and/or services in relation to the Project, the Operator must as soon as reasonably practicable take all reasonable action to address or remove these practices, including where relevant by addressing any practices of other entities in its supply chains.
  3. Workplace Laws
     + 1. The Operator must perform its obligations under this Agreement in such a way that the Operator does not breach, and the Commonwealth is not placed in breach of, any applicable workplace Laws, including work health and safety, workplace relations or workers' compensation Laws.
       2. The Operator must comply with any request, policy or direction issued by the Commonwealth and otherwise cooperate with the Commonwealth in relation to any action taken by the Commonwealth required or authorised by applicable workplace Laws, including work health and safety, workplace relations or workers' compensation Laws at no cost to the Commonwealth.
       3. The Operator must ensure that any Subcontract entered into by the Operator for the purposes of fulfilling its obligations under this Agreement after the Signing Date imposes on the Subcontractor the same obligations that the Operator has under this section 4, other than this requirement to impose obligations on any further subcontractor.
  4. Significant Events
     1. Definition

In this section 5, **Significant Event** means:

* + - 1. any adverse comments or findings made by a court, commission, tribunal or other statutory or professional body regarding the conduct or performance of the Operator or its Associates that impacts or could be reasonably perceived to impact on their professional capacity, capability, fitness or reputation;
      2. any other significant matters, including the commencement of legal, regulatory or disciplinary action involving the Operator or its Associates, that may adversely impact on compliance with Commonwealth policy, applicable Laws or the Commonwealth’s reputation;
      3. any unsettled judicial decisions against the Operator (including in or related to overseas jurisdictions relating to employee entitlements where the employee entitlements remain unpaid (but excluding judgments under appeal or instances where the period for appeal or payment/settlement has not expired); or
      4. any non-compliance by the Operator or its Associates any judgment against that person from any court or tribunal (including overseas jurisdictions but excluding judgments under appeal or instances where the period for appeal or payment/settlement has not expired) relating to a breach of applicable workplace Laws, including workplace relations law, work health and safety law or workers’ compensation law.
    1. No existing Significant Event

The Operator warrants and represents that there is no Significant Event in relation to the Operator and its Associates as at the Signing Date.

* + 1. Notice of Significant Event
       1. The Operator must immediately upon becoming aware of a Significant Event in relation to the Operator or its Associates, notify the Commonwealth in writing, providing:
          1. a summary of the Significant Event, including the date or dates on which it occurred and the date on which the Operator became aware of it; and
          2. details of the relevant Operator and/or its Associates involved in the Significant Event.
       2. If, prior to the Operator providing notice under section 5.3(a), the Commonwealth notifies the Operator in writing that an event or circumstance is to be considered a Significant Event for the purposes of this section 5**,** the Operator must notify the Commonwealth in writing as if section 5.3(a) applied, within 3 Business Days after receiving the notice issued under this section 5.3(b).
       3. Where reasonably requested by the Commonwealth, the Operator must, within 3 Business Days after the request, provide the Commonwealth with additional information in writing regarding a Significant Event, to the extent that information is known by or reasonably available to the Operator.
    2. Commonwealth response to a Significant Event

If the Commonwealth is notified of a Significant Event pursuant to section 5.3(a) or notifies the Operator of a Significant Event pursuant to section 5.3(b), the Commonwealth may:

* + - 1. notify the Operator that no further action in relation to the Significant Event is required;
      2. request the Operator to submit a remediation plan to the Commonwealth; or
      3. acting reasonably, determine that the Significant Event is of such a serious or significant nature that it is not appropriate in the circumstances for the Operator to continue as a party to this Agreement, in which case the Commonwealth may terminate this Agreement in accordance with clause 22.2**.**
    1. Remediation plan
       1. If notified by the Commonwealth pursuant to section 5.4(b), the Operator must prepare a draft remediation plan and submit that draft plan to the Commonwealth for approval within 10 Business Days after receipt of that request.
       2. A draft remediation plan prepared by the Operator under section 5.5(a) must include the following information:
          1. how and the timeframe within which the Operator will address the Significant Event in the context of this Agreement and the Project, including confirmation that the implementation of the remediation plan will not in any way impact this Agreement or the Project or compliance by the Operator with its other obligations under this Agreement or otherwise at Law;
          2. how the Operator will ensure events or circumstances similar to the Significant Event do not occur again; and
          3. any other matter reasonably requested by the Commonwealth.
       3. The Commonwealth must review the draft remediation plan and may:
          1. approve the draft remediation plan;
          2. notify the Operator of the details of any changes that the Commonwealth considers are reasonably required to the draft remediation plan; or
          3. reject the draft remediation plan if the Commonwealth, acting reasonably, considers that the draft remediation plan is unsatisfactory having regard to the nature of the Significant Event and the likelihood that the draft remediation plan could address the matters raised by the Significant Event. If this applies, the Commonwealth will notify the Operator in writing of that fact, and that the failure to provide a satisfactory remediation plan will be a failure to comply in a material respect with an obligation under this Agreement for the purposes of clause 22.2(e).
       4. The Operator must make any changes to the draft remediation plan reasonably requested by the Commonwealth and resubmit the draft remediation plan to the Commonwealth for approval within 3 Business Days after the request unless otherwise agreed in writing by the Commonwealth. This section 5.5(d) will also apply to any resubmitted draft remediation plan.
       5. The Commonwealth must review the draft resubmitted remediation plan and may:
          1. approve the draft remediation plan;
          2. notify the Operator of the details of any changes that the Commonwealth considers are reasonably required to the draft remediation plan; or
          3. reject the draft remediation plan if the Commonwealth, acting reasonably, considers that the draft remediation plan is unsatisfactory having regard to the nature of the Significant Event and the likelihood that the draft remediation plan could address the matters raised by the Significant Event. If this applies, the Commonwealth will notify the Operator in writing of that fact, and that the failure to provide a satisfactory remediation plan will be a failure to comply in a material respect with an obligation under this Agreement for the purposes of clause 22.2(e).
       6. Without limiting its other obligations under this Agreement, the Operator must comply with the approved remediation plan or approved resubmitted remediation plan.
       7. The Operator must provide reports and other information about the Operator's progress in implementing the approved remediation plan as reasonably requested by the Commonwealth and within the time reasonably requested by the Commonwealth.
       8. A failure by the Operator to comply with its obligations under this section 5 will be a failure to comply in a material respect with an obligation under this Agreement for the purposes of clause 22.2(e).
    2. General
       1. The Commonwealth's rights under this section 5 are in addition to and do not otherwise limit or affect any other rights the Commonwealth may have under this Agreement or otherwise at Law.
       2. The performance by the Operator of its obligations under this section 5 will be at no additional cost to the Commonwealth.
       3. The Commonwealth may, in addition to any of its other rights or remedies under this Agreement or otherwise at Law, take into account the occurrence of a Significant Event at any time, including when:
          1. conducting future tenders or procurement processes;
          2. deciding whether to consent to any changes to Key Subcontractors;
          3. exercising any rights of the Commonwealth in relation to access, audit, or the treatment of documentation under or in connection with this Agreement; and
          4. deciding whether to exercise any rights in relation to termination of this Agreement.
  1. Archives Act
     + 1. In this section 6, **Archives Act** means the *Archives Act* *1983* (Cth).
       2. The Operator acknowledges that the Commonwealth is the owner of certain records relating to the Project (including those required to be delivered to the Commonwealth in accordance with this Agreement) that are created or maintained by the Operator and that these records are to be dealt with in accordance with the Archives Act.
       3. The Operator must not take any action which would cause the Commonwealth to be in breach of its obligations under the Archives Act.
       4. The Operator must comply with any reasonable request, policy or direction issued by the Commonwealth and otherwise cooperate with the Commonwealth in relation to any action taken by the Commonwealth required or authorised by the Archives Act at no cost to the Commonwealth.
       5. The Operator must ensure that any Subcontract entered into by the Operator for the purposes of fulfilling its obligations under this Agreement imposes on the Subcontractor the same obligations that the Operator has under this section 6, including this requirement to impose obligations on any further subcontractor.
       6. The Operator's obligations under this section 6 shall survive termination or expiry of this Agreement.
  2. National Anti-Corruption Commission
     + 1. In this section 7, **NACC Act** means the *National Anti‑Corruption Commission Act 2022* (Cth).
       2. The Operator must comply with any reasonable request, policy or direction issued by the Commonwealth and otherwise cooperate with the Commonwealth in relation to any action taken by the Commonwealth required or authorised by the NACC Act.
       3. The Operator must ensure that any Subcontract entered into by the Operator for the purposes of fulfilling its obligations under this Agreement imposes on the Subcontractor the same obligations that the Operator has under this section 7, including this requirement to impose obligations on any further subcontractor.
       4. The Operator's obligations under this section 7 shall survive termination or expiry of this Agreement.
  3. Public Interest Disclosure
     + 1. In this section 8, **PID Act** means the Public Interest Disclosure Act 2013 (Cth).
       2. The Operator must comply with any reasonable request, policy or direction issued by the Commonwealth and otherwise cooperate with the Commonwealth in relation to any action taken by the Commonwealth required or authorised by the PID Act.
       3. The Operator must ensure that any Subcontract entered into by the Operator after the Signing Date for the purposes of fulfilling its obligations under this Agreement imposes on the Subcontractor the same obligations that the Operator has under this section 8, other than this requirement to impose obligations on any further subcontractor.
       4. The Operator's obligations under this section 8 shall survive termination or expiry of this Agreement.
  4. Criminal Code
     + 1. In this section 9, **Criminal Code** means *Criminal Code Act* *1995* (Cth).
       2. The Operator acknowledges that the giving of false or misleading information to the Commonwealth is a serious offence under section 137.1 of the schedule to the Criminal Code.
       3. The Operator acknowledges that unauthorised disclosure of security-classified information is an offence and that there are Laws, including the Criminal Code which contain provisions relating to the protection of certain information and sets out the penalties for the unauthorised disclosure of that information.
       4. The Operator must ensure that any Subcontract entered into by the Operator for the purposes of fulfilling its obligations under this Agreement imposes on the Subcontractor the same obligations that the Operator has under this section 9, including this requirement to impose obligations on any further subcontractor.
       5. The Operator's obligations under this section 9 shall survive termination or expiry of this Agreement.
  5. Prohibited dealings
     + 1. The Operator must ensure that the Operator and any individuals, persons, entities or organisations involved in the Project, including its Associates, are not:
          1. directly or indirectly engaged in preparing, planning, assisting or fostering a terrorist act;
          2. listed terrorist organisations for the purposes of the *Criminal Code Act 1995* (Cth) (details of listed terrorist organisations are available at https://www.nationalsecurity.gov.au/what-australia-is-doing/terrorist-organisations/listed-terrorist-organisations );
          3. subject to sanctions or similar measures under the *Charter of the United Nations Act 1945* (Cth) or the *Autonomous Sanctions Act 2011* (Cth) (details of individuals and entities are available at: https://dfat.gov.au/international-relations/security/sanctions/Pages/consolidated-list.aspx);
          4. listed on the 'World Bank's Listing of Ineligible Firms and Individuals' posted at: https://www.worldbank.org/en/projects-operations/procurement/debarred-firms;
          5. owned, controlled by, acting on behalf of, or at the direction of individuals, persons, entities or organisations referred to in section 10(a)(i) to 10(a)(iv); or
          6. providing direct or indirect support, resources or assets (including any grant monies) to individuals, persons, entities or organisations referred to in section 10(a)(i) to 10(a)(iv).
       2. If the Operator becomes aware that there are reasonable grounds to suspect it or any of its Associates has or may have contravened any part of section 10(a), the Operator must:
          1. notify the Commonwealth and confirm that information in writing as soon as possible, which must be no later than within 24 hours;
          2. immediately take all reasonable action to mitigate the risks; and
          3. take any other action required by the Commonwealth.
       3. The Operator must ensure that any Subcontract entered into by the Operator for the purposes of fulfilling its obligations under this Agreement imposes on the Subcontractor the same obligations that the Operator has under this section 10, including this requirement to impose obligations on any further subcontractor.
  6. Environment
     + 1. The Operator shall perform its obligations under this Agreement in such a way that the Commonwealth is not placed in breach of any applicable environmental Laws, including the *Environment Protection and Biodiversity Conservation Act* *1999* (Cth).
       2. The Operator must comply with any reasonable request, policy or direction issued by the Commonwealth and otherwise cooperate with the Commonwealth in relation to any action taken by the Commonwealth required or authorised by applicable environmental Laws, including the *Environment Protection and Biodiversity Conservation Act* *1999* (Cth).
       3. The Operator must ensure that any Subcontract entered into by the Operator for the purposes of fulfilling its obligations under this Agreement imposes on the Subcontractor the same obligations that the Operator has under this section 11, including this requirement to impose obligations on any further subcontractor.
       4. The Operator's obligations under this section 11 shall survive termination or expiry of this Agreement.
  7. Privacy
     + 1. In this section 12**,** **Privacy Act** means the *Privacy Act 1988* (Cth).
       2. The Operator shall perform its obligations under this Agreement in such a way that the Commonwealth is not placed in breach of any applicable privacy Laws, including the Privacy Act and the "Australian Privacy Principles" as defined in the Privacy Act.
       3. The Operator must comply with any reasonable request, policy or direction issued by the Commonwealth and otherwise cooperate with the Commonwealth in relation to any action taken by the Commonwealth required or authorised by applicable privacy Laws, including the including the Privacy Act and the "Australian Privacy Principles" as defined in the Privacy Act.
       4. The Operator must ensure that any Subcontract entered into by the Operator for the purposes of fulfilling its obligations under this Agreement imposes on the Subcontractor the same obligations that the Operator has under this section 12, including this requirement to impose obligations on any further subcontractor.
       5. The Operator's obligations under this section 12 shall survive termination or expiry of this Agreement.
  8. Fraud
     + 1. In this section 13, **Fraud** means dishonestly obtaining a benefit from the Commonwealth or causing a loss to the Commonwealth by deception or other means and includes alleged, attempted, suspected or detected fraud.
       2. The Operator must take all reasonable steps to prevent and detect Fraud in relation to the performance of this Agreement and the Project.
       3. The Operator acknowledges the occurrence of Fraud in relation to the performance of this Agreement and the Project will constitute a breach of this Agreement.
       4. If an investigation finds that the Operator or any of its Associates have committed Fraud, or the Operator has failed to take reasonable steps to prevent Fraud in relation to the performance of this Agreement and the Project, the Operator must reimburse or compensate the Commonwealth in full.
       5. The Operator must ensure that any Subcontract entered into by the Operator for the purposes of fulfilling its obligations under this Agreement imposes on the Subcontractor the same obligations that the Operator has under this section 13, including this requirement to impose obligations on any further subcontractor.
       6. The Operator's obligations under this section 13 shall survive termination or expiry of this Agreement.

Signing page

**EXECUTED** as an agreement.

Each signatory executing this Agreement (electronically or otherwise) intends by that execution to be bound by this Agreement, and where the signatory has signed as an officer or attorney of a party, for that party to be bound by this Agreement.

|  |  |  |
| --- | --- | --- |
| **Signed** for and on behalf of **the Commonwealth of Australia** as represented by the Department of Climate Change, Energy, the Environment and Water by its duly authorised delegate in the presence of: |  |  |
|  |  |  |
|  |  |  |
| Signature of witness |  | Signature of delegate |
|  |  |  |
| Name of witness (print) |  | Name of delegate (print) |

**The Operator**

|  |  |  |
| --- | --- | --- |
| **Executed** by **[**insertName of company**]** in accordance with Section 127 of the *Corporations Act 2001* |  |  |
|  |  |  |
|  |  |  |
| Signature of director |  | Signature of director/company secretary  (Please delete as applicable) |
|  |  |  |
| Name of director (print) |  | Name of director/company secretary (print) |